## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Kalchini | Alipurduar Division | BHATPARA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14212 | New | Providing balance FHTC from existing distribution system as per specification for BHATPARA TG PWSS under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000315/2023-2024 | 2185/ALD | 06/10/2023 | 05/12/2023 | MAHENDRA CHHETRI | 17.77 | 0 | 0 | 0
2 | ALIPURDUAR | Kalchini | Alipurduar Division | BHATPARA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14212 | New | Material Requisition To Resource Division |  |  | RTOR000025/2023-2024 | 1270/ALD | 11/08/2023 | 11/08/2023 | Resource Division | 17.99 | 0 | 0 | 0
3 | ALIPURDUAR | Kalchini | Alipurduar Division | BHATPARA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14212 | New | Material Requisition To Resource Division |  |  | RTOR000086/2023-2024 | 110/ALD | 10/01/2024 | 10/01/2024 | Resource Division | 14.3 | 0 | 0 | 0
4 | ALIPURDUAR | Kalchini | Alipurduar Division | BHATPARA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14212 | New | Material Requisition To Resource Division |  |  | RTOR000075/2023-2024 | 99/ALD | 10/01/2024 | 10/01/2024 | Resource Division | 14.3 | 0 | 0 | 0
5 | ALIPURDUAR | Kalchini | Alipurduar Division | BHATPARA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14212 | New | Material Requisition To Resource Division |  |  | RTOR000032/2024-2025 | 4248/ALD | 13/12/2024 | 13/12/2024 | Resource Division | 3.63 | 0 | 0 | 0
6 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | BHATPARA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14212 | New | New Service connection for Bhatpara TG PWSS, P/H-II |  |  | BILL/02409/2023-2024 | BP-2023-24-532 | 11/01/2024 | 11/01/2024 | WBSEDCL | 5.26 | 0 | 0 | 0
7 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | BHATPARA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14212 | New | New Service Connection Charge for Bhatpara TG PWSS P/HNO-I |  |  | BILL/02636/2023-2024 | BP-2023-24-601 | 15/02/2024 | 15/02/2024 | WBSEDCL | 21.27 | 0 | 0 | 0
8 | ALIPURDUAR | Kalchini | Alipurduar Division | BHATPARA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14212 | New | T/W Boring by ODEX-165 Method of drilling at HW FIRST TW site including LDS with new HDPE P/L, Cons. of 250 Cum OHR as per Departmental Design and drawing including soil investigation works, 2nos. pumphouse and boundary wall, providing FHTC and others allied works for BHATPARA TG PWSS under Alipurduar Division PHE DTE | HQ-A.E | RWS Kalchini Block,RWS Kumargram Block | ORD/000452/2022-2023 | 2969/ALD | 31/01/2023 | 14/07/2026 | MAHENDRA CHHETRI | 362.78 | 0 | 0 | 90
9 | ALIPURDUAR | Kalchini | Alipurduar Division | BHATPARA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14212 | New | Continuation order of Supply of fuel for Additional Diesel Vehicle Maxi Cab(At least 7 seater ) for inspection and monitoring of Jal Jeevan Mission (JJM) works under Alipurduar Division, P.H.E. Dte.(from 01.02.2023 to 30.04.2023) | Alipurduar Sadar Sub Division,HQ-A.E | Birpara Sub Division | ORD/000566/2022-2023 | 2952/ALD | 24/01/2023 | 24/04/2023 | NIRANJAN KIRTANIA | 0.7 | 0 | 0 | 0
10 | ALIPURDUAR | Kalchini | Alipurduar Division | BHATPARA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14212 | New | Laying of HDPE Pipeline for left out household connection, boundary wall, pump house, OHR, Land Development, Pathway Platform for FHTC and allied works at Bhatpara PWSS under Alipurduar Division, P.H.E. Dte. (SM/14212) | HQ-A.E | RWS Kalchini Block,RWS Kumargram Block | ORD/000510/2023-2024 | 828/ALD | 14/03/2024 | 12/02/2026 | MAHENDRA CHHETRI | 47.4 | 0 | 0 | 28
11 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | BHATPARA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14212 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division,,Junior Engineer 1, Northern Mechanical Division-II,PHE ,Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000062/2025-2026 | 1155/NMD-II | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
12 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | BHATPARA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14212 | New | Solarization of grid connected pumping installation at Different PWSS at Kalchini Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000130/2025-2026 | 1331/NMD-II | 18/06/2025 | 16/09/2025 | M R S ELECTRICAL | 27.3 | 0 | 0 | 0
13 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | BHATPARA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14212 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Bhatpara TG water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte. APD | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000833/2023-2024 | 2414/NMD-II | 10/08/2023 | 02/03/2025 | SARKAR ELECTRIC | 21.92 | 0 | 0 | 90
Total | [13 empty] | 1280.74 | 0 | 0