## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Kalchini | Alipurduar Division | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14213 | New | Providing FHTC from existing distribution system as per specification for Rangamati TG PWSS under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000262/2023-2024 | 1880/ALD | 07/09/2023 | 07/10/2023 | ASHOK PRADHAN | 9.49 | 0 | 0 | 0
2 | ALIPURDUAR | Kalchini | Alipurduar Division | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14213 | New | Material Requisition To Resource Division |  |  | RTOR000080/2023-2024 | 104/ALD | 10/01/2024 |  | Resource Division | 9.73 | 0 | 0 | 0
3 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14213 | New | New Service connection for Rangamati TG PWSS, Zone-I, P/H-I |  |  | BILL/02404/2023-2024 | BP-2023-24-526 | 11/01/2024 |  | WBSEDCL | 6.39 | 0 | 0 | 0
4 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14213 | New | New Service Connection for Rangamati TG PWSS, Zone-I, P/H-II |  |  | BILL/02405/2023-2024 | BP-2023-24-525 | 11/01/2024 |  | WBSEDCL | 5.22 | 0 | 0 | 0
5 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14213 | New | New Service Connection for Rangamati PWSS, Zone-II, P/H no.-I |  |  | BILL/02406/2023-2024 | BP-2023-24-524 | 11/01/2024 |  | WBSEDCL | 5.58 | 0 | 0 | 0
6 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14213 | New | New Service Connection for Rangamati TG PWSS, Zone-II, P/H no.-II |  |  | BILL/02407/2023-2024 | BP-2023-24-527 | 11/01/2024 |  | WBSEDCL | 6.97 | 0 | 0 | 0
7 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14213 | New | New Service Connection for Rangamati TG PWSS, Zone-II, P/H no.-II |  |  | BILL/02407/2023-2024 | BP-2023-24-527 | 11/01/2024 |  | WBSEDCL | 6.97 | 0 | 0 | 0
8 | ALIPURDUAR | Kalchini | Alipurduar Division | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14213 | New | Hydro-Geologica! investigation aboutWater evaluation, availability and quality parameterfor both ground and surface sources at Lankapara and Gentral Dooars Tea Estate within Alipuduar district. |  |  | BILL/00683/2023-2024 | 429/23-24/PFMS | 28/03/2024 |  | IIT CONSULTATIVE PRACTICE | 2.36 | 0 | 0 | 0
9 | ALIPURDUAR | Kalchini | Alipurduar Division | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14213 | New | Supply of DIDF pipes and specials and Sluice Valve for Rangamati TG Water Supply Scheme (SM/14213) of Kalchini Block under Alipurduar Division P.H.E. Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000520/2023-2024 | 839/ALD | 14/03/2024 | 12/06/2024 | SSPR VALVE MANUFACTURING PVT LTD | 16.24 | 3.69 | 22.73 | 15
10 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14213 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Rangamati TG water supply scheme, TW no I and II of Zone-I and TW no I and II of Zone-II under Jal Jeevan Mission under NMD-II, PHE Dte.APD | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/001137/2023-2024 | 2933/NMD-II | 07/11/2023 | 07/12/2023 | S.P ENTERPRISE (SLG) | 44.02 | 15.32 | 34.8 | 40
11 | ALIPURDUAR | Kalchini | Alipurduar Division | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14213 | New | Constructions of 2(TWO) NOS 150 Cum OHR as per Departmental Design & drawing including laying distribution system with new HDPE pipeline, RISING MAIN, Construction of BOUNDARY WALL, 4(FOUR) NOS ODEX-165 TUBE WELL, 4(FOUR) NOS PUMP HOUSE, Soil Investigation work, providing FHTC and others allied works for RANGAMATI TEA GAEDEN PWSS(ZONE-I+ZONE-II), Alipurduar Division, PHE DTE. | HQ-A.E | RWS Kalchini Block | ORD/000182/2023-2024 | 1171/ALD | 03/08/2023 | 30/01/2024 | M/S RADHASWAMI ENTERPRISE | 440.2 | 0 | 0 | 35
Total | [13 empty] | 553.16 | 19.01 | 3.44