## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Kalchini | Alipurduar Division | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14213 | New | Providing FHTC from existing distribution system as per specification for Rangamati TG PWSS under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000262/2023-2024 | 1880/ALD | 07/09/2023 | 07/10/2023 | ASHOK PRADHAN | 9.49 | 0 | 0 | 0
2 | ALIPURDUAR | Kalchini | Alipurduar Division | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14213 | New | Material Requisition To Resource Division |  |  | RTOR000080/2023-2024 | 104/ALD | 10/01/2024 | 10/01/2024 | Resource Division | 9.73 | 0 | 0 | 0
3 | ALIPURDUAR | Kalchini | Alipurduar Division | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14213 | New | Material Requisition To Resource Division |  |  | RTOR000019/2024-2025 | 3953/ALD | 26/11/2024 | 26/11/2024 | Resource Division | 13.97 | 0 | 0 | 0
4 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14213 | New | New Service Connection for Rangamati PWSS, Zone-II, P/H no.-I |  |  | BILL/02406/2023-2024 | BP-2023-24-524 | 11/01/2024 | 11/01/2024 | WBSEDCL | 5.58 | 0 | 0 | 0
5 | ALIPURDUAR | Kalchini | Alipurduar Division | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14213 | New | Hydro-Geologica! investigation aboutWater evaluation, availability and quality parameterfor both ground and surface sources at Lankapara and Gentral Dooars Tea Estate within Alipuduar district. |  |  | BILL/00683/2023-2024 | 429/23-24/PFMS | 28/03/2024 | 28/03/2024 | IIT CONSULTATIVE PRACTICE | 2.36 | 0 | 0 | 0
6 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14213 | New | New Service connection for Rangamati TG PWSS, Zone-I, P/H-I |  |  | BILL/02404/2023-2024 | BP-2023-24-526 | 11/01/2024 | 11/01/2024 | WBSEDCL | 6.39 | 0 | 0 | 0
7 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14213 | New | New Service Connection for Rangamati TG PWSS, Zone-II, P/H no.-II |  |  | BILL/02407/2023-2024 | BP-2023-24-527 | 11/01/2024 | 11/01/2024 | WBSEDCL | 6.97 | 0 | 0 | 0
8 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14213 | New | New Service Connection for Rangamati TG PWSS, Zone-I, P/H-II |  |  | BILL/02405/2023-2024 | BP-2023-24-525 | 11/01/2024 | 11/01/2024 | WBSEDCL | 5.22 | 0 | 0 | 0
9 | ALIPURDUAR | Kalchini | Alipurduar Division | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14213 | New | Constructions of 2(TWO) NOS 150 Cum OHR as per Departmental Design & drawing including laying distribution system with new HDPE pipeline, RISING MAIN, Construction of BOUNDARY WALL, 4(FOUR) NOS ODEX-165 TUBE WELL, 4(FOUR) NOS PUMP HOUSE, Soil Investigation work, providing FHTC and others allied works for RANGAMATI TEA GAEDEN PWSS(ZONE-I+ZONE-II), Alipurduar Division, PHE DTE. | HQ-A.E | RWS Kalchini Block | ORD/000182/2023-2024 | 1171/ALD | 03/08/2023 | 23/07/2025 | M/S RADHASWAMI ENTERPRISE | 440.2 | 89.83 | 20.41 | 40
10 | ALIPURDUAR | Kalchini | Alipurduar Division | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14213 | New | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Birpara A.E,HQ-A.E | RWS Falakata Block,RWS Kumargram Block | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 02/11/2025 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
11 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14213 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division,,Junior Engineer 1, Northern Mechanical Division-II,PHE ,Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000062/2025-2026 | 1155/NMD-II | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
12 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14213 | New | Solarization of grid connected pumping installation at Different PWSS at Kalchini Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000130/2025-2026 | 1331/NMD-II | 18/06/2025 | 16/09/2025 | M R S ELECTRICAL | 27.3 | 0 | 0 | 0
13 | ALIPURDUAR | Kalchini | Alipurduar Division | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14213 | New | Supply of DIDF pipes and specials and Sluice Valve for Rangamati TG Water Supply Scheme (SM/14213) of Kalchini Block under Alipurduar Division P.H.E. Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000520/2023-2024 | 839/ALD | 14/03/2024 | 09/03/2025 | SSPR VALVE MANUFACTURING PVT LTD | 16.24 | 7.38 | 45.45 | 15
14 | ALIPURDUAR | Kalchini | Alipurduar Division | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14213 | New | Sinking of 1nos Big dia Tubewell (250 x 200 x 150 mm dia) by modified DTH-ODEX of drilling for Rangamati Zone-II PWSS site within Kalchini Block under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000414/2024-2025 | 4592/ALD | 03/01/2025 | 01/04/2025 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT LTD | 24.05 | 0 | 0 | 100
15 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14213 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Rangamati TG water supply scheme, TW no I and II of Zone-I and TW no I and II of Zone-II under Jal Jeevan Mission under NMD-II, PHE Dte.APD | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/001137/2023-2024 | 2933/NMD-II | 07/11/2023 | 07/12/2023 | S.P ENTERPRISE (SLG) | 44.02 | 30.63 | 69.59 | 60
Total | [13 empty] | 1412.02 | 127.85 | 9.05