## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Kalchini | Alipurduar Division | BEECH TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14214 | New | Material Requisition To Resource Division |  |  | RTOR000014/2023-2024 | 220/ALD | 03/05/2023 |  | Resource Division | 36.92 | 0 | 0 | 0
2 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | BEECH TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14214 | New | NEW SERVICE CONNECTION FOR BEECH TG PWSS P/H NO II,HASIMARA APPLICATION NO 4003208193 |  |  | BILL/01823/2023-2024 | BP-2023-24-324 | 27/09/2023 |  | WBSEDCL | 5.67 | 0 | 0 | 0
3 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | BEECH TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14214 | New | NEW SERVICE CONNECTION FOR BEECH TG PWSS P/H NO I,HASIMARA APPLICATION NO 4003208190 |  |  | BILL/01814/2023-2024 | BP-2023-24-323 | 27/09/2023 |  | WBSEDCL | 5.4 | 0 | 0 | 0
4 | ALIPURDUAR | Kalchini | Alipurduar Division | BEECH TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14214 | New | Material Requisition To Resource Division |  |  | RTOR000076/2023-2024 | 100/ALD | 10/01/2024 |  | Resource Division | 9.73 | 0 | 0 | 0
5 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | BEECH TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14214 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Beech TG water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte.APD | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000754/2023-2024 | 2336/NMD-II | 01/08/2023 | 31/08/2023 | KARMAKAR CONSTRUCTION | 21.39 | 10.05 | 46.98 | 85
6 | ALIPURDUAR | Kalchini | Alipurduar Division | BEECH TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14214 | New | Providing balance FHTC from existing distribution system as per specification for BEECH TG PWSS under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000316/2023-2024 | 2184/ALD | 06/10/2023 | 01/08/2024 | D. K. & SONS | 16.37 | 0 | 0 | 0
7 | ALIPURDUAR | Kalchini | Alipurduar Division | BEECH TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14214 | New | Supply of DIDF pipes and specials and Sluice Valve for Beech TG Water Supply Scheme (SM/14214) under Alipurduar Division P.H.E. Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000204/2024-2025 | 1953/ALD | 02/07/2024 | 01/08/2024 | KAMALA VALVES AND ENGINEERING PRIVATE LIMITED | 15.43 | 0 | 0 | 0
8 | ALIPURDUAR | Kalchini | Alipurduar Division | BEECH TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14214 | New | Tube well Boring by ODEX-165 Method of drilling at HW, FIRST TUBE WELL site including laying distribution system with new HDPE pipeline , Constructions of 150 Cum OHR as per Departmental Design & drawing , TWO nos. pump house & boundary wall, providing FHTC, Soil Investigation work and others allied works for BEECH TEA GARDEN AREA PWSS Under Alipurduar Division PHE DTE. (2nd call) | HQ-A.E | RWS Kalchini Block | ORD/000511/2022-2023 | 3398/ALD | 16/03/2023 | 06/09/2024 | MAHENDRA CHHETRI | 309.23 | 202.99 | 65.65 | 91
9 | ALIPURDUAR | Kalchini | Alipurduar Division | BEECH TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14214 | New | Balance portion of boundary wall and pump house and land development of HW site, 1st site and construction of culvert and platform for BEECH TG PWSS under Kalchini Block, Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000491/2023-2024 | 747/ALD | 12/03/2024 | 08/09/2024 | MAHENDRA CHHETRI | 29.65 | 0 | 0 | 90
Total | [13 empty] | 449.79 | 213.04 | 47.36