## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Kalchini | Alipurduar Division | NIMTIJHORA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14215 | New | Material Requisition To Resource Division |  |  | RTOR000071/2023-2024 | 2784/ALD | 18/12/2023 | 18/12/2023 | Resource Division | 6.17 | 0 | 0 | 0
2 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | NIMTIJHORA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14215 | New | New Service connection charge for Nimti Jhora tea garden PWSS P/H No-I. |  |  | BILL/00561/2023-2024 | BP-2023-24-190 | 22/06/2023 | 22/06/2023 | WBSEDCL | 1.36 | 0 | 0 | 0
3 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | NIMTIJHORA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14215 | New | New Service connection charge for Nimti Jhora tea garden PWSS P/H No-II |  |  | BILL/00562/2023-2024 | BP-2023-24-189 | 22/06/2023 | 22/06/2023 | WBSEDCL | 1.36 | 0 | 0 | 0
4 | ALIPURDUAR | Kalchini | Alipurduar Division | NIMTIJHORA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14215 | New | Tube well Boring by ODEX-165 Method of drilling at HW, FIRST TUBE WELL site including laying distribution system with new HDPE pipeline , Constructions of 100 Cum OHR as per Departmental Design & drawing , TWO nos. pump house & boundary wall, providing FHTC, Soil Investigation work and others allied works for NIMTIJHORA TEA GARDEN AREA PWSS Under Alipurduar Division PHE DTE | HQ-A.E | Alipurduar Sub Division | ORD/000578/2022-2023 | 3639/ALD | 31/03/2023 | 20/03/2025 | SAMIRON PODDER | 207.36 | 0 | 0 | 95
5 | ALIPURDUAR | Kalchini | Alipurduar Division | NIMTIJHORA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14215 | New | Material Requisition To Resource Division |  |  | RTOR000036/2024-2025 | 4252/ALD | 13/12/2024 | 13/12/2024 | Resource Division | 1.61 | 0 | 0 | 0
6 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | NIMTIJHORA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14215 | New | Solarization of grid connected pumping installation at Different PWSS at Kalchini Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P |  | ORD/001209/2024-2025 | 823/NMD-II | 06/03/2025 | 05/04/2025 | THE BUSINESS ENGINEERS INDIA | 28.94 | 0 | 0 | 0
7 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | NIMTIJHORA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14215 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division,,Junior Engineer 1, Northern Mechanical Division-II,PHE ,Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000062/2025-2026 | 1155/NMD-II | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
8 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | NIMTIJHORA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14215 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Nimtijhora TG water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte.APD | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000838/2023-2024 | 2413/NMD-II | 10/08/2023 | 02/08/2024 | SUNLIT | 18.75 | 0 | 0 | 100
9 | ALIPURDUAR | Kalchini | Alipurduar Division | NIMTIJHORA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14215 | New | Providing FHTC from existing distribution system as per specification for Nimtijhora TG PWSS under Alipurduar Division, PHE Dte. | HQ-A.E | Alipurduar Sub Division,RWS Kalchini Block | ORD/000264/2023-2024 | 1882/ALD | 07/09/2023 | 25/02/2025 | M/S A. B. ENTERPRISE | 7.09 | 0 | 0 | 100
10 | ALIPURDUAR | Kalchini | Alipurduar Division | NIMTIJHORA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14215 | New | Laying of CIDI pipes & HDPE (PN-10) pipeline and other allied works for Nimtijhora Tea Garden PWSS under Alipurduar Division, PHE Dte. | HQ-A.E | Alipurduar Sub Division,RWS Kalchini Block | ORD/000396/2023-2024 | 207/ALD | 16/01/2024 | 10/04/2025 | SAMIRON PODDER | 44.44 | 0 | 0 | 100
Total | [13 empty] | 1043.24 | 0 | 0