## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Madarihat | Alipurduar Division | GAROCHIRA BANDAPANI PIPED WATER SUPPLY SCHEME | SM/14216 | New | Material Requisition To Resource Division |  |  | RTOR000045/2023-2024 | 1953/ALD | 12/09/2023 | 12/09/2023 | Resource Division | 33.29 | 0 | 0 | 0
2 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | GAROCHIRA BANDAPANI PIPED WATER SUPPLY SCHEME | SM/14216 | New | QUOTATION FOR NEW SERVICE CONNECTION AT GAROCHIRA BANDAPANI TW NO-I |  |  | BILL/00064/2023-2024 | BP-2023-24-58 | 13/05/2023 | 13/05/2023 | WBSEDCL | 1.46 | 0 | 0 | 0
3 | ALIPURDUAR | Madarihat | Alipurduar Division | GAROCHIRA BANDAPANI PIPED WATER SUPPLY SCHEME | SM/14216 | New | Construction of Tubewell by ODEX-165 method of drilling at HW site, construction of pump house and boundary wall at H/W site, laying of distribution line and providing FHTC as per Departmental Design & drawing for Garochera Bandapani PWSS Under Birpara Sub-division, Alipurduar Division PHE DTE. | Birpara A.E | Birpara Sub Division | ORD/000451/2022-2023 | 2922/ALD | 19/01/2023 | 19/05/2023 | RATAN DUTTA | 73.26 | 0 | 0 | 62
4 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | GAROCHIRA BANDAPANI PIPED WATER SUPPLY SCHEME | SM/14216 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Garochira Bandapani Water Supply Scheme TW No.-I under NMD-II,PHE.Dte,Apd. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000400/2023-2024 | 1674/NMD-II | 17/07/2023 | 16/08/2023 | PRAGATI CONSTRUCTION COMPANY | 9.38 | 0 | 0 | 100
5 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | GAROCHIRA BANDAPANI PIPED WATER SUPPLY SCHEME | SM/14216 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division,,Junior Engineer 1, Northern Mechanical Division-II,PHE ,Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000062/2025-2026 | 1155/NMD-II | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
6 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | GAROCHIRA BANDAPANI PIPED WATER SUPPLY SCHEME | SM/14216 | New | Solarization of grid connected pumping installation at Different PWSS at Kalchini, Madarihat -Birpara ,kumargram Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000131/2025-2026 | 1332/NMD-II | 18/06/2025 | 16/09/2025 | M R S ELECTRICAL | 27.3 | 0 | 0 | 0
Total | [13 empty] | 870.85 | 0 | 0