## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Madarihat | Alipurduar Division | DAKSHIN RANGALIBAZNA PIPED WATER SUPPLY SCHEME | SM/14217 | New | Cons. of Rig bored TW(2nos) by ODEX-165 method of drilling at HW and 2nd site, cons of 100 cum OHR at HW including soil testing, cons. of P/H and B/W at HW,2nd site, Laying of rising main, distribution line and providing FHTC as per Departmental Design & drawing for Dakshin Rangalibazna PWSS under Birpara Sub-Division, Alipurduar Division, PHE DTE. | Birpara A.E | Birpara Sub Division | ORD/000509/2022-2023 | 3396/ALD | 16/03/2023 | 12/09/2023 | S.G. CONSTRUCTION | 247.26 | 0 | 0 | 32
2 | ALIPURDUAR | Madarihat | Alipurduar Division | DAKSHIN RANGALIBAZNA PIPED WATER SUPPLY SCHEME | SM/14217 | New | Providing FHTC from existing distribution system as per specification for Dakshin Rangalibazna PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000303/2023-2024 | 2134/ALD | 03/10/2023 | 02/11/2023 | MANI PRADHAN | 3.25 | 0 | 0 | 0
3 | ALIPURDUAR | Madarihat | Alipurduar Division | DAKSHIN RANGALIBAZNA PIPED WATER SUPPLY SCHEME | SM/14217 | New | Material Requisition To Resource Division |  |  | RTOR000045/2022-2023 | 3487ALD | 23/03/2023 | 23/03/2023 | Resource Division | 4.89 | 0 | 0 | 0
4 | ALIPURDUAR | Madarihat | Alipurduar Division | DAKSHIN RANGALIBAZNA PIPED WATER SUPPLY SCHEME | SM/14217 | New | Material Requisition To Resource Division |  |  | RTOR000056/2023-2024 | 2702 | 12/12/2023 | 12/12/2023 | Resource Division | 68.94 | 0 | 0 | 0
5 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | DAKSHIN RANGALIBAZNA PIPED WATER SUPPLY SCHEME | SM/14217 | New | NEW CONNECTION SERVICE FOR DAKSHIN RANGALIBAZNA PWSS P/H NO II APPLICATION NO 4003065179 |  |  | BILL/01802/2023-2024 | BP-2023-24-381 | 27/09/2023 | 27/09/2023 | WBSEDCL | 11.63 | 0 | 0 | 0
6 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | DAKSHIN RANGALIBAZNA PIPED WATER SUPPLY SCHEME | SM/14217 | New | NEW CONNECTION SERVICE FOR DAKSHIN RANGALIBAZNA PWSS P/H NO I APPLICATION NO 4003065178 |  |  | BILL/01798/2023-2024 | BP-2023-24-382 | 27/09/2023 | 27/09/2023 | WBSEDCL | 11.71 | 0 | 0 | 0
7 | ALIPURDUAR | Madarihat | Alipurduar Division | DAKSHIN RANGALIBAZNA PIPED WATER SUPPLY SCHEME | SM/14217 | New | Material Requisition To Resource Division |  |  | RTOR000088/2023-2024 | 112/ALD | 10/01/2024 | 10/01/2024 | Resource Division | 4.89 | 0 | 0 | 0
8 | ALIPURDUAR | Madarihat | Alipurduar Division | DAKSHIN RANGALIBAZNA PIPED WATER SUPPLY SCHEME | SM/14217 | New | Material Requisition To Resource Division |  |  | RTOR000030/2024-2025 | 3988/ALD | 27/11/2024 | 27/11/2024 | Resource Division | 4.89 | 0 | 0 | 0
9 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | DAKSHIN RANGALIBAZNA PIPED WATER SUPPLY SCHEME | SM/14217 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Dakhshin Rangalibazna Water Supply Scheme TW No.-I and II under NMD-II,PHE.Dte,Apd. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000886/2023-2024 | 2464/NMD-II | 11/08/2023 | 07/04/2025 | S.D CONCERN WORKSHOP | 20.48 | 0 | 0 | 49
10 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | DAKSHIN RANGALIBAZNA PIPED WATER SUPPLY SCHEME | SM/14217 | New | Solarization of grid connected pumping installation at Different PWSS at Kalchini Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000133/2025-2026 | 1334/NMD-II | 18/06/2025 | 16/09/2025 | M. M. ENTERPRISE | 16.38 | 0 | 0 | 0
11 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | DAKSHIN RANGALIBAZNA PIPED WATER SUPPLY SCHEME | SM/14217 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division,,Junior Engineer 1, Northern Mechanical Division-II,PHE ,Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000062/2025-2026 | 1155/NMD-II | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
Total | [13 empty] | 1120.47 | 0 | 0