## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Alipurduar - I | Alipurduar Division | TORSHA FOREST PIPED WATER SUPPLY SCHEME | SM/14220 | New | Boring of Tubewell, Construction of pump house, boundary wall, Laying of Rising main, distribution system and providing FHTC for Torsha Forest PWSS under Alipurduar Division PHE Dte. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000448/2022-2023 | 2919/ALD | 19/01/2023 | 10/09/2024 | KAMALESH ROY | 79.66 | 70.41 | 88.39 | 94
2 | ALIPURDUAR | Alipurduar - I | Northern Mechanical Division II | TORSHA FOREST PIPED WATER SUPPLY SCHEME | SM/14220 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Torsha Forest Water Supply Scheme TW No.-I under NMD-II,PHE.Dte,Apd. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000045/2023-2024 | 1060/NMD-II | 26/05/2023 | 25/06/2023 | DIPA CHHETRI | 9.38 | 8.33 | 88.77 | 100
3 | ALIPURDUAR | Alipurduar - I | Alipurduar Division | TORSHA FOREST PIPED WATER SUPPLY SCHEME | SM/14220 | New | Laying of remaining Distribution Line and providing FHTC at different areas under Torsha FOREST PWSS under Alipurduar Division, PHE Dte | Alipurduar RWS | JUNIOR ENGINEER | ORD/000221/2023-2024 | 1581/ALD | 24/08/2023 | 23/10/2023 | KAMALESH ROY | 10.84 | 5.42 | 50 | 100
4 | ALIPURDUAR | Alipurduar - I | Northern Mechanical Division II | TORSHA FOREST PIPED WATER SUPPLY SCHEME | SM/14220 | New | QUOTATION FOR NSC AT TORSHA FOREST PH NO-I |  |  | BILL/01812/2023-2024 | BP-2023-24-375 | 27/09/2023 |  | WBSEDCL | 4.07 | 0 | 0 | 0
Total | [13 empty] | 103.95 | 84.16 | 80.97