## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Madarihat | Alipurduar Division | BALLALGURI PIPED WATER SUPPLY SCHEME | SM/14221 | New | Providing FHTC from existing distribution system as per specification for Ballalguri PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | RWS Madarihat - Birpara Block | ORD/000258/2023-2024 | 1876/ALD | 07/09/2023 | 07/10/2023 | RATAN DUTTA | 4.38 | 0 | 0 | 0
2 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | BALLALGURI PIPED WATER SUPPLY SCHEME | SM/14221 | New | QUOTATION FOR NEW SERVICE CONNECTION AT BALLALGURI TW NO-I |  |  | BILL/00073/2023-2024 | BP-2023-24-68 | 13/05/2023 | 13/05/2023 | WBSEDCL | 1.6 | 0 | 0 | 0
3 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | BALLALGURI PIPED WATER SUPPLY SCHEME | SM/14221 | New | QUOTATION FOR NEW SERVICE CONNECTION AT BALLALGURI TW NO-II |  |  | BILL/00074/2023-2024 | BP-2023-24-67 | 13/05/2023 | 13/05/2023 | WBSEDCL | 1.6 | 0 | 0 | 0
4 | ALIPURDUAR | Madarihat | Alipurduar Division | BALLALGURI PIPED WATER SUPPLY SCHEME | SM/14221 | New | Material Requisition To Resource Division |  |  | RTOR000112/2023-2024 | 136/ALD | 10/01/2024 | 10/01/2024 | Resource Division | 3.5 | 0 | 0 | 0
5 | ALIPURDUAR | Madarihat | Alipurduar Division | BALLALGURI PIPED WATER SUPPLY SCHEME | SM/14221 | New | Boring of Tube Well, Construction of Pump House, Boundary Wall, OHR (100cum) including soil testing, Laying Of Rising Main, Distribution System and providing FHTC for Ballalguri PWSS Under Alipurduar Division, PHE Dte. | Alipurduar RWS | JUNIOR ENGINEER,RWS Falakata Block | ORD/000459/2022-2023 | 2980/ALD | 02/02/2023 | 29/05/2025 | DILIP MAHATO | 255.82 | 120.85 | 47.24 | 70
6 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | BALLALGURI PIPED WATER SUPPLY SCHEME | SM/14221 | New | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for BALLALGURI water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte. Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000081/2023-2024 | 1266/NMD-II | 05/07/2023 | 05/03/2025 | MADHAB SAHA | 18.4 | 0 | 0 | 50
7 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | BALLALGURI PIPED WATER SUPPLY SCHEME | SM/14221 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division,,Junior Engineer 1, Northern Mechanical Division-II,PHE ,Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000062/2025-2026 | 1155/NMD-II | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
8 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | BALLALGURI PIPED WATER SUPPLY SCHEME | SM/14221 | New | Solarization of grid connected pumping installation at Different PWSS at Kalchini, Madarihat -Birpara ,kumargram Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000131/2025-2026 | 1332/NMD-II | 18/06/2025 | 16/09/2025 | M R S ELECTRICAL | 27.3 | 0 | 0 | 0
Total | [13 empty] | 1038.74 | 120.85 | 11.63