## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | Laying of HDPE pipe line for the Birpara Water Supply Scheme under Alipurduar Division,PHE Dte.(Part-2) | Birpara A.E | Birpara Sub Division | ORD/000230/2021-2022 | 1571/ALD | 22/11/2021 | 21/01/2022 | PRAMESH LAMA | 51.34 | 44.47 | 86.62 | 7
2 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | Laying of CI/DI/MS/HDPE pipe and providing FHTC for BIRPARA TEA GARDEN (ZONE-2) AREA PWSS Under Alipurduar Division PHE DTE. PART-A | Birpara A.E | Alipurduar Sub Division | ORD/000440/2022-2023 | 2869/ALD | 17/01/2023 | 18/03/2023 | AMBITIOUS ENTERPRISE | 97.44 | 41.77 | 42.87 | 7
3 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | Laying of CI/DI/MS/HDPE pipe and providing FHTC for BIRPARA TEA GARDEN (ZONE-3) AREA PWSS Under Alipurduar Division PHE DTE. PART-A | Birpara A.E | Alipurduar Sub Division | ORD/000441/2022-2023 | 2870/ALD | 17/01/2023 | 18/03/2023 | ANUP KUNDU CONSTRUCTION CO. | 95.98 | 81.06 | 84.46 | 7
4 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | SHIFTING OF LTOH LINE AT BHANUNAGAR UNDER BIRPARA CCC |  |  | BILL/00234/2023-2024 | BP-2023-24-130 | 23/05/2023 |  | WBSEDCL | 0.47 | 0 | 0 | 0
5 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | Construction of pump house, Boundary Wall, Tube well Boring (by ODEX-165 method of drilling) and Rising main for Zone-III 2nd TW site at Augmentation of Birpara PWSS under Alipurduar Division, PHE Dte. | Birpara A.E |  | ORD/000171/2023-2024 | 962/ALD | 12/07/2023 | 09/11/2023 | SUBIR GHOSH | 32.45 | 0 | 0 | 0
6 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | Laying of DI/MS/HDPE pipe line and providing Functional Household Tap connection (FHTC) in connection with Jaldhara/Jal Sapna for the Birpara Boro Houda WSS under Alipurduar Division, PHE Dte.(Phase-II) | Birpara A.E | Birpara Sub Division | ORD/000320/2020-2021 | 1453/ALD | 25/01/2021 | 11/03/2021 | PRAMESH LAMA | 33.97 | 0 | 0 | 100
7 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna (Schools, AWC and others) for BirparaZone-I (North) PWSS under Alipurduar Division, PHE Dte. Part-1 | Alipurduar RWS,Birpara A.E | Birpara Sub Division | ORD/000444/2022-2023 | 2873/ALD | 17/01/2023 | 03/03/2023 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 24.27 | 0 | 0 | 0
8 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna (Schools, AWC and others) for Birpara (South) PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS |  | ORD/000447/2022-2023 | 2876/ALD | 17/01/2023 | 03/03/2023 | DILIP MAHATO | 34.6 | 0 | 0 | 0
9 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna (Schools, AWC and others) for Birpara Zone-II (Middle) PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS |  | ORD/000446/2022-2023 | 2875/ALD | 17/01/2023 | 03/03/2023 | NARENDRA BHADANI. | 24.11 | 0 | 0 | 0
10 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna (Schools, AWC and others) for Birpara Zone-I (North) PWSS under Alipurduar Division, PHE Dte. Part-2 | Alipurduar RWS |  | ORD/000445/2022-2023 | 2874/ALD | 17/01/2023 | 03/03/2023 | BILTU DAS | 24.22 | 0 | 0 | 0
11 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | Providing FHTC from existing distribution system as per specification for BIRPARA PWSS under Alipurduar Division, PHE Dte. | Birpara A.E |  | ORD/000296/2023-2024 | 2105/ALD | 29/09/2023 | 28/11/2023 | GIRIRAJ ENTERPRISE | 34.39 | 0 | 0 | 0
12 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | QUOTATION FOR BURNT METER AT BIRPARA |  |  | BILL/01825/2023-2024 | BP-2023-24-329 | 27/09/2023 |  | WBSEDCL | 0.09 | 0 | 0 | 0
13 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | Construction of pump house, Boundary Wall, Tube well Boring (by ODEX-165 method of drilling) and Rising main for Zone-I 1st TW site at Augmentation of Birpara PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000040/2023-2024 | 386/ALD | 19/05/2023 | 16/09/2023 | KAJAL KUMAR DE | 32.74 | 13.42 | 40.98 | 30
14 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000060/2023-2024 | 2722/ALD | 13/12/2023 |  | Resource Division | 137.01 | 0 | 0 | 0
15 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | NEW CONNECTION FOR BIRPARA(AUG) ZONE- IPHNO-II |  |  | BILL/02001/2023-2024 | BP-2023-24-460 | 07/12/2023 |  | WBSEDCL | 4.26 | 0 | 0 | 0
16 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | NEW CONNECTION FOR BIRPARA (AUG) ZONE-I PHNO-III |  |  | BILL/02002/2023-2024 | BP-2023-24-461 | 07/12/2023 |  | WBSEDCL | 5.5 | 0 | 0 | 0
17 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | NEW CONNECTION FOR BIRPARA (AUG) ZONE-I PHNO-III |  |  | BILL/02002/2023-2024 | BP-2023-24-461 | 07/12/2023 |  | WBSEDCL | 5.5 | 0 | 0 | 0
18 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000114/2023-2024 | 138/ALD | 10/01/2024 |  | Resource Division | 61.13 | 0 | 0 | 0
19 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | Construction of pump house boundary wall Tubewell boring (by ODEX-165 method of drilling) and rising main for Zone-II 3rd TW site at Augmentation of Birpara PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000009/2023-2024 | 93/ALD | 18/04/2023 | 16/08/2023 | SUBHAK CHIK BARAIK | 31.63 | 2.98 | 9.43 | 100
20 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | Construction of Pump House, B/wall, TW boring by ODEX-165 method of drilling and rising main for Zone-I Headwork TW Site at Augmentation od Birpara PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000342/2023-2024 | 2543/ALD | 28/11/2023 | 27/03/2024 | KAMALESH ROY | 44.55 | 2.84 | 6.38 | 5
21 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | NEW SERVICE CONNECTION FOR Augumentation of Birpara PWSS ZONE-IIII P/H NO-III |  |  | BILL/02471/2023-2024 | BP-2023-24-572 | 01/02/2024 |  | WBSEDCL | 12.06 | 0 | 0 | 0
22 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | Construction of Pump House, B/wall, TW boring by ODEX-165 method of drilling and rising main for Zone-I 3rd TW Site at Augmentation of Birpara PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000350/2023-2024 | 2602/ALD | 04/12/2023 | 02/04/2024 | FAUDA SINGH CHHETRI | 31.46 | 2.89 | 9.18 | 5
23 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | New Service Connection for Birpara Thana PWSS, Zone-II, P/H No-II |  |  | BILL/02301/2023-2024 | BP-2023-24-618 | 16/02/2024 |  | WBSEDCL | 3.74 | 0 | 0 | 0
24 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | New Service Connection for Birpara Thana PWSS, Zone-II, P/H No-II |  |  | BILL/02301/2023-2024 | BP-2023-24-618 | 16/02/2024 |  | WBSEDCL | 3.74 | 0 | 0 | 0
25 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | NEW SERVICE CONNECTION CHARGES FOR KFC GROUND AUGUMENTATION OF BIRPARA PWSS ZONE-III P/H NO-II |  |  | BILL/02804/2023-2024 | BP-2023-24-644 | 29/02/2024 |  | WBSEDCL | 7.01 | 0 | 0 | null
26 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | Cons. of pump house, boundary wall and Rising Main for Zone-II 4thTube well site at Aug. of Birpara PWSS of Birpara Sub-Division under Alipurduar Division, PHE Dte. (SM/14233) | Birpara A.E | Birpara Sub Division | ORD/000531/2023-2024 | 850/ALD | 14/03/2024 | 12/07/2024 | RATAN DUTTA | 18.26 | 0 | 0 | 0
27 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | "Hiring of Motor Cab (Non-air conditioned) for site visit of JJM Works under the Office of the EE/NMD-II P.H.E. Dte." | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/001249/2023-2024 | 419/AMSD | 16/10/2023 | 15/12/2023 | MUSTAFI CONCERN | 0.69 | 0 | 0 | 100
28 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | Hiring of Additional Diesel Vehicle Maxi Cab(At least 7 seater ) for Assistant Engineer ,Birpara Sub- Division ,P.H.E. Dte..(from 01.04.2024 to 01.03.2025) | Birpara A.E | Birpara Sub Division | ORD/000538/2023-2024 | 893/ALD | 15/03/2024 | 15/03/2025 | PARITOSH SUTRADHAR | 4.8 | 0 | 0 | 0
29 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | Supply of drinking water through tanker by hired vehicle to mitigate drinking water crisis at Huntapara TG, Dhumchipara TG and Gargenda TG and lankapara TG under Madarihat-Birpara Block under Alipurduar Division, PHE Dte. | Birpara A.E |  | ORD/000309/2023-2024 | 2174/ALD | 06/10/2023 | 20/11/2023 | BHAGWATI BHUJEL | 9.82 | 4.91 | 50 | 100
30 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | Tube well Boring by ODEX-165 Method of drilling at TUBE WELL site including laying distribution system with new HDPE pipeline ,One nos pump house & boundary wall, providing FHTC and others allied works for Bhutri Forest PWSS Under Alipurduar Division PHE DTE. | HQ-A.E | RWS Kalchini Block | ORD/000010/2023-2024 | 94/ALD | 18/04/2023 | 16/08/2023 | FAUDA SINGH CHHETRI | 34.7 | 29.27 | 84.36 | 100
31 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | NEW SERVICE CONNECTION CHARGE FOR BIRPARA CIRCUS GROUND ZONE-III, P/H NO-I |  |  | BILL/03018/2023-2024 | BP-2023-24-695 | 14/03/2024 |  | WBSEDCL | 9.12 | 0 | 0 | null
32 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | NEW SERVICE CONNECTION CHARGE FOR BIRPARA CIRCUS GROUND ZONE-III, P/H NO-I |  |  | BILL/03018/2023-2024 | BP-2023-24-695 | 14/03/2024 |  | WBSEDCL | 9.12 | 0 | 0 | null
33 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | NEW SERVICE CONNECTION CHARGE FOR AUGUMENTATION OF BIRPARA ZONE-I P/HNO-I |  |  | BILL/03019/2023-2024 | BP-2023-24-696 | 14/03/2024 |  | WBSEDCL | 7.9 | 0 | 0 | null
34 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | Construction of 550cum. OHR for Birpara TG (Middle) Water Supply Scheme under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000438/2022-2023 | 2867/ALD | 17/01/2023 | 16/07/2023 | DILIP MAHATO | 98.12 | 23.46 | 23.9 | 24
35 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | Construction of Pump House, B/wall, TW boring by ODEX-165 method of drilling and rising main for Zone-III Headwork TW Site at Augmentation of Birpara PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000343/2023-2024 | 2544/ALD | 28/11/2023 | 27/03/2024 | RATAN DUTTA | 46.23 | 3.19 | 6.89 | 5
36 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | Protective and Decorative Acrylic exterior paint on existing 350 cum OHR at Birpara of Birpara Sub-Division under Alipurduar Division, P.H.E.Dte. (SM/14233) | Birpara A.E | RWS Falakata Block | ORD/000506/2023-2024 | 824/ALD | 14/03/2024 | 13/05/2024 | BHAGWATI BHUJEL | 1.96 | 0.97 | 49.69 | 10
37 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | Construction of pump house, Boundary Wall, Tube well Boring (by ODEX-165 method of drilling) and Rising main for Zone-II 1st TW site at Augmentation of Birpara PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000158/2023-2024 | 663/ALD | 07/06/2023 | 29/09/2024 | BRAJA GOPAL SAHA | 31.58 | 8.66 | 27.4 | 20
38 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | SOIL INVESTIGATION AT OHR AND CONS. OF 450 CUM OHR AT ZONE-3 FOR AUGMENTATIN OF BIRPARA PWSS UNDER ALIPURDUAR DIVISION OF NORTH BENGAL CIRCLE-I, PHE DTE. | Birpara A.E | Birpara Sub Division,RWS Falakata Block | ORD/000433/2023-2024 | 234/ALD | 17/01/2024 | 12/11/2024 | AMBITIOUS ENTERPRISE | 239.31 | 0 | 0 | 5
39 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | Laying of CI/DI/MS/HDPE pipe and providing FHTC for BIRPARA TEA GARDEN (ZONE-3) AREA PWSS Under Alipurduar Division PHE DTE. PART-C | Birpara A.E | Birpara Sub Division | ORD/000443/2022-2023 | 2872/ALD | 17/01/2023 | 18/03/2023 | DILIP MAHATO | 96.76 | 68.66 | 70.95 | 65
40 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | Construction of pump house boundary wall Tubewell boring (by ODEX-165 method of drilling) and rising main for Zone-III 3rd TW site at Augmentation of Birpara PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000014/2023-2024 | 166/ALD | 26/04/2023 | 18/08/2024 | RATAN DUTTA | 31.78 | 2.88 | 9.08 | 65
41 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | Sinking of Big dia. Tubewell (200 x 150 mm dia.)by modified DTH -ODEX method of drilling at Paschim Khairbari PWSS(SM/10672) and Birpara PWSS Zone-II, 4th TW site(SM/14233)of Birpara Sub-Division under Alipurduar Division, PHE Dte. | Birpara A.E | JUNIOR ENGINEER | ORD/000493/2023-2024 | 749/ALD | 12/03/2024 | 25/07/2024 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT LTD | 33.26 | 9.2 | 27.66 | 50
42 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | Supply, delivery, installation, commissioning and trial run of electro mechanical component along with Cu. wound line voltage corrector for Augmentation of Birpara water supply scheme TW No.- I,II and III of Zone-I and TW No.- I,II,III and IV of Zone-II and TW No.- I,II and III of Zone-III under Northern Mechanical Division-II, PHE Dte, Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/001136/2023-2024 | 2873/NMD-II | 17/10/2023 | 15/01/2024 | EASTERN INDIA SALES & SERVICE | 176.42 | 42.74 | 24.23 | 55
43 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | NEW SERVICE CONNECTION CHARGES FOR AUGUMENTATION OF BIRPARA Z-II P/HNO-IV |  |  | BILL/03011/2023-2024 | BP-2023-24-688 | 14/03/2024 |  | WBSEDCL | 6.55 | 0 | 0 | null
44 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | NEW SERVICE CONNECTION CHARGES FOR AUGUMENTATION OF BIRPARA Z-II P/HNO-IV |  |  | BILL/03011/2023-2024 | BP-2023-24-688 | 14/03/2024 |  | WBSEDCL | 6.55 | 0 | 0 | null
45 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA WATER SUPPLY SCHEME | SM/14233 | Augmentation | Soil investigation at OHR site and construction of 450cum OHR at Zone-1 for Augmentation of Birpara PWSS under Alipurduar Divisionof North Bengal Circle-I, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000459/2023-2024 | 495/ALD | 16/02/2024 | 12/12/2024 | KAMALESH ROY | 120.29 | 14.45 | 12.01 | 10
Total | [13 empty] | 1816.9 | 397.81 | 21.9