## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Falakata | Alipurduar Division | MAIRADANGA PIPED WATER SUPPLY SCHEME | SM/15206 | New | Construction of tube wells (2 nos.) by Reverse rotary method of drilling at HW site and 2nd TW site , Soil investigation at OHR site, constructions of 350 Cum OHR at HW , construction of pump house and boundary wall at H/W and 2nd site, laying of rising main, distribution line and providing FHTC as per Departmental Design & drawing for MAIRADANGA PWSS Under Birpara Subdivision, Alipurduar Division PHE DTE. | Birpara A.E | Birpara Sub Division | ORD/000030/2023-2024 | 334/ALD | 16/05/2023 | 12/11/2023 | MESSRS A.B.G CONSTRUCTION | 653.77 | 181.47 | 27.76 | 65
2 | ALIPURDUAR | Falakata | Northern Mechanical Division II | MAIRADANGA PIPED WATER SUPPLY SCHEME | SM/15206 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Mairadanga Water Supply Scheme TW No.-I and II under NMD-II,PHE.Dte,Apd. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Northern Mechanical Division-II,PHE | ORD/000896/2023-2024 | 2475/NMD-II | 11/08/2023 | 10/09/2023 | SUBODH KUMAR BANIK | 21.06 | 0 | 0 | 0
3 | ALIPURDUAR | Falakata | Alipurduar Division | MAIRADANGA PIPED WATER SUPPLY SCHEME | SM/15206 | New | Construction of slab culvert, pathway and other allied works at 3rd TW Site, painting existing boundary wall, pump house, roof treatment, plinth protection at 2nd TW site of Chhoto Salkumar WSS adjacent to Mairadanga PWSS including gap filling in distribution line (90mm dia) under Alipurduar Division, PHE Dte. | Birpara A.E |  | ORD/000354/2023-2024 | 2606/ALD | 04/12/2023 | 02/04/2024 | ASSOCIATE CONSTRUCTION COMPANY | 23.88 | 0 | 0 | 0
4 | ALIPURDUAR | Falakata | Alipurduar Division | MAIRADANGA PIPED WATER SUPPLY SCHEME | SM/15206 | New | Material Requisition To Resource Division |  |  | RTOR000058/2023-2024 | 2720/ALD | 13/12/2023 |  | Resource Division | 68.94 | 0 | 0 | 0
5 | ALIPURDUAR | Falakata | Alipurduar Division | MAIRADANGA PIPED WATER SUPPLY SCHEME | SM/15206 | New | Material Requisition To Resource Division |  |  | RTOR000096/2023-2024 | 120/ALD | 10/01/2024 |  | Resource Division | 15.91 | 0 | 0 | 0
6 | ALIPURDUAR | Falakata | Northern Mechanical Division II | MAIRADANGA PIPED WATER SUPPLY SCHEME | SM/15206 | New | New Servivce Connection for Marindanga PH NO-I PWSS |  |  | BILL/00985/2024-2025 | BP-279/24-25 | 22/08/2024 |  | WBSEDCL | 7.07 | 0 | 0 | null
7 | ALIPURDUAR | Falakata | Northern Mechanical Division II | MAIRADANGA PIPED WATER SUPPLY SCHEME | SM/15206 | New | New Service Connection for Mairadanga PH NO-II PWSS |  |  | BILL/00984/2024-2025 | BP-278/24-25 | 22/08/2024 |  | WBSEDCL | 5.22 | 0 | 0 | null
Total | [13 empty] | 795.84 | 181.47 | 22.8