## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Falakata | Northern Mechanical Division II | DHANIRAMPUR PIPED WATER SUPPLY SCHEME | SM/15208 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Dhanirampur Water Supply Scheme TW No.-I and II under NMD-II,PHE.Dte,Apd. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Northern Mechanical Division-II,PHE | ORD/000899/2023-2024 | 2473/NMD-II | 11/08/2023 | 31/12/2024 | SARKAR ELECTRIC | 21.08 | 2.74 | 13 | 60
2 | ALIPURDUAR | Falakata | Alipurduar Division | DHANIRAMPUR PIPED WATER SUPPLY SCHEME | SM/15208 | New | Laying of rising main, delivery main, bypass arrangement, Laying of HDPE Pipeline for left out household connection and other allied works at Dhanirampur PWSS (both H/W and 2nd site) of Birpara Sub-Division under Alipurduar Division, P.H.E. Dte. (SM/15208) | Birpara A.E | RWS Falakata Block | ORD/000511/2023-2024 | 829/ALD | 14/03/2024 | 28/04/2024 | DILIP MAHATO | 58.7 | 47.31 | 80.6 | 70
3 | ALIPURDUAR | Falakata | Alipurduar Division | DHANIRAMPUR PIPED WATER SUPPLY SCHEME | SM/15208 | New | Supply of DIDF pipes and DI specials and CI Jeffy Coupling for Dhanirampur Water Supply Scheme (SM/15208) of Falakata Block under Alipurduar Division P.H.E. Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000519/2023-2024 | 838/ALD | 14/03/2024 | 13/04/2024 | BARMAN ENTERPRISE | 9.78 | 9.78 | 100 | 90
4 | ALIPURDUAR | Falakata | Alipurduar Division | DHANIRAMPUR PIPED WATER SUPPLY SCHEME | SM/15208 | New | Material Requisition To Resource Division |  |  | RTOR000095/2023-2024 | 119/ALD | 10/01/2024 | 10/01/2024 | Resource Division | 9.56 | 0 | 0 | 0
5 | ALIPURDUAR | Falakata | Northern Mechanical Division II | DHANIRAMPUR PIPED WATER SUPPLY SCHEME | SM/15208 | New | NEW SERVICE CONNECTION CHARGES FOR DHANIRAMPURPH NO-I |  |  | BILL/03014/2023-2024 | BP-2023-24-691 | 14/03/2024 | 14/03/2024 | WBSEDCL | 4.08 | 0 | 0 | 0
6 | ALIPURDUAR | Falakata | Northern Mechanical Division II | DHANIRAMPUR PIPED WATER SUPPLY SCHEME | SM/15208 | New | NEW SERVICE CONNECTION CHARGE DHANIRAMPUR PH NO-II |  |  | BILL/03016/2023-2024 | BP-2023-24-693 | 14/03/2024 | 14/03/2024 | WBSEDCL | 5.85 | 0 | 0 | 0
7 | ALIPURDUAR | Falakata | Alipurduar Division | DHANIRAMPUR PIPED WATER SUPPLY SCHEME | SM/15208 | New | Construction of tubewells (2 nos.) by Reverse rotary method of drilling at HW site and 2nd TW site , Soil investigation at OHR site, constructions of 250 Cum OHR at HW , construction of pump house and boundary wall at H/W and 2nd site, laying of rising main, distribution line and providing FHTC as per Departmental Design & drawing for DHANIRAMPUR PWSS Under Birpara Subdivision, Alipurduar Division PHE DTE. | Birpara A.E | RWS Falakata Block | ORD/000575/2022-2023 | 3636/ALD | 31/03/2023 | 16/09/2025 | DILIP MAHATO | 457.51 | 430.34 | 94.06 | 95
8 | ALIPURDUAR | Falakata | Northern Mechanical Division II | DHANIRAMPUR PIPED WATER SUPPLY SCHEME | SM/15208 | New | Yard lighting arrangement at Head Work Site for Different PWSS (PASCHIM DEOGAON and others) under JJM in the BLOCK: Falakata, DISTRICT: ALIPURDUAR under NMD-II,PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Northern Mechanical Division-II,PHE | ORD/000169/2025-2026 | 1385/NMD-II | 26/06/2025 | 26/07/2025 | M/S SAJAHAN CHOWDHURY | 20.56 | 0 | 0 | 0
9 | ALIPURDUAR | Falakata | Northern Mechanical Division II | DHANIRAMPUR PIPED WATER SUPPLY SCHEME | SM/15208 | New | Solarization of grid connected pumping installation at Different PWSS at Falakata Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Northern Mechanical Division-II,PHE | ORD/000134/2025-2026 | 1344/NMD-II | 19/06/2025 | 17/09/2025 | M/S SAJAHAN CHOWDHURY | 42.58 | 0 | 0 | 0
10 | ALIPURDUAR | Falakata | Northern Mechanical Division II | DHANIRAMPUR PIPED WATER SUPPLY SCHEME | SM/15208 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division,,Junior Engineer 1, Northern Mechanical Division-II,PHE ,Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000062/2025-2026 | 1155/NMD-II | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
11 | ALIPURDUAR | Falakata | Alipurduar Division | DHANIRAMPUR PIPED WATER SUPPLY SCHEME | SM/15208 | New | Laying of HDPE pipeline (left out ) at Dhanirampur PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | RWS Falakata Block | ORD/000133/2025-2026 | 1626/ALD | 04/08/2025 | 03/10/2025 | DILIP MAHATO | 30.28 | 0 | 0 | 0
Total | [13 empty] | 1386.11 | 490.16 | 35.36