## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Kalchini | Alipurduar Division | KALCHINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/15482 | New | Retrofitting and Extension of pipeline for Kalchini area under DIMA PWSS at Kalchini Block under Alipurduar Division. PHE Dte. Part-B | HQ-A.E | Birpara Sub Division | ORD/000373/2020-2021 | 1769/ALD | 19/02/2021 | 20/04/2021 | RAMESH SHARMA | 49.52 | 0 | 0 | 93
2 | ALIPURDUAR | Kalchini | Alipurduar Division | KALCHINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/15482 | New | Retrofitting and Extension of pipeline for Kalchini area under DIMA PWSS at Kalchini Block under Alipurduar Division. PHE Dte. Part-A | HQ-A.E | RWS Kalchini Block | ORD/000372/2020-2021 | 1768/ALD | 19/02/2021 | 20/04/2021 | SUNDAR SING LAMA | 41.98 | 0 | 0 | 86
3 | ALIPURDUAR | Kalchini | Alipurduar Division | KALCHINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/15482 | New | Construction of Pump House, Boundary Wall, Tube well Boring by ODEX-165 Method of drilling at 2nd & 3rd site including laying distribution system , Rising main and providing FHTC for KALCHINI TG ZONE-I PWSS Under Alipurduar Division PHE DTE. | HQ-A.E | RWS Kalchini Block | ORD/000014/2022-2023 | 3229/ALD. | 27/02/2023 | 27/06/2023 | SHREE RANISATI ENTERPRISE | 143.22 | 63.43 | 44.29 | 30
4 | ALIPURDUAR | Kalchini | Alipurduar Division | KALCHINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/15482 | New | Construction of Pump House, Boundary Wall, Tube well Boring by ODEX-165 Method of drilling at H/W site including laying distribution system and providing FHTC for KALCHINI TG ZONE-I PWSS Under Alipurduar Division PHE DTE | HQ-A.E | RWS Kalchini Block | ORD/000009/2022-2023 | 3230/ALD. | 27/02/2023 | 25/10/2023 | SHREE RANISATI ENTERPRISE | 190.87 | 119.33 | 62.52 | 10
5 | ALIPURDUAR | Kalchini | Alipurduar Division | KALCHINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/15482 | New | Construction of Pump House, Boundary Wall, Tube well Boring by ODEX-165 Method of drilling at 3rd & 4th site including laying distribution system , Rising main and providing FHTC for KALCHINI TG ZONE-II PWSS Under Alipurduar Division PHE DTE. | HQ-A.E |  | ORD/000015/2022-2023 | 3227/ALD | 27/02/2023 | 27/06/2023 | SHREE RANISATI ENTERPRISE | 179.1 | 0 | 0 | 0
6 | ALIPURDUAR | Kalchini | Alipurduar Division | KALCHINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/15482 | New | Construction of Pump House, Boundary Wall, Tube well Boring by ODEX-165 Method of drilling at H/W site & 2nd site including laying distribution system and providing FHTC for KALCHINI TG ZONE-II PWSS Under Alipurduar Division PHE DTE | HQ-A.E |  | ORD/000474/2022-2023 | 3228/ALD | 27/02/2023 | 27/06/2023 | SHREE RANISATI ENTERPRISE | 179.69 | 0 | 0 | 0
7 | ALIPURDUAR | Kalchini | Alipurduar Division | KALCHINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/15482 | New | Construction of 350cum OHR for Kalchini TG Water Supply Scheme under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000564/2022-2023 | 3233/ALD | 27/02/2023 | 26/08/2023 | Z STAR COMMOTRADE PVT LTD. | 71.41 | 0 | 0 | 0
8 | ALIPURDUAR | Kalchini | Alipurduar Division | KALCHINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/15482 | New | Construction of 500cum OHR for Kalchini TG Water Supply Scheme under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000565/2022-2023 | 3234ALD | 27/02/2023 | 22/02/2024 | SHREE RANISATI ENTERPRISE | 91.81 | 41.04 | 44.7 | 40
9 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | KALCHINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/15482 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for KALCHINI TG AREA Water Supply Scheme TW No.-I,II,III of Zone-I and TW No.-I,II,III,IV of Zone-II under NMD-II,Apd | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000906/2023-2024 | 2490/NMD-II | 14/08/2023 | 13/09/2023 | M/S P.P ELECTRICALS | 81.19 | 56.97 | 70.17 | 40
10 | ALIPURDUAR | Kalchini | Alipurduar Division | KALCHINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/15482 | New | Material Requisition To Resource Division |  |  | RTOR000042/2022-2023 | 3484/ALD | 23/03/2023 | 23/03/2023 | Resource Division | 36.96 | 0 | 0 | 0
11 | ALIPURDUAR | Kalchini | Alipurduar Division | KALCHINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/15482 | New | Material Requisition To Resource Division |  |  | RTOR000027/2023-2024 | 1272/ALD | 11/08/2023 | 11/08/2023 | Resource Division | 77.78 | 0 | 0 | 0
12 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | KALCHINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/15482 | New | NEW SERVICE CONNECTION FOR KALCHINI TG PWSS P/H NO II,ZONE-II,KALCHINI APPLICATION NO 4003208210 |  |  | BILL/01821/2023-2024 | BP-2023-24-322 | 27/09/2023 | 27/09/2023 | WBSEDCL | 9.42 | 0 | 0 | 0
13 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | KALCHINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/15482 | New | NEW SERVIVCE CONNECTION FOR KALCHINI TG PWSS P/H NO II,ZONE-I,KALCHINI APPLICATION NO 4003208205 |  |  | BILL/01817/2023-2024 | BP-2023-24-321 | 27/09/2023 | 27/09/2023 | WBSEDCL | 5.56 | 0 | 0 | 0
14 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | KALCHINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/15482 | New | NEW CONNECTION SETRVICE FOR KALCHINI T.G.,PWSS P/H NO I,ZONE II, KALCHINI APPLICATION NO 4003208203 |  |  | BILL/01806/2023-2024 | BP-2023-24-380 | 27/09/2023 | 27/09/2023 | WBSEDCL | 5.6 | 0 | 0 | 0
15 | ALIPURDUAR | Kalchini | Alipurduar Division | KALCHINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/15482 | New | Supply of CIDF/CIPE pipes and specials & CI Jeffy Coupling for Kalchini TG Water Supply Scheme under Alipurduar Division P.H.E. Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000483/2023-2024 | 739/ALD | 12/03/2024 | 11/04/2024 | MADHAB SAHA | 13.81 | 0 | 0 | 0
16 | ALIPURDUAR | Kalchini | Alipurduar Division | KALCHINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/15482 | New | Conceptualization, design and implementing mass awareness generation through Wall writing at 22 nos. villages (Block - Madarihat) by dissemination of awareness generation IEC messages FHTC, Provision on legal provision damage or illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation and WASH related issues as per guideline of JJM at Alipurduar district under Alipurduar Division, PHE Dte, Govt. of West Bengal.( SM/15482) | Birpara A.E | JUNIOR ENGINEER | ORD/000497/2023-2024 | 753/ALD | 12/03/2024 | 11/04/2024 | BARMAN ENTERPRISE | 5.27 | 5.27 | 99.96 | 100
17 | ALIPURDUAR | Kalchini | Alipurduar Division | KALCHINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/15482 | New | Road Restoration at kalchini Old Scheme area within Kalchini block under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000407/2024-2025 | 4536/ALD | 26/12/2024 | 24/02/2025 | RK DISTRIBUTORS | 2.08 | 2.08 | 99.69 | 100
18 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | KALCHINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/15482 | New | New Service Connection for Kalchini TG PWSS, Zone-II, P/H-II |  |  | BILL/02402/2023-2024 | BP-2023-24-530 | 11/01/2024 | 11/01/2024 | WBSEDCL | 7.15 | 0 | 0 | 0
19 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | KALCHINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/15482 | New | New Service connection for Kalchini TG PWSS, Zone-II, P/H-IV |  |  | BILL/02403/2023-2024 | BP-2023-24-529 | 11/01/2024 | 11/01/2024 | WBSEDCL | 5.43 | 0 | 0 | 0
20 | ALIPURDUAR | Kalchini | Alipurduar Division | KALCHINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/15482 | New | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA |  |  | BILL/00501/2024-2025 | 321/24-25/PFMS | 14/11/2024 | 14/11/2024 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0 | 0
21 | ALIPURDUAR | Kalchini | Alipurduar Division | KALCHINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/15482 | New | Reparing of Pump House at Headwork site of Kalchini PWSS Under Alipurduar Division PHE DTE. |  |  | ORD/000592/2024-2025 | 5421/ALD | 19/03/2025 | 18/05/2025 | DOOARS SOCIAL WELFARE ORGANISATION | 0.98 | 0 | 0 | 0
22 | ALIPURDUAR | Kalchini | Alipurduar Division | KALCHINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/15482 | New | Reparing of Pump House at 3nd site of Kalchini PWSS Under Alipurduar Division PHE DTE. |  |  | ORD/000594/2024-2025 | 5423/ALD | 19/03/2025 | 18/05/2025 | DOOARS SOCIAL WELFARE ORGANISATION | 0.98 | 0 | 0 | 0
23 | ALIPURDUAR | Kalchini | Alipurduar Division | KALCHINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/15482 | New | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Birpara A.E,HQ-A.E | RWS Falakata Block,RWS Kumargram Block | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 02/11/2025 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
24 | ALIPURDUAR | Kalchini | Alipurduar Division | KALCHINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/15482 | New | Reparing of Pump House at 2nd site of Kalchini PWSS Under Alipurduar Division PHE DTE. |  |  | ORD/000601/2024-2025 | 5422/ALD | 19/03/2025 | 18/05/2025 | DOOARS SOCIAL WELFARE ORGANISATION | 0.93 | 0 | 0 | 0
25 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | KALCHINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/15482 | New | New service connection charges for Aug Kalchini TG zone-I ,PH-III under NMD-II |  |  | BILL/03117/2024-2025 |  | 19/03/2025 | 19/03/2025 | WBSEDCL | 11.75 | 0 | 0 | 0
26 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | KALCHINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/15482 | New | New service connection charges for Kalchini TG zone-I,PH- IV under NMD-II |  |  | BILL/03116/2024-2025 |  | 19/03/2025 | 19/03/2025 | WBSEDCL | 16.7 | 0 | 0 | 0
Total | [13 empty] | 1367.56 | 288.11 | 21.07