## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Kumargram | Alipurduar Division | MADHYA KAMAKHYAGURI PIPED WATER SUPPLY SCHEME | SM/15517 | New | Cons. of pump house and Sinking of 250 mm x 200 mm X 150 mtr. big dia. TW at HW site and 2nd site, LDS with UPVC pipeline, Cons. of 350 cum OHR as per Departmental Design & drawing , providing FHTC and others allied works for MADHYA KAMAKHYAGURI PWSS Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000466/2022-2023 | 3155/ALD | 22/02/2023 | 21/08/2023 | GHOSH & SAHA CONSTRUCTION | 478.58 | 453.17 | 94.69 | 85
2 | ALIPURDUAR | Kumargram | Alipurduar Division | MADHYA KAMAKHYAGURI PIPED WATER SUPPLY SCHEME | SM/15517 | New | Supply of DI pipe & CI special for Madhya Kamakhyaguri PWSS under Alipurduar Division PHE Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000044/2023-2024 | 390/ALD | 19/05/2023 | 18/06/2023 | DILIP MAHATO | 71.61 | 68.44 | 95.57 | 75
3 | ALIPURDUAR | Kumargram | Alipurduar Division | MADHYA KAMAKHYAGURI PIPED WATER SUPPLY SCHEME | SM/15517 | New | Providing balance FHTC for MADHYA KAMAKHYAGURI PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000249/2023-2024 | 1850/ALD | 04/09/2023 | 19/10/2023 | MONORAMA ENTERPRISE | 5.85 | 0 | 0 | 0
4 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | MADHYA KAMAKHYAGURI PIPED WATER SUPPLY SCHEME | SM/15517 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Madhya Kamakhyaguri Water Supply Scheme TW No.-I and II under NMD-II,PHE.Dte,Apd. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000888/2023-2024 | 2466/NMD-II | 11/08/2023 | 10/09/2023 | M/S PARITOSH BHOWMICK & CO. | 21.92 | 10.3 | 46.98 | 100
5 | ALIPURDUAR | Kumargram | Alipurduar Division | MADHYA KAMAKHYAGURI PIPED WATER SUPPLY SCHEME | SM/15517 | New | Material Requisition To Resource Division |  |  | RTOR000032/2023-2024 | 1277/ALD | 11/08/2023 | 11/08/2023 | Resource Division | 49.36 | 0 | 0 | 0
6 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | MADHYA KAMAKHYAGURI PIPED WATER SUPPLY SCHEME | SM/15517 | New | QUOTATION FOR NEW SERVICE CONNECTION AT MADHYA KAMAKHYAGURI PWSS PH NO-I |  |  | BILL/00046/2023-2024 | BP-2023-24-41 | 12/05/2023 | 12/05/2023 | WBSEDCL | 1.21 | 0 | 0 | 0
7 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | MADHYA KAMAKHYAGURI PIPED WATER SUPPLY SCHEME | SM/15517 | New | QUOTATION FOR NEW SERVICE CONNECTION AT MADHYA KAMAKHYAGURI PWSS PH NO-II |  |  | BILL/00045/2023-2024 | BP-2023-24-42 | 12/05/2023 | 12/05/2023 | WBSEDCL | 1.21 | 0 | 0 | 0
8 | ALIPURDUAR | Kumargram | Alipurduar Division | MADHYA KAMAKHYAGURI PIPED WATER SUPPLY SCHEME | SM/15517 | New | Supply of DI/DIDF Specials for Madhya Kamakhyaguri (SM/15517)WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000396/2024-2025 | 4235/ALD | 12/12/2024 | 11/01/2025 | MADHAB SAHA | 16.91 | 0 | 0 | 0
9 | ALIPURDUAR | Kumargram | Alipurduar Division | MADHYA KAMAKHYAGURI PIPED WATER SUPPLY SCHEME | SM/15517 | New | Laying of new UPVC/DI pipeline for interconnection in the distribution system and bridge/culvert crossing, Construction of surface drain, pathway other allied works in connection with the Madhya Kamakhyaguri PWSS Alipurduar Sadar Sub-Division, under Alipurduar Division PHE DTE. .(SM/15517) | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000226/2024-2025 | 2279/ALD | 05/08/2024 | 01/02/2025 | GHOSH & SAHA CONSTRUCTION | 61.08 | 0 | 0 | 70
10 | ALIPURDUAR | Kumargram | Alipurduar Division | MADHYA KAMAKHYAGURI PIPED WATER SUPPLY SCHEME | SM/15517 | New | Material Requisition To Resource Division |  |  | RTOR000104/2023-2024 | 128/ALD | 10/01/2024 | 10/01/2024 | Resource Division | 10.13 | 0 | 0 | 0
11 | ALIPURDUAR | Kumargram | Alipurduar Division | MADHYA KAMAKHYAGURI PIPED WATER SUPPLY SCHEME | SM/15517 | New | Material Requisition To Resource Division |  |  | RTOR000045/2024-2025 | 4261/ALD | 13/12/2024 | 13/12/2024 | Resource Division | 13.19 | 0 | 0 | 0
12 | ALIPURDUAR | Kumargram | Alipurduar Division | MADHYA KAMAKHYAGURI PIPED WATER SUPPLY SCHEME | SM/15517 | New | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA |  |  | BILL/00501/2024-2025 | 321/24-25/PFMS | 14/11/2024 | 14/11/2024 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0 | 0
13 | ALIPURDUAR | Kumargram | Alipurduar Division | MADHYA KAMAKHYAGURI PIPED WATER SUPPLY SCHEME | SM/15517 | New | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Birpara A.E,HQ-A.E | RWS Falakata Block,RWS Kumargram Block | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 02/11/2025 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
14 | ALIPURDUAR | Kumargram | Alipurduar Division | MADHYA KAMAKHYAGURI PIPED WATER SUPPLY SCHEME | SM/15517 | New | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna for Kumargram Block under Alipurduar Division, PHE Dte. (Pin point site of the FHTC will be given at the time of issue of work order) | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000081/2025-2026 | 1049/ALD | 17/06/2025 | 13/04/2026 | MOTI INDUSTRIES | 18.14 | 0 | 0 | 15
15 | ALIPURDUAR | Kumargram | Alipurduar Division | MADHYA KAMAKHYAGURI PIPED WATER SUPPLY SCHEME | SM/15517 | New | Continuation of work of Hiring of Diesel Vehicle Maxi Cab (At least 7 seater ) for Executive Engineer, Alipurduar Division, P.H.E. Dte. (from 01.04.2025 to 30.04.2025) | HQ-A.E | Birpara Sub Division | ORD/000745/2024-2025 | 5591/ALD | 26/03/2025 | 26/04/2025 | APSARI BHOWMICK | 0.4 | 0 | 0 | 0
16 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | MADHYA KAMAKHYAGURI PIPED WATER SUPPLY SCHEME | SM/15517 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division,,Junior Engineer 1, Northern Mechanical Division-II,PHE ,Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000062/2025-2026 | 1155/NMD-II | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
17 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | MADHYA KAMAKHYAGURI PIPED WATER SUPPLY SCHEME | SM/15517 | New | Yard lighting arrangement at Head Work Site for Different PWSS (PASCHIM CHENGMARI and others) under JJM in the BLOCK: Kumargram, DISTRICT: ALIPURDUAR under NMD-II,PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000138/2025-2026 | 1347/NMD-II | 19/06/2025 | 19/07/2025 | S.K ENTERPRISE | 26.74 | 0 | 0 | 0
18 | ALIPURDUAR | Kumargram | Alipurduar Division | MADHYA KAMAKHYAGURI PIPED WATER SUPPLY SCHEME | SM/15517 | New | Material Requisition To Resource Division |  |  | RTOR000008/2025-2026 | 1566/ALD | 31/07/2025 | 31/07/2025 | Resource Division | 5.78 | 0 | 0 | 0
19 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | MADHYA KAMAKHYAGURI PIPED WATER SUPPLY SCHEME | SM/15517 | New | Additional QUOTATION for Madhya Kamakhyaguri P/H NO-II under NMD-II |  |  | BILL/02039/2024-2025 | BP-454/24-25 | 09/01/2025 | 09/01/2025 | WBSEDCL | 3.03 | 0 | 0 | 0
Total | [13 empty] | 1649.65 | 531.91 | 32.24