## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Kumargram | Alipurduar Division | MADHYA KAMAKHYAGURI PIPED WATER SUPPLY SCHEME | SM/15517 | New | Cons. of pump house and Sinking of 250 mm x 200 mm X 150 mtr. big dia. TW at HW site and 2nd site, LDS with UPVC pipeline, Cons. of 350 cum OHR as per Departmental Design & drawing , providing FHTC and others allied works for MADHYA KAMAKHYAGURI PWSS Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000466/2022-2023 | 3155/ALD | 22/02/2023 | 21/08/2023 | GHOSH & SAHA CONSTRUCTION | 478.58 | 411.1 | 85.9 | 85
2 | ALIPURDUAR | Kumargram | Alipurduar Division | MADHYA KAMAKHYAGURI PIPED WATER SUPPLY SCHEME | SM/15517 | New | Supply of DI pipe & CI special for Madhya Kamakhyaguri PWSS under Alipurduar Division PHE Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000044/2023-2024 | 390/ALD | 19/05/2023 | 18/06/2023 | DILIP MAHATO | 71.61 | 34.22 | 47.79 | 75
3 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | MADHYA KAMAKHYAGURI PIPED WATER SUPPLY SCHEME | SM/15517 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Madhya Kamakhyaguri Water Supply Scheme TW No.-I and II under NMD-II,PHE.Dte,Apd. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000888/2023-2024 | 2466/NMD-II | 11/08/2023 | 10/09/2023 | M/S PARITOSH BHOWMICK & CO. | 21.92 | 0 | 0 | 40
4 | ALIPURDUAR | Kumargram | Alipurduar Division | MADHYA KAMAKHYAGURI PIPED WATER SUPPLY SCHEME | SM/15517 | New | Providing balance FHTC for MADHYA KAMAKHYAGURI PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000249/2023-2024 | 1850/ALD | 04/09/2023 | 19/10/2023 | MONORAMA ENTERPRISE | 5.85 | 0 | 0 | 0
5 | ALIPURDUAR | Kumargram | Alipurduar Division | MADHYA KAMAKHYAGURI PIPED WATER SUPPLY SCHEME | SM/15517 | New | Laying of new UPVC/DI pipeline for interconnection in the distribution system and bridge/culvert crossing, Construction of surface drain, pathway other allied works in connection with the Madhya Kamakhyaguri PWSS Alipurduar Sadar Sub-Division, under Alipurduar Division PHE DTE. .(SM/15517) | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000226/2024-2025 | 2279/ALD | 05/08/2024 | 04/10/2024 | GHOSH & SAHA CONSTRUCTION | 61.08 | 0 | 0 | 0
6 | ALIPURDUAR | Kumargram | Alipurduar Division | MADHYA KAMAKHYAGURI PIPED WATER SUPPLY SCHEME | SM/15517 | New | Material Requisition To Resource Division |  |  | RTOR000104/2023-2024 | 128/ALD | 10/01/2024 |  | Resource Division | 10.13 | 0 | 0 | 0
7 | ALIPURDUAR | Kumargram | Alipurduar Division | MADHYA KAMAKHYAGURI PIPED WATER SUPPLY SCHEME | SM/15517 | New | Material Requisition To Resource Division |  |  | RTOR000032/2023-2024 | 1277/ALD | 11/08/2023 |  | Resource Division | 49.36 | 0 | 0 | 0
8 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | MADHYA KAMAKHYAGURI PIPED WATER SUPPLY SCHEME | SM/15517 | New | QUOTATION FOR NEW SERVICE CONNECTION AT MADHYA KAMAKHYAGURI PWSS PH NO-II |  |  | BILL/00045/2023-2024 | BP-2023-24-42 | 12/05/2023 |  | WBSEDCL | 1.21 | 0 | 0 | 0
9 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | MADHYA KAMAKHYAGURI PIPED WATER SUPPLY SCHEME | SM/15517 | New | QUOTATION FOR NEW SERVICE CONNECTION AT MADHYA KAMAKHYAGURI PWSS PH NO-I |  |  | BILL/00046/2023-2024 | BP-2023-24-41 | 12/05/2023 |  | WBSEDCL | 1.21 | 0 | 0 | 0
Total | [13 empty] | 700.95 | 445.32 | 63.53