## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Kalchini | Alipurduar Division | UTTAR BARAJHAR FOREST PIPE WATER SUPPLY SCHEME | SM/15914 | New | Providing FHTC from existing distribution system as per specification for Uttar Barajhar PWSS PWSS under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000270/2023-2024 | 1887/ALD | 07/09/2023 | 07/10/2023 | TAPASH DAS | 4.24 | 0 | 0 | 0
2 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | UTTAR BARAJHAR FOREST PIPE WATER SUPPLY SCHEME | SM/15914 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Uttar Barajhar FOREST Water Supply Scheme TW No.- I AND II under NMD-II,PHE.Dte,APD. |  |  | ORD/001095/2023-2024 | 2809/NMD-II | 09/10/2023 | 08/11/2023 | SUBODH KUMAR BANIK | 19.86 | 0 | 0 | 0
3 | ALIPURDUAR | Kalchini | Alipurduar Division | UTTAR BARAJHAR FOREST PIPE WATER SUPPLY SCHEME | SM/15914 | New | Material Requisition To Resource Division |  |  | RTOR000034/2022-2023 | 3014/ALD, | 07/02/2023 | 07/02/2023 | Resource Division | 10.87 | 0 | 0 | 0
4 | ALIPURDUAR | Kalchini | Alipurduar Division | UTTAR BARAJHAR FOREST PIPE WATER SUPPLY SCHEME | SM/15914 | New | Tube well Boring by ODEX-165 Method of drilling at HW, FIRST TUBE WELL site including laying distribution system with new UPVC pipeline , Constructions of 100 Cum OHR as per Departmental Design & drawing including soil investigation works, TWO nos. pump house & boundary wall, providing FHTC and others allied works for UTTAR BARAJHAR FOREST PWSS Under Alipurduar Division PHE DTE. (2nd call) | HQ-A.E | RWS Kalchini Block | ORD/000011/2023-2024 | 134/ALD | 24/04/2023 | 21/10/2023 | TAPASH DAS | 193.2 | 32.59 | 16.87 | 15
5 | ALIPURDUAR | Kalchini | Alipurduar Division | UTTAR BARAJHAR FOREST PIPE WATER SUPPLY SCHEME | SM/15914 | New | Material Requisition To Resource Division |  |  | RTOR000079/2023-2024 | 103/ALD | 10/01/2024 | 10/01/2024 | Resource Division | 3.49 | 0 | 0 | 0
6 | ALIPURDUAR | Kalchini | Alipurduar Division | UTTAR BARAJHAR FOREST PIPE WATER SUPPLY SCHEME | SM/15914 | New | Material Requisition To Resource Division |  |  | RTOR000025/2024-2025 | 3983/ALD | 27/11/2024 | 27/11/2024 | Resource Division | 3.49 | 0 | 0 | 0
7 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | UTTAR BARAJHAR FOREST PIPE WATER SUPPLY SCHEME | SM/15914 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division,,Junior Engineer 1, Northern Mechanical Division-II,PHE ,Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000062/2025-2026 | 1155/NMD-II | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
Total | [13 empty] | 961.31 | 32.59 | 3.39