## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Falakata | Northern Mechanical Division II | UMACHARANPUR PIPED WATER SUPPLY SCHEME | SM/16114 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Umacharanpur Water Supply Scheme TW No.-I and II under NMD-II,PHE.Dte,Apd. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Northern Mechanical Division-II,PHE | ORD/000895/2023-2024 | 2476/NMD-II | 11/08/2023 | 10/09/2023 | CINZANO | 21.9 | 0 | 0 | 0
2 | ALIPURDUAR | Falakata | Alipurduar Division | UMACHARANPUR PIPED WATER SUPPLY SCHEME | SM/16114 | New | Construction of tubewells (2 nos.) by Reverse rotary method of drilling at HW site and 2nd TW site, Soil investigation at OHR site, constructions of 500 Cum OHR at HW, construction of pump house and boundary wall at H/W and 2nd site, laying of rising main, distribution line and providing FHTC as per Departmental Design & drawing for Uma Charanpur PWSS Under Birpara Subdivision, Alipurduar Division PHE DTE. | Birpara A.E | RWS Falakata Block | ORD/000251/2023-2024 | 1873/ALD | 07/09/2023 | 03/06/2024 | TAPASH KUMAR BHOWMICK | 608.41 | 121.28 | 19.93 | 37
3 | ALIPURDUAR | Falakata | Alipurduar Division | UMACHARANPUR PIPED WATER SUPPLY SCHEME | SM/16114 | New | Laying of rising main DI (K7), interconnection work with HDPE pipe , Construction of sluice valve chamber for Umacharanpur PWSS under Birpara Sub- Division ,Alipurduar Division PHE Dte. under North Bengal Circle-I PHE DTE. | Birpara A.E | RWS Falakata Block | ORD/000210/2024-2025 | 2061/ALD | 12/07/2024 | 08/05/2025 | TAPASH KUMAR BHOWMICK | 101.24 | 46.59 | 46.02 | 90
4 | ALIPURDUAR | Falakata | Alipurduar Division | UMACHARANPUR PIPED WATER SUPPLY SCHEME | SM/16114 | New | Supply of CI Sluice Valve and Special & CI Jeffy Coupling for Umachndrapur Water Supply Scheme under Alipurduar Division P.H.E. Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000465/2023-2024 | 608/ALD | 29/02/2024 | 30/03/2024 | MANSAROVAR CASTING | 11.95 | 5.98 | 50 | 85
5 | ALIPURDUAR | Falakata | Alipurduar Division | UMACHARANPUR PIPED WATER SUPPLY SCHEME | SM/16114 | New | Material Requisition To Resource Division |  |  | RTOR000065/2023-2024 | 2775/ALD | 18/12/2023 |  | Resource Division | 18.81 | 0 | 0 | 0
6 | ALIPURDUAR | Falakata | Northern Mechanical Division II | UMACHARANPUR PIPED WATER SUPPLY SCHEME | SM/16114 | New | New Service Connection Charges for UMACHARANPUR PWSS P/H NO-I,10 mile |  |  | BILL/00050/2024-2025 | BP-10/24-25 | 08/04/2024 |  | WBSEDCL | 12.04 | 0 | 0 | null
7 | ALIPURDUAR | Falakata | Northern Mechanical Division II | UMACHARANPUR PIPED WATER SUPPLY SCHEME | SM/16114 | New | New Service Connection for Umacharanpur PH NO-II PWSS |  |  | BILL/00987/2024-2025 | BP-276/24-25 | 22/08/2024 |  | WBSEDCL | 10.48 | 0 | 0 | null
Total | [13 empty] | 784.81 | 173.84 | 22.15