## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Kumargram | Alipurduar Division | PURBBA NARATHALI PIPED WATER SUPPLY SCHEME. | SM/16537 | New | Material Requisition To Resource Division |  |  | RTOR000005/2023-2024 | 186/ALD | 28/04/2023 | 28/04/2023 | Resource Division | 246.11 | 0 | 0 | 0
2 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | PURBBA NARATHALI PIPED WATER SUPPLY SCHEME. | SM/16537 | New | QUOTATION FOR NEW SERVICE CONNECTION AT PURBA NARTHALI PWSS PH NO-I |  |  | BILL/00035/2023-2024 | BP-2023-24-49 | 12/05/2023 | 12/05/2023 | WBSEDCL | 1.21 | 0 | 0 | 0
3 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | PURBBA NARATHALI PIPED WATER SUPPLY SCHEME. | SM/16537 | New | QUOTATION FOR NEW SERVICE CONNECTION AT PURBA NARTHALI PWSS PH NO-II |  |  | BILL/00036/2023-2024 | BP-2023-24-48 | 12/05/2023 | 12/05/2023 | WBSEDCL | 1.21 | 0 | 0 | 0
4 | ALIPURDUAR | Kumargram | Alipurduar Division | PURBBA NARATHALI PIPED WATER SUPPLY SCHEME. | SM/16537 | New | Laying of rising main line with HDPE PN10, horizontal boring by HDD method , bridge and culvert crossing, construction of pathway, surface drain and chatal, installation of paver block, land development along with the other allied works at PURBA NARATHALI HW site PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000371/2023-2024 | 87/ALD | 10/01/2024 | 09/04/2024 | MADHAB SAHA | 34.86 | 16.14 | 46.3 | 45
5 | ALIPURDUAR | Kumargram | Alipurduar Division | PURBBA NARATHALI PIPED WATER SUPPLY SCHEME. | SM/16537 | New | Supply of DI specials and CI Jeffy coupling for Purba Narathali Water Supply Scheme(SM/16537) of Kumargram Block under Alipurduar Division P.H.E. Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000514/2023-2024 | 833/ALD | 14/03/2024 | 13/04/2024 | DILIP MAHATO | 13.51 | 0 | 0 | 0
6 | ALIPURDUAR | Kumargram | Alipurduar Division | PURBBA NARATHALI PIPED WATER SUPPLY SCHEME. | SM/16537 | New | Laying of new UPVC/DI pipeline for interconnection in the distribution system, fixing of FHTC by means of PCC Concrete Block and others allied works in connection with the Purba Narathali (SM/16537) PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000348/2024-2025 | 3418/ALD | 26/09/2024 | 25/11/2024 | MADHAB SAHA | 57.8 | 0 | 0 | 0
7 | ALIPURDUAR | Kumargram | Alipurduar Division | PURBBA NARATHALI PIPED WATER SUPPLY SCHEME. | SM/16537 | New | Supply of CIDF Specials and Jeffy Coupling for Purba Narathali (SM/16537) WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000400/2024-2025 | 4266/ALD | 13/12/2024 | 12/01/2025 | HITANGSHU CHOUDHURY | 19.67 | 0 | 0 | 0
8 | ALIPURDUAR | Kumargram | Alipurduar Division | PURBBA NARATHALI PIPED WATER SUPPLY SCHEME. | SM/16537 | New | Land Development, repairing of Pump house, construction of Pathway and protection work of 3rd TW site of Narathali PWSS under Alipurduar Divn, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000334/2023-2024 | 2520/ALD | 24/11/2023 | 23/01/2024 | SREE MAA CONSTRUCTION | 6.99 | 4.93 | 70.52 | 100
9 | ALIPURDUAR | Kumargram | Alipurduar Division | PURBBA NARATHALI PIPED WATER SUPPLY SCHEME. | SM/16537 | New | Repairing of HW site boundary wall (40M), construction of pathway, surface drain, chatal and other misc works related to Narathali PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000338/2023-2024 | 2524/ALD | 24/11/2023 | 23/01/2024 | TAPAN CHANDA | 5.33 | 5.33 | 99.93 | 100
10 | ALIPURDUAR | Kumargram | Alipurduar Division | PURBBA NARATHALI PIPED WATER SUPPLY SCHEME. | SM/16537 | New | Material Requisition To Resource Division |  |  | RTOR000102/2023-2024 | 26/ALD | 10/01/2024 | 10/01/2024 | Resource Division | 10.95 | 0 | 0 | 0
11 | ALIPURDUAR | Kumargram | Alipurduar Division | PURBBA NARATHALI PIPED WATER SUPPLY SCHEME. | SM/16537 | New | Material Requisition To Resource Division |  |  | RTOR000047/2024-2025 | 4267/ALD | 13/12/2024 | 13/12/2024 | Resource Division | 13.19 | 0 | 0 | 0
12 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | PURBBA NARATHALI PIPED WATER SUPPLY SCHEME. | SM/16537 | New | ADDITIONAL QUOTATION FOR PURBA NARARTHALI PH NO-2 |  |  | BILL/00045/2024-2025 | BP-05/24-25 | 08/04/2024 | 08/04/2024 | WBSEDCL | 12.74 | 0 | 0 | 0
13 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | PURBBA NARATHALI PIPED WATER SUPPLY SCHEME. | SM/16537 | New | ADDITIONAL QUOTATION FOR PURBA NARARTHALI PH NO-I |  |  | BILL/00043/2024-2025 | BP-04/24-25 | 08/04/2024 | 08/04/2024 | WBSEDCL | 2.27 | 0 | 0 | 0
14 | ALIPURDUAR | Kumargram | Alipurduar Division | PURBBA NARATHALI PIPED WATER SUPPLY SCHEME. | SM/16537 | New | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA |  |  | BILL/00501/2024-2025 | 321/24-25/PFMS | 14/11/2024 | 14/11/2024 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0 | 0
15 | ALIPURDUAR | Kumargram | Alipurduar Division | PURBBA NARATHALI PIPED WATER SUPPLY SCHEME. | SM/16537 | New | Constructions of pump house & Tube well Boring by ODEX-165 Method of drilling at HW site & 2nd site , laying of distribution system with UPVC pipeline including rising main & delivery connection, Constructions of 250 Cum OHR as per Departmental Design & drawing along with the Soil investigation works , providing FHTC and others allied works for Purba Narathali PWSS Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000550/2022-2023 | 3573ALD | 27/03/2023 | 16/03/2025 | MADHAB SAHA | 373.15 | 311.75 | 83.55 | 5
16 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | PURBBA NARATHALI PIPED WATER SUPPLY SCHEME. | SM/16537 | New | Solarization of grid connected pumping installation at Different PWSS at Kumargram Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P |  | ORD/001206/2024-2025 | 820/NMD-II | 06/03/2025 | 05/04/2025 | WATER TECH | 29.68 | 0 | 0 | 0
17 | ALIPURDUAR | Kumargram | Alipurduar Division | PURBBA NARATHALI PIPED WATER SUPPLY SCHEME. | SM/16537 | New | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Birpara A.E,HQ-A.E | RWS Falakata Block,RWS Kumargram Block | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 02/11/2025 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
18 | ALIPURDUAR | Kumargram | Alipurduar Division | PURBBA NARATHALI PIPED WATER SUPPLY SCHEME. | SM/16537 | New | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna for Kumargram Block under Alipurduar Division, PHE Dte. (Pin point site of the FHTC will be given at the time of issue of work order) | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000081/2025-2026 | 1049/ALD | 17/06/2025 | 16/08/2025 | MOTI INDUSTRIES | 18.14 | 0 | 0 | 0
19 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | PURBBA NARATHALI PIPED WATER SUPPLY SCHEME. | SM/16537 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division,,Junior Engineer 1, Northern Mechanical Division-II,PHE ,Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000062/2025-2026 | 1155/NMD-II | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
20 | ALIPURDUAR | Kumargram | Alipurduar Division | PURBBA NARATHALI PIPED WATER SUPPLY SCHEME. | SM/16537 | New | Laying Rising Main and delivery main connection along with laying of new UPVC/DI pipeline for interconnection in the distribution system and bridge/culvert crossing and other allied works for Nararthali PWSS adjacent to Purba Narathali WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000067/2025-2026 | 819/ALD | 03/06/2025 | 01/09/2025 | NARAYANIMAA EXIM PVT. LTD. | 32.53 | 0 | 0 | 0
Total | [13 empty] | 1743.86 | 338.15 | 19.39