## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Kalchini | Alipurduar Division | UTTAR MANDABARI PIPED WATER SUPPLY SCHEME | SM/16539 | New | Constructions of 250 Cum OHR as per Departmental Design & drawing including laying distribution system with new HDPE pipeline, RISING MAIN, Construction of 2(TWO) NOS of BOUNDARY WALL, 3(THREE) NOS ODEX-165 TUBE WELL, 3(THREE) NOS PUMP HOUSE, Soil Investigation work, providing FHTC and others allied works for UTTAR MANDABARI PWSS(ZONE-I+ZONE-II), Alipurduar Division, PHE DTE. | HQ-A.E | RWS Kalchini Block | ORD/000177/2023-2024 | 1113/ALD | 28/07/2023 | 22/07/2024 | MAHENDRA CHHETRI | 736.75 | 268.08 | 36.39 | 77
2 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | UTTAR MANDABARI PIPED WATER SUPPLY SCHEME | SM/16539 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Uttar Mandabari Water Supply Scheme TW No.- I and II of Zone-I and TW No- I of Zone-II under NMD-II,PHE.Dte,APD. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000894/2023-2024 | 2481/NMD-II | 11/08/2023 | 10/09/2023 | DEY ENTERPRISE (MALDA) | 32.91 | 12.86 | 39.08 | 40
3 | ALIPURDUAR | Kalchini | Alipurduar Division | UTTAR MANDABARI PIPED WATER SUPPLY SCHEME | SM/16539 | New | Providing balance FHTC from existing distribution system as per specification for UTTAR MANDABARI PWSS under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000281/2023-2024 | 1988/ALD | 15/09/2023 | 14/11/2023 | SHYAMAL ROY | 11.35 | 0 | 0 | 0
4 | ALIPURDUAR | Kalchini | Alipurduar Division | UTTAR MANDABARI PIPED WATER SUPPLY SCHEME | SM/16539 | New | Supply of DIDF pipes and specials and Sluice Valve for Uttar Mendabari Water Supply (SM/16539) Scheme OF Kalchini Block under Alipurduar Division P.H.E. Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000203/2024-2025 | 1952/ALD | 02/07/2024 | 01/08/2024 | KAMALA VALVES AND ENGINEERING PRIVATE LIMITED | 16.5 | 0 | 0 | 85
5 | ALIPURDUAR | Kalchini | Alipurduar Division | UTTAR MANDABARI PIPED WATER SUPPLY SCHEME | SM/16539 | New | Material Requisition To Resource Division |  |  | RTOR000019/2023-2024 | 1257/ALD | 10/08/2023 |  | Resource Division | 35.74 | 0 | 0 | 0
6 | ALIPURDUAR | Kalchini | Alipurduar Division | UTTAR MANDABARI PIPED WATER SUPPLY SCHEME | SM/16539 | New | Material Requisition To Resource Division |  |  | RTOR000087/2023-2024 | 111/ALD | 10/01/2024 |  | Resource Division | 14.35 | 0 | 0 | 0
7 | ALIPURDUAR | Kalchini | Alipurduar Division | UTTAR MANDABARI PIPED WATER SUPPLY SCHEME | SM/16539 | New | Material Requisition To Resource Division |  |  | RTOR000011/2024-2025 | 3946/ALD | 26/11/2024 |  | Resource Division | 14.35 | 0 | 0 | 0
8 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | UTTAR MANDABARI PIPED WATER SUPPLY SCHEME | SM/16539 | New | New Service connection for Uttar Mendabari PWSS, Zone-I, P/H no.-I |  |  | BILL/02408/2023-2024 | BP-2023-24-528 | 11/01/2024 |  | WBSEDCL | 6.69 | 0 | 0 | 0
9 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | UTTAR MANDABARI PIPED WATER SUPPLY SCHEME | SM/16539 | New | NEW SERVICE CONNECTION FOR UTTAR MENDABARI PWSS ZONE-I P/H NO-I |  |  | BILL/02470/2023-2024 | BP-2023-24-549 | 18/01/2024 |  | WBSEDCL | 10.65 | 0 | 0 | 0
10 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | UTTAR MANDABARI PIPED WATER SUPPLY SCHEME | SM/16539 | New | New Service Connection Charges for Uttar Medabari PWSS PH NO-I Zone-II Under NMD-II |  |  | BILL/02021/2024-2025 | null | 10/12/2024 |  | WBSEDCL | 8.13 | 0 | 0 | null
Total | [13 empty] | 887.42 | 280.94 | 31.66