## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Kalchini | Alipurduar Division | UTTAR MANDABARI PIPED WATER SUPPLY SCHEME | SM/16539 | New | Providing balance FHTC from existing distribution system as per specification for UTTAR MANDABARI PWSS under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000281/2023-2024 | 1988/ALD | 15/09/2023 | 14/11/2023 | SHYAMAL ROY | 11.35 | 0 | 0 | 0
2 | ALIPURDUAR | Kalchini | Alipurduar Division | UTTAR MANDABARI PIPED WATER SUPPLY SCHEME | SM/16539 | New | Material Requisition To Resource Division |  |  | RTOR000019/2023-2024 | 1257/ALD | 10/08/2023 | 10/08/2023 | Resource Division | 35.74 | 0 | 0 | 0
3 | ALIPURDUAR | Kalchini | Alipurduar Division | UTTAR MANDABARI PIPED WATER SUPPLY SCHEME | SM/16539 | New | Supply of DIDF pipes and specials and Sluice Valve for Uttar Mendabari Water Supply (SM/16539) Scheme OF Kalchini Block under Alipurduar Division P.H.E. Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000203/2024-2025 | 1952/ALD | 02/07/2024 | 01/08/2024 | KAMALA VALVES AND ENGINEERING PRIVATE LIMITED | 16.5 | 0 | 0 | 85
4 | ALIPURDUAR | Kalchini | Alipurduar Division | UTTAR MANDABARI PIPED WATER SUPPLY SCHEME | SM/16539 | New | Material Requisition To Resource Division |  |  | RTOR000087/2023-2024 | 111/ALD | 10/01/2024 | 10/01/2024 | Resource Division | 14.35 | 0 | 0 | 0
5 | ALIPURDUAR | Kalchini | Alipurduar Division | UTTAR MANDABARI PIPED WATER SUPPLY SCHEME | SM/16539 | New | Material Requisition To Resource Division |  |  | RTOR000037/2024-2025 | 4253/ALD | 13/12/2024 | 13/12/2024 | Resource Division | 43.88 | 0 | 0 | 0
6 | ALIPURDUAR | Kalchini | Alipurduar Division | UTTAR MANDABARI PIPED WATER SUPPLY SCHEME | SM/16539 | New | Material Requisition To Resource Division |  |  | RTOR000011/2024-2025 | 3946/ALD | 26/11/2024 | 26/11/2024 | Resource Division | 14.35 | 0 | 0 | 0
7 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | UTTAR MANDABARI PIPED WATER SUPPLY SCHEME | SM/16539 | New | NEW SERVICE CONNECTION FOR UTTAR MENDABARI PWSS ZONE-I P/H NO-I |  |  | BILL/02470/2023-2024 | BP-2023-24-549 | 18/01/2024 | 18/01/2024 | WBSEDCL | 10.65 | 0 | 0 | 0
8 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | UTTAR MANDABARI PIPED WATER SUPPLY SCHEME | SM/16539 | New | New Service Connection Charges for Uttar Medabari PWSS PH NO-I Zone-II Under NMD-II |  |  | BILL/02021/2024-2025 | BP-432/24-25 | 16/12/2024 | 16/12/2024 | WBSEDCL | 8.13 | 0 | 0 | 0
9 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | UTTAR MANDABARI PIPED WATER SUPPLY SCHEME | SM/16539 | New | New Service connection for Uttar Mendabari PWSS, Zone-I, P/H no.-I |  |  | BILL/02408/2023-2024 | BP-2023-24-528 | 11/01/2024 | 11/01/2024 | WBSEDCL | 6.69 | 0 | 0 | 0
10 | ALIPURDUAR | Kalchini | Alipurduar Division | UTTAR MANDABARI PIPED WATER SUPPLY SCHEME | SM/16539 | New | Constructions of 250 Cum OHR as per Departmental Design & drawing including laying distribution system with new HDPE pipeline, RISING MAIN, Construction of 2(TWO) NOS of BOUNDARY WALL, 3(THREE) NOS ODEX-165 TUBE WELL, 3(THREE) NOS PUMP HOUSE, Soil Investigation work, providing FHTC and others allied works for UTTAR MANDABARI PWSS(ZONE-I+ZONE-II), Alipurduar Division, PHE DTE. | HQ-A.E | RWS Kalchini Block | ORD/000177/2023-2024 | 1113/ALD | 28/07/2023 | 17/07/2025 | MAHENDRA CHHETRI | 736.75 | 0 | 0 | 77
11 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | UTTAR MANDABARI PIPED WATER SUPPLY SCHEME | SM/16539 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Uttar Mandabari Water Supply Scheme TW No.- I and II of Zone-I and TW No- I of Zone-II under NMD-II,PHE.Dte,APD. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000894/2023-2024 | 2481/NMD-II | 11/08/2023 | 10/09/2023 | DEY ENTERPRISE (MALDA) | 32.91 | 0 | 0 | 60
12 | ALIPURDUAR | Kalchini | Alipurduar Division | UTTAR MANDABARI PIPED WATER SUPPLY SCHEME | SM/16539 | New | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Birpara A.E,HQ-A.E | RWS Falakata Block,RWS Kumargram Block | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 02/11/2025 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
13 | ALIPURDUAR | Kalchini | Alipurduar Division | UTTAR MANDABARI PIPED WATER SUPPLY SCHEME | SM/16539 | New | Construction of 1 no. pump house, boundary wall, 1 no. T/W boring by ODEX- 165 method of drilling at Uttar Mendabari pwss area under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000463/2024-2025 | 5297/ALD | 07/03/2025 | 05/07/2025 | D.K & SONS | 20.47 | 0 | 0 | 0
14 | ALIPURDUAR | Kalchini | Alipurduar Division | UTTAR MANDABARI PIPED WATER SUPPLY SCHEME | SM/16539 | New | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna for Alipurduar-I Block under Alipurduar Division, PHE Dte. (Pin point site of the FHTC will be given at the time of issue of work order) | HQ-A.E | JUNIOR ENGINEER,RWS Kalchini Block | ORD/000082/2025-2026 | 1050/ALD | 17/06/2025 | 16/08/2025 | MOTI INDUSTRIES | 18.14 | 0 | 0 | 0
15 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | UTTAR MANDABARI PIPED WATER SUPPLY SCHEME | SM/16539 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division,,Junior Engineer 1, Northern Mechanical Division-II,PHE ,Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000062/2025-2026 | 1155/NMD-II | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
16 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | UTTAR MANDABARI PIPED WATER SUPPLY SCHEME | SM/16539 | New | Solarization of grid connected pumping installation at Different PWSS at Kalchini, Madarihat -Birpara ,kumargram Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000131/2025-2026 | 1332/NMD-II | 18/06/2025 | 16/09/2025 | M R S ELECTRICAL | 27.3 | 0 | 0 | 0
Total | [13 empty] | 1797.71 | 0 | 0