## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Falakata | Alipurduar Division | MALSAGAON PIPED WATER SUPPLY SCHEME | SM/16818 | New | Material Requisition To Resource Division |  |  | RTOR000066/2023-2024 | 2776/ALD | 18/12/2023 | 18/12/2023 | Resource Division | 9.12 | 0 | 0 | 0
2 | ALIPURDUAR | Falakata | Alipurduar Division | MALSAGAON PIPED WATER SUPPLY SCHEME | SM/16818 | New | Rising Main, Laying of DI (K7), gap filling of HDPE pipe, construction of sluice valve chamber for washout purpose in the command area of Malsagaon PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | RWS Falakata Block | ORD/000341/2023-2024 | 2542/ALD | 28/11/2023 | 26/02/2024 | BHAGWATI BHUJEL | 76.02 | 76 | 99.97 | 100
3 | ALIPURDUAR | Falakata | Northern Mechanical Division II | MALSAGAON PIPED WATER SUPPLY SCHEME | SM/16818 | New | NEW SERVICE CONNECTION CHARGES FOR MALSAGAON PWSS TW NO-II IN THE DIST OF ALIPURDUAR. |  |  | BILL/00632/2024-2025 | BP-174/24-25 | 03/07/2024 | 03/07/2024 | WBSEDCL | 0.5 | 0 | 0 | 0
4 | ALIPURDUAR | Falakata | Northern Mechanical Division II | MALSAGAON PIPED WATER SUPPLY SCHEME | SM/16818 | New | New Service connection charges under Malsagaon pwss TW no-I in the dist of Alipurduar. |  |  | BILL/00662/2024-2025 | BP-175/24-25 | 03/07/2024 | 03/07/2024 | WBSEDCL | 9.94 | 0 | 0 | 0
5 | ALIPURDUAR | Falakata | Alipurduar Division | MALSAGAON PIPED WATER SUPPLY SCHEME | SM/16818 | New | Construction of tubewells (2 nos.) by Reverse rotary method of drilling at HW site and 2nd TW site, soil investigation at HW site, constructions of 350 Cum OHR at HW, construction of pump house and boundary wall at H/W and 2nd site, laying of rising main, distribution line and providing FHTC as per Departmental Design & drawing for Malsagaon PWSS Under Birpara Subdivision, Alipurduar Division PHE DTE. | Birpara A.E | Alipurduar Sub Division,RWS Falakata Block | ORD/000252/2023-2024 | 1874/ALD | 07/09/2023 | 25/05/2026 | DILIP MAHATO | 517.3 | 494.44 | 95.58 | 90
6 | ALIPURDUAR | Falakata | Northern Mechanical Division II | MALSAGAON PIPED WATER SUPPLY SCHEME | SM/16818 | New | Solarization of grid connected pumping installation at Different PWSS at Falakata Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P |  | ORD/001207/2024-2025 | 821/NMD-II | 06/03/2025 | 05/04/2025 | THE BUSINESS ENGINEERS INDIA | 28.94 | 0 | 0 | 0
7 | ALIPURDUAR | Falakata | Northern Mechanical Division II | MALSAGAON PIPED WATER SUPPLY SCHEME | SM/16818 | New | Yard lighting arrangement at Head Work Site for Different PWSS (PASCHIM DEOGAON and others) under JJM in the BLOCK: Falakata, DISTRICT: ALIPURDUAR under NMD-II,PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Northern Mechanical Division-II,PHE | ORD/000169/2025-2026 | 1385/NMD-II | 26/06/2025 | 26/07/2025 | M/S SAJAHAN CHOWDHURY | 20.56 | 0 | 0 | 0
8 | ALIPURDUAR | Falakata | Northern Mechanical Division II | MALSAGAON PIPED WATER SUPPLY SCHEME | SM/16818 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division,,Junior Engineer 1, Northern Mechanical Division-II,PHE ,Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000062/2025-2026 | 1155/NMD-II | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
9 | ALIPURDUAR | Falakata | Alipurduar Division | MALSAGAON PIPED WATER SUPPLY SCHEME | SM/16818 | New | Laying of HDPE pipeline (new and Parallel ) at Malsagaon PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | RWS Falakata Block | ORD/000134/2025-2026 | 1625/ALD | 04/08/2025 | 18/10/2025 | DILIP MAHATO | 65.97 | 0 | 0 | 0
10 | ALIPURDUAR | Falakata | Northern Mechanical Division II | MALSAGAON PIPED WATER SUPPLY SCHEME | SM/16818 | New | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for Rejuvenation of MALSAGAON water supply scheme, TW no I AND II under JJM under NMD-II, PHE Dte. APD. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Northern Mechanical Division-II,PHE | ORD/000963/2023-2024 | 2572/NMD-II | 22/08/2023 | 02/07/2025 | M/S ANJALI ENTERPRISE | 22.82 | 0 | 0 | 100
Total | [13 empty] | 1477.32 | 570.44 | 38.61