## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Falakata | Alipurduar Division | LACHHIMANDABRI PIPED WATER SUPPLY SCHEME | SM/16819 | New | Material Requisition To Resource Division |  |  | RTOR000038/2023-2024 | 1476/ALD | 16/08/2023 |  | Resource Division | 21.37 | 0 | 0 | 0
2 | ALIPURDUAR | Falakata | Alipurduar Division | LACHHIMANDABRI PIPED WATER SUPPLY SCHEME | SM/16819 | New | Material Requisition To Resource Division |  |  | RTOR000054/2023-2024 | 2700/ALD | 12/12/2023 |  | Resource Division | 84.45 | 0 | 0 | 0
3 | ALIPURDUAR | Falakata | Alipurduar Division | LACHHIMANDABRI PIPED WATER SUPPLY SCHEME | SM/16819 | New | Material Requisition To Resource Division |  |  | RTOR000063/2023-2024 | 2773/ALD | 18/12/2023 |  | Resource Division | 7.84 | 0 | 0 | 0
4 | ALIPURDUAR | Falakata | Alipurduar Division | LACHHIMANDABRI PIPED WATER SUPPLY SCHEME | SM/16819 | New | Supply of CIDF/CIPE pipes and specials & CI Jeffy Coupling for Lachman Dabri Water Supply Scheme under Alipurduar Division P.H.E. Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000478/2023-2024 | 696/ALD | 07/03/2024 | 06/04/2024 | HARIDAS GHOSH | 18.07 | 0 | 0 | 0
5 | ALIPURDUAR | Falakata | Northern Mechanical Division II | LACHHIMANDABRI PIPED WATER SUPPLY SCHEME | SM/16819 | New | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for Rejuvenation of LACHHIAMANDABRI water supply scheme, TW no I AND II under JJM under NMD-II, PHE Dte. APD. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Northern Mechanical Division-II,PHE | ORD/000964/2023-2024 | 2571/NMD-II | 22/08/2023 | 21/09/2023 | DEY ENTERPRISE (MALDA) | 22.2 | 8.89 | 40.02 | 100
6 | ALIPURDUAR | Falakata | Alipurduar Division | LACHHIMANDABRI PIPED WATER SUPPLY SCHEME | SM/16819 | New | Construction of tubewells (2 nos.) by Reverse rotary method of drilling at HW site and 2nd TW site , soil investigation at OHR site, constructions of 300 Cum OHR at HW , construction of pump house and boundary wall at H/W and 2nd site, laying of rising main, distribution line and providing FHTC as per Departmental Design & drawing for Lachhimandabri PWSS Under Birpara Subdivision, Alipurduar Division PHE DTE. | Birpara A.E | Birpara Sub Division | ORD/000183/2023-2024 | 1172/ALD | 03/08/2023 | 30/01/2024 | M/S T M CONSTRUCTION | 433.46 | 49.26 | 11.36 | 35
Total | [13 empty] | 587.39 | 58.15 | 9.9