## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Falakata | Alipurduar Division | BENGKANDI PIPED WATER SUPPLY SCHEME | SM/16820 | New | Material Requisition To Resource Division |  |  | RTOR000043/2023-2024 | 1482/ALD | 16/08/2023 | 16/08/2023 | Resource Division | 21.99 | 0 | 0 | 0
2 | ALIPURDUAR | Falakata | Alipurduar Division | BENGKANDI PIPED WATER SUPPLY SCHEME | SM/16820 | New | Material Requisition To Resource Division |  |  | RTOR000069/2023-2024 | 2782/ALD | 18/12/2023 | 18/12/2023 | Resource Division | 12.78 | 0 | 0 | 0
3 | ALIPURDUAR | Falakata | Alipurduar Division | BENGKANDI PIPED WATER SUPPLY SCHEME | SM/16820 | New | Material Requisition To Resource Division |  |  | RTOR000053/2023-2024 | 2699/ALD | 12/12/2023 | 12/12/2023 | Resource Division | 68.94 | 0 | 0 | 0
4 | ALIPURDUAR | Falakata | Alipurduar Division | BENGKANDI PIPED WATER SUPPLY SCHEME | SM/16820 | New | Supply of CI Sluice Valve and Special & CI Jeffy Coupling for Benkandi Water Supply Scheme under Alipurduar Division P.H.E. Dte. | Alipurduar Sadar Sub Division,Birpara A.E | Birpara Sub Division | ORD/000541/2023-2024 | 754/ALD | 12/03/2024 | 10/06/2024 | SSPR VALVE MANUFACTURING PVT LTD | 12.88 | 12.88 | 100 | 15
5 | ALIPURDUAR | Falakata | Northern Mechanical Division II | BENGKANDI PIPED WATER SUPPLY SCHEME | SM/16820 | New | NEW SERVICE CONNECTION CHARGES AT BENGKANDI PWSS P/H NO-I DIST- ALIPURDUAR. |  |  | BILL/02828/2023-2024 | BP-2023-24-660 | 04/03/2024 | 04/03/2024 | WBSEDCL | 5.92 | 0 | 0 | 0
6 | ALIPURDUAR | Falakata | Northern Mechanical Division II | BENGKANDI PIPED WATER SUPPLY SCHEME | SM/16820 | New | New service Connection Charges at Bengkandi PWSS P/H No- II in the Dist of Alipurduar. |  |  | BILL/02829/2023-2024 | BP-2023-24-659 | 04/03/2024 | 04/03/2024 | WBSEDCL | 4.74 | 0 | 0 | 0
7 | ALIPURDUAR | Falakata | Alipurduar Division | BENGKANDI PIPED WATER SUPPLY SCHEME | SM/16820 | New | Construction of tube wells (2 nos.) by Reverse rotary method of drilling at HW site and 2nd TW site , soil investigation at OHR site, constructions of 400 Cum OHR at HW , construction of pump house and boundary wall at H/W and 2nd site, laying of rising main, distribution line and providing FHTC as per Departmental Design & drawing for Bengkandi PWSS Under Birpara Subdivision, Alipurduar Division PHE DTE. | Birpara A.E | Birpara Sub Division | ORD/000178/2023-2024 | 1114/ALD | 28/07/2023 | 28/09/2025 | M/S ELITE CONSTRUCTION | 655.41 | 402.25 | 61.37 | 51
8 | ALIPURDUAR | Falakata | Northern Mechanical Division II | BENGKANDI PIPED WATER SUPPLY SCHEME | SM/16820 | New | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for Rejuvenation of BENGKANDI water supply scheme, TW no I AND II under JJM under NMD-II,PHE Dte. APD | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Northern Mechanical Division-II,PHE | ORD/000930/2023-2024 | 2541/NMD-II | 16/08/2023 | 19/04/2027 | A.S. ENTERPRISE | 22.88 | 0 | 0 | 90
9 | ALIPURDUAR | Falakata | Alipurduar Division | BENGKANDI PIPED WATER SUPPLY SCHEME | SM/16820 | New | Laying of different dia. HDPE Pipe line and other allied works in connection with Jal Jeevan Mission for Bengkandi PWSS under Alipurduar Division, PHE DTE. | Birpara A.E | Birpara Sub Division | ORD/000424/2024-2025 | 4948/ALD | 06/02/2025 | 07/05/2025 | M/S ELITE CONSTRUCTION | 106.35 | 0 | 0 | 0
10 | ALIPURDUAR | Falakata | Northern Mechanical Division II | BENGKANDI PIPED WATER SUPPLY SCHEME | SM/16820 | New | Yard lighting arrangement at Head Work Site for Different PWSS (PASCHIM DEOGAON and others) under JJM in the BLOCK: Falakata, DISTRICT: ALIPURDUAR under NMD-II,PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Northern Mechanical Division-II,PHE | ORD/000169/2025-2026 | 1385/NMD-II | 26/06/2025 | 26/07/2025 | M/S SAJAHAN CHOWDHURY | 20.56 | 0 | 0 | 0
11 | ALIPURDUAR | Falakata | Northern Mechanical Division II | BENGKANDI PIPED WATER SUPPLY SCHEME | SM/16820 | New | Solarization of grid connected pumping installation at Different PWSS at Falakata Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Northern Mechanical Division-II,PHE | ORD/000134/2025-2026 | 1344/NMD-II | 19/06/2025 | 17/09/2025 | M/S SAJAHAN CHOWDHURY | 42.58 | 0 | 0 | 0
12 | ALIPURDUAR | Falakata | Northern Mechanical Division II | BENGKANDI PIPED WATER SUPPLY SCHEME | SM/16820 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division,,Junior Engineer 1, Northern Mechanical Division-II,PHE ,Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000062/2025-2026 | 1155/NMD-II | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
Total | [13 empty] | 1701.17 | 415.14 | 24.4