## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Falakata | Alipurduar Division | TASTI TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/16822 | New | Collection of house hold details at prescribed format through mobile app/Hard Copy including Geo-reference as directed by the E.I.C. and submission the same (soft copy) to P.H.E. Dte. Part-B | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000048/2023-2024 | 394/ALD | 19/05/2023 | 16/09/2023 | TAPASH KUMAR BHOWMICK | 4.67 | 4.67 | 100 | 0
2 | ALIPURDUAR | Falakata | Alipurduar Division | TASTI TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/16822 | New | Material Requisition To Resource Division |  |  | RTOR000039/2023-2024 | 1478/ALD | 16/08/2023 |  | Resource Division | 40.6 | 0 | 0 | 0
3 | ALIPURDUAR | Falakata | Northern Mechanical Division II | TASTI TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/16822 | New | Supply, delivery, installation, commissioning andtrial run of electro-mechanical components alongwith Cu wound line voltage corrector forRejuvenation of TASTI T.G water supply scheme,TW no I AND II under JJM under NMD-II,PHE Dte.APD. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Northern Mechanical Division-II,PHE | ORD/000938/2023-2024 | 2542/NMD-II | 16/08/2023 | 15/09/2023 | MADHAB SAHA | 21.86 | 0 | 0 | 0
4 | ALIPURDUAR | Falakata | Alipurduar Division | TASTI TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/16822 | New | Material Requisition To Resource Division |  |  | RTOR000062/2023-2024 | 2772/ALD | 18/12/2023 |  | Resource Division | 7.29 | 0 | 0 | 0
5 | ALIPURDUAR | Falakata | Alipurduar Division | TASTI TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/16822 | New | Supply of CIDF/CIPE Pipes and Special & CI Jeffy Coupling for Tasati TG Water Supply Scheme under Alipurduar Division P.H.E. Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000485/2023-2024 | 741/ALD | 12/03/2024 | 11/04/2024 | MADHAB SAHA | 12.19 | 0 | 0 | 0
6 | ALIPURDUAR | Falakata | Alipurduar Division | TASTI TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/16822 | New | Construction of tube wells (2 nos.) by Reverse rotary method of drilling at HW site and 2nd TW site , constructions of 200 Cum OHR at HW including soil investigation, construction of pump house and boundary wall at H/W and 2nd site, laying of rising main, distribution line and providing FHTC as per Departmental Design & drawing for Tasti Tea Garden PWSS Under Birpara Subdivision, Alipurduar Division PHE DTE.(2nd call) | Birpara A.E | Birpara Sub Division | ORD/000170/2023-2024 | 975/ALD | 12/07/2023 | 06/07/2024 | MADHAB SAHA | 298.87 | 47.53 | 15.9 | 15
7 | ALIPURDUAR | Falakata | Northern Mechanical Division II | TASTI TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/16822 | New | NEW SERVICE CONNECTION CHARGES FOR TASTI TG ( NEAR- FOOTBALL MATH) PWSS PH NO-II |  |  | BILL/00619/2024-2025 | BP-142/24-25 | 11/06/2024 |  | WBSEDCL | 5.12 | 0 | 0 | null
8 | ALIPURDUAR | Falakata | Northern Mechanical Division II | TASTI TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/16822 | New | NEW SERVICE CONNECTION CHARGES FOR TASTI TG (NEAR-RATION SHOP) PWSS PH NO-I. |  |  | BILL/00620/2024-2025 | BP-143/24-25 | 11/06/2024 |  | WBSEDCL | 4.53 | 0 | 0 | null
9 | ALIPURDUAR | Falakata | Northern Mechanical Division II | TASTI TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/16822 | New | NEW SERVICE CONNECTION CHARGES FOR TASTI TG (NEAR-RATION SHOP) PWSS PH NO-I. |  |  | BILL/00620/2024-2025 | BP-143/24-25 | 11/06/2024 |  | WBSEDCL | 4.53 | 0 | 0 | null
Total | [13 empty] | 399.68 | 52.2 | 13.06