## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Falakata | Alipurduar Division | TASTI TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/16822 | New | Collection of house hold details at prescribed format through mobile app/Hard Copy including Geo-reference as directed by the E.I.C. and submission the same (soft copy) to P.H.E. Dte. Part-B | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000048/2023-2024 | 394/ALD | 19/05/2023 | 16/09/2023 | TAPASH KUMAR BHOWMICK | 4.67 | 4.67 | 100 | 0
2 | ALIPURDUAR | Falakata | Alipurduar Division | TASTI TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/16822 | New | Material Requisition To Resource Division |  |  | RTOR000039/2023-2024 | 1478/ALD | 16/08/2023 | 16/08/2023 | Resource Division | 40.6 | 0 | 0 | 0
3 | ALIPURDUAR | Falakata | Alipurduar Division | TASTI TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/16822 | New | Material Requisition To Resource Division |  |  | RTOR000062/2023-2024 | 2772/ALD | 18/12/2023 | 18/12/2023 | Resource Division | 7.29 | 0 | 0 | 0
4 | ALIPURDUAR | Falakata | Alipurduar Division | TASTI TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/16822 | New | Construction of tube wells (2 nos.) by Reverse rotary method of drilling at HW site and 2nd TW site , constructions of 200 Cum OHR at HW including soil investigation, construction of pump house and boundary wall at H/W and 2nd site, laying of rising main, distribution line and providing FHTC as per Departmental Design & drawing for Tasti Tea Garden PWSS Under Birpara Subdivision, Alipurduar Division PHE DTE.(2nd call) | Birpara A.E | Birpara Sub Division | ORD/000170/2023-2024 | 975/ALD | 12/07/2023 | 01/05/2025 | MADHAB SAHA | 298.87 | 95.05 | 31.8 | 15
5 | ALIPURDUAR | Falakata | Alipurduar Division | TASTI TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/16822 | New | Supply of CIDF/CIPE Pipes and Special & CI Jeffy Coupling for Tasati TG Water Supply Scheme under Alipurduar Division P.H.E. Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000485/2023-2024 | 741/ALD | 12/03/2024 | 11/04/2024 | MADHAB SAHA | 12.19 | 0 | 0 | 0
6 | ALIPURDUAR | Falakata | Alipurduar Division | TASTI TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/16822 | New | Material Requisition To Resource Division |  |  | RTOR000020/2024-2025 | 3954/ALD | 26/11/2024 | 26/11/2024 | Resource Division | 7.29 | 0 | 0 | 0
7 | ALIPURDUAR | Falakata | Northern Mechanical Division II | TASTI TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/16822 | New | NEW SERVICE CONNECTION CHARGES FOR TASTI TG ( NEAR- FOOTBALL MATH) PWSS PH NO-II |  |  | BILL/00619/2024-2025 | BP-142/24-25 | 11/06/2024 | 11/06/2024 | WBSEDCL | 5.12 | 0 | 0 | 0
8 | ALIPURDUAR | Falakata | Northern Mechanical Division II | TASTI TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/16822 | New | NEW SERVICE CONNECTION CHARGES FOR TASTI TG (NEAR-RATION SHOP) PWSS PH NO-I. |  |  | BILL/00620/2024-2025 | BP-143/24-25 | 11/06/2024 | 11/06/2024 | WBSEDCL | 4.53 | 0 | 0 | 0
9 | ALIPURDUAR | Falakata | Northern Mechanical Division II | TASTI TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/16822 | New | Supply, delivery, installation, commissioning andtrial run of electro-mechanical components alongwith Cu wound line voltage corrector forRejuvenation of TASTI T.G water supply scheme,TW no I AND II under JJM under NMD-II,PHE Dte.APD. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Northern Mechanical Division-II,PHE | ORD/000938/2023-2024 | 2542/NMD-II | 16/08/2023 | 15/09/2023 | MADHAB SAHA | 21.86 | 4.37 | 19.97 | 50
10 | ALIPURDUAR | Falakata | Alipurduar Division | TASTI TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/16822 | New | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Birpara A.E,HQ-A.E | RWS Falakata Block,RWS Kumargram Block | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 02/11/2025 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
11 | ALIPURDUAR | Falakata | Northern Mechanical Division II | TASTI TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/16822 | New | Solarization of grid connected pumping installation at Different PWSS at Falakata Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Northern Mechanical Division-II,PHE | ORD/000134/2025-2026 | 1344/NMD-II | 19/06/2025 | 17/09/2025 | M/S SAJAHAN CHOWDHURY | 42.58 | 0 | 0 | 0
12 | ALIPURDUAR | Falakata | Northern Mechanical Division II | TASTI TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/16822 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division,,Junior Engineer 1, Northern Mechanical Division-II,PHE ,Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000062/2025-2026 | 1155/NMD-II | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
13 | ALIPURDUAR | Falakata | Alipurduar Division | TASTI TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/16822 | New | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna for Falakata Block under Alipurduar Division, PHE Dte. (Pin point site of the FHTC will be given at the time of issue of work order) | Birpara A.E | RWS Falakata Block | ORD/000130/2025-2026 | 1629/ALD | 04/08/2025 | 03/10/2025 | NARENDRA BHADANI. | 18.13 | 0 | 0 | 0
Total | [13 empty] | 1263.66 | 104.09 | 8.24