## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Falakata | Alipurduar Division | DALGAON TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/16823 | New | Construction of tube wells (2 nos.) by Reverse rotary method of drilling at HW site and 2nd TW site , constructions of 200 Cum OHR at HW including soil investigation , construction of pump house and boundary wall at H/W and 2nd site, laying of rising main, distribution line and providing FHTC as per Departmental Design & drawing for Dalgaon Tea Garden PWSS Under Birpara Subdivision, Alipurduar Division PHE DTE. | Birpara A.E | Alipurduar RWS,Birpara Sub Division | ORD/000573/2022-2023 | 3634/ALD | 31/03/2023 | 22/09/2026 | M/S MRITYUNJAY PAUL AND SONS | 390.34 | 197.43 | 50.58 | 51
2 | ALIPURDUAR | Falakata | Northern Mechanical Division II | DALGAON TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/16823 | New | Supply, delivery, installation, commissioning andtrial run of electro-mechanical components alongwith Cu wound line voltage corrector forRejuvenation of DALGAON T.G water supplyscheme, TW no I AND II underJJM under NMD II,PHE Dte. APD. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Northern Mechanical Division-II,PHE | ORD/000935/2023-2024 | 2544/NMD-II | 16/08/2023 | 16/09/2025 | M/S MATRI CONSTRUCTION | 21.85 | 0 | 0 | 100
3 | ALIPURDUAR | Falakata | Alipurduar Division | DALGAON TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/16823 | New | Entry of data for house Connection (JJM) of PWSS in website under Alipurduar division, PHE Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000049/2023-2024 | 395/ALD | 19/05/2023 | 16/09/2023 | TAPASH KUMAR BHOWMICK | 4.29 | 4.29 | 100 | 20
4 | ALIPURDUAR | Falakata | Alipurduar Division | DALGAON TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/16823 | New | Material Requisition To Resource Division |  |  | RTOR000046/2023-2024 | 1954/ALD | 12/09/2023 | 12/09/2023 | Resource Division | 40.05 | 0 | 0 | 0
5 | ALIPURDUAR | Falakata | Alipurduar Division | DALGAON TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/16823 | New | "Supply of DIDF Special and CI Jeffy Coupling for Dalgaon TG Water Supply Scheme(SM/16823) of Falakata Block under Alipurduar Division P.H.E. Dte. " | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000527/2023-2024 | 846/ALD | 14/03/2024 | 12/06/2024 | MADHAB SAHA | 16.41 | 16.41 | 100 | 62
6 | ALIPURDUAR | Falakata | Northern Mechanical Division II | DALGAON TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/16823 | New | NEW SERIVICE CONNECTION CHARGES FOR DALGAON TG PWSS TW NO-I |  |  | BILL/03010/2023-2024 | BP-2023-24-687 | 14/03/2024 | 14/03/2024 | WBSEDCL | 21.42 | 0 | 0 | 0
7 | ALIPURDUAR | Falakata | Alipurduar Division | DALGAON TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/16823 | New | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA |  |  | BILL/00501/2024-2025 | 321/24-25/PFMS | 14/11/2024 | 14/11/2024 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0 | 0
8 | ALIPURDUAR | Falakata | Northern Mechanical Division II | DALGAON TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/16823 | New | NEW SERVICE CONNECTION CHARGE FOR DALGAON TG P/H NO-II |  |  | BILL/03015/2023-2024 | BP-2023-24-692 | 14/03/2024 | 14/03/2024 | WBSEDCL | 4.69 | 0 | 0 | 0
9 | ALIPURDUAR | Falakata | Alipurduar Division | DALGAON TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/16823 | New | Supply of DI/DIDF Specials for Dalgaon TG (SM/16823)WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000410/2024-2025 | 4582/ALD | 02/01/2025 | 01/02/2025 | TAPASH KUMAR BHOWMICK | 16.98 | 0 | 0 | 0
10 | ALIPURDUAR | Falakata | Alipurduar Division | DALGAON TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/16823 | New | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Birpara A.E,HQ-A.E | RWS Falakata Block,RWS Kumargram Block | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 02/11/2025 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
11 | ALIPURDUAR | Falakata | Northern Mechanical Division II | DALGAON TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/16823 | New | Solarization of grid connected pumping installation at Different PWSS at APD-I ,APD-II , Falakata Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Northern Mechanical Division-II,PHE ,Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000132/2025-2026 | 1333/NMD-II | 18/06/2025 | 16/09/2025 | M R S ELECTRICAL | 27.3 | 0 | 0 | 0
12 | ALIPURDUAR | Falakata | Northern Mechanical Division II | DALGAON TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/16823 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division,,Junior Engineer 1, Northern Mechanical Division-II,PHE ,Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000062/2025-2026 | 1155/NMD-II | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
13 | ALIPURDUAR | Falakata | Alipurduar Division | DALGAON TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/16823 | New | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna for Falakata Block under Alipurduar Division, PHE Dte. (Pin point site of the FHTC will be given at the time of issue of work order) | Birpara A.E | RWS Falakata Block | ORD/000130/2025-2026 | 1629/ALD | 04/08/2025 | 03/10/2025 | NARENDRA BHADANI. | 18.13 | 0 | 0 | 0
Total | [13 empty] | 1425.97 | 218.13 | 15.3