## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Kalchini | Alipurduar Division | Malangi Tea Garden Area Piped Water Supply Scheme | SM/18150 | New | Tube well Boring by ODEX-165 Method of drilling at HW, 2nd TUBE WELL site including two nos. pump house and boundary wall, providing FHTC and others allied works for MALANGI TEA GARDEN AREA PWSS Under Alipurduar Division PHE DTE. | HQ-A.E | RWS Kalchini Block | ORD/000018/2023-2024 | 236/ALD | 04/05/2023 | 01/09/2023 | RAMESH SHARMA | 139.9 | 10.6 | 7.58 | 10
2 | ALIPURDUAR | Kalchini | Alipurduar Division | Malangi Tea Garden Area Piped Water Supply Scheme | SM/18150 | New | Constructions of 300 Cum OHR as per Departmental Design & drawing, including laying distribution system with new HDPE pipeline , Rising Main, Soil Investigation work and others allied works for MALANGI TEA GARDEN AREA PWSS Under Alipurduar Division PHE DTE. | HQ-A.E | RWS Kalchini Block | ORD/000175/2023-2024 | 1049/ALD | 20/07/2023 | 16/01/2024 | CAPITAL ENGINEERS | 201.31 | 26.11 | 12.97 | 45
3 | ALIPURDUAR | Kalchini | Alipurduar Division | Malangi Tea Garden Area Piped Water Supply Scheme | SM/18150 | New | Providing balance FHTC from existing distribution system as per specification for MALANGI TG PWSS under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000282/2023-2024 | 1989/ALD | 15/09/2023 | 14/11/2023 | KAMALESH ROY | 10.86 | 0 | 0 | 0
4 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Malangi Tea Garden Area Piped Water Supply Scheme | SM/18150 | New | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for MALANGI T.G water supply scheme, TW no I and II under JJM under NMD-II, PHE Dte. APD. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000990/2023-2024 | 2620/NMD-II | 25/08/2023 | 24/09/2023 | B.B CONCERNED | 21.9 | 0 | 0 | 0
5 | ALIPURDUAR | Kalchini | Alipurduar Division | Malangi Tea Garden Area Piped Water Supply Scheme | SM/18150 | New | Material Requisition To Resource Division |  |  | RTOR000074/2023-2024 | 99/ALD | 10/01/2024 |  | Resource Division | 13.03 | 0 | 0 | 0
6 | ALIPURDUAR | Kalchini | Alipurduar Division | Malangi Tea Garden Area Piped Water Supply Scheme | SM/18150 | New | Material Requisition To Resource Division |  |  | RTOR000024/2024-2025 | 3982/ALD | 27/11/2024 |  | Resource Division | 13.03 | 0 | 0 | 0
7 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Malangi Tea Garden Area Piped Water Supply Scheme | SM/18150 | New | QUOTATION CHARGES FOR MALANGI TG PWSS |  |  | BILL/00273/2024-2025 | BP-66/24-25 | 09/05/2024 |  | WBSEDCL | 1.36 | 0 | 0 | null
8 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Malangi Tea Garden Area Piped Water Supply Scheme | SM/18150 | New | New Service Connection Charges for Malongi TG PWSS PH NO-02 |  |  | BILL/00733/2024-2025 | BP-196/24-25 | 09/07/2024 |  | WBSEDCL | 9.66 | 0 | 0 | null
9 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Malangi Tea Garden Area Piped Water Supply Scheme | SM/18150 | New | New Service connection charges for Malongi TG PWSS PH NO-01, HASHIMARA |  |  | BILL/00734/2024-2025 | BP-195/24-25 | 09/07/2024 |  | WBSEDCL | 5.06 | 0 | 0 | null
Total | [13 empty] | 416.1 | 36.71 | 8.82