## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Kumargram | Alipurduar Division | Chengmari Piped Water Supply Scheme | SM/18152 | New | Supply of CIDF & CISS Pipes and specials for Paschim Chegmari WSS Under Alipurduar Division P.H.E Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000233/2023-2024 | 1597/ALD | 25/08/2023 | 24/09/2023 | M/S SSB CONSTRUCTION CO. | 6.77 | 0 | 0 | 0
2 | ALIPURDUAR | Kumargram | Alipurduar Division | Chengmari Piped Water Supply Scheme | SM/18152 | New | Material Requisition To Resource Division |  |  | RTOR000052/2023-2024 | 2698/ALD | 12/12/2023 | 12/12/2023 | Resource Division | 21.43 | 0 | 0 | 0
3 | ALIPURDUAR | Kumargram | Alipurduar Division | Chengmari Piped Water Supply Scheme | SM/18152 | New | Laying of distribution system with HDPE/DI pipeline, Providing FHTC and others allied works for Chengmari PWSS Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000015/2023-2024 | 233/ALD | 04/05/2023 | 29/01/2024 | HARIDAS GHOSH | 248.85 | 0 | 0 | 65
4 | ALIPURDUAR | Kumargram | Alipurduar Division | Chengmari Piped Water Supply Scheme | SM/18152 | New | Material Requisition To Resource Division |  |  | RTOR000100/2023-2024 | 214/ALD | 10/01/2024 | 10/01/2024 | Resource Division | 10.47 | 0 | 0 | 0
5 | ALIPURDUAR | Kumargram | Alipurduar Division | Chengmari Piped Water Supply Scheme | SM/18152 | New | Material Requisition To Resource Division |  |  | RTOR000014/2024-2025 | 3948/ALD | 26/11/2024 | 26/11/2024 | Resource Division | 10.47 | 0 | 0 | 0
6 | ALIPURDUAR | Kumargram | Alipurduar Division | Chengmari Piped Water Supply Scheme | SM/18152 | New | Material Requisition To Resource Division |  |  | RTOR000050/2024-2025 | 4270/ALD | 13/12/2024 | 13/12/2024 | Resource Division | 22.34 | 0 | 0 | 0
7 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | Chengmari Piped Water Supply Scheme | SM/18152 | New | New Service Connection Charges for Chegmari PWSS PH NO-1 |  |  | BILL/00735/2024-2025 | BP-193/24-25 | 09/07/2024 | 09/07/2024 | WBSEDCL | 3.31 | 0 | 0 | 0
8 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | Chengmari Piped Water Supply Scheme | SM/18152 | New | New Service Connection for Chengmari PWSS P/H NO-2 |  |  | BILL/00825/2024-2025 | BP-272/24-25 | 12/08/2024 | 12/08/2024 | WBSEDCL | 0.76 | 0 | 0 | 0
9 | ALIPURDUAR | Kumargram | Alipurduar Division | Chengmari Piped Water Supply Scheme | SM/18152 | New | Constructions of pump house and Tube well Boring by ODEX-165 Method of drilling at HW site and 2nd site, Laying of distribution system with HDPE pipeline including rising main and delivery connection, Constructions of 200 Cum OHR as per Departmental Design and drawing along with the Soil investigation works, providing FHTC and others allied works for Chengmari PWSS Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000055/2023-2024 | 423/ALD | 24/05/2023 | 01/04/2025 | HARIDAS GHOSH | 240.7 | 0 | 0 | 85
10 | ALIPURDUAR | Kumargram | Alipurduar Division | Chengmari Piped Water Supply Scheme | SM/18152 | New | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Birpara A.E,HQ-A.E | RWS Falakata Block,RWS Kumargram Block | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 02/11/2025 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
11 | ALIPURDUAR | Kumargram | Alipurduar Division | Chengmari Piped Water Supply Scheme | SM/18152 | New | Laying of new HDPE pipeline for interconnection in the distributation system and bridge/culvert crossing and other allied works in connection with Chengmari PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000078/2025-2026 | 976/ALD | 12/06/2025 | 10/09/2025 | HARI CONSTRUCTION | 49.29 | 0 | 0 | 0
12 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | Chengmari Piped Water Supply Scheme | SM/18152 | New | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for CHENGMARI water supply scheme, TW no I AND II under JJM under NMD-II, PHE Dte. APD. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000992/2023-2024 | 2622/NMD-II | 25/08/2023 | 04/04/2025 | P K ENGINEERING | 22 | 0 | 0 | 100
Total | [13 empty] | 710.73 | 0 | 0