## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Kalchini | Alipurduar Division | Bhutri Forest Piped Water Supply Scheme | SM/18156 | New | Tube well Boring by ODEX-165 Method of drilling at TUBE WELL site including laying distribution system with new HDPE pipeline ,One nos pump house & boundary wall, providing FHTC and others allied works for Bhutri Forest PWSS Under Alipurduar Division PHE DTE. | HQ-A.E | RWS Kalchini Block | ORD/000010/2023-2024 | 94/ALD | 18/04/2023 | 16/08/2023 | FAUDA SINGH CHHETRI | 34.7 | 0 | 0 | 100
2 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Bhutri Forest Piped Water Supply Scheme | SM/18156 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for BHUTRI FOREST Water Supply Scheme TW No- I under NMDII, PHE.Dte,APD. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/001102/2023-2024 | 2836/NMD-II | 12/10/2023 | 11/11/2023 | PRAGATI CONSTRUCTION COMPANY | 10.18 | 4.9 | 48.11 | 100
3 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Bhutri Forest Piped Water Supply Scheme | SM/18156 | New | NEW SERVICE CONNECTION FOR BHUTRI FOREST PWSS P/H NO I,KALCHINI APPLICATION NO 4003208197 |  |  | BILL/01827/2023-2024 | BP-2023-24-320 | 27/09/2023 |  | WBSEDCL | 4.1 | 0 | 0 | 0
Total | [13 empty] | 48.97 | 4.9 | 10