## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | Purbba Majherdabri Tea Garden Area Piped Water Supply Scheme | SM/18157 | New | Supply of DIDF Pipes and DI Special and CI Jeffy Coupling for Purba Majherdabri TG Water Supply Scheme (SM/18157) of Alipurduar-II Block under Alipurduar Division P.H.E. Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000217/2024-2025 | 2069/ALD | 12/07/2024 | 11/08/2024 | GUHA ENTERPRISE | 8.02 | 8.02 | 100 | 100
2 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | Purbba Majherdabri Tea Garden Area Piped Water Supply Scheme | SM/18157 | New | Material Requisition To Resource Division |  |  | RTOR000023/2024-2025 | 39818/ALD | 27/11/2024 | 27/11/2024 | Resource Division | 9.47 | 0 | 0 | 0
3 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | Purbba Majherdabri Tea Garden Area Piped Water Supply Scheme | SM/18157 | New | NEW SERVICE CONNECTION CHARGE FOR PURBA MAJHERDABRI W/S/SCHEME PH NO.I |  |  | BILL/02800/2023-2024 | BP-2023-24-640 | 29/02/2024 | 29/02/2024 | WBSEDCL | 3.89 | 0 | 0 | 0
4 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | Purbba Majherdabri Tea Garden Area Piped Water Supply Scheme | SM/18157 | New | NEW SERVICE CONNECTION CHARGE AT PURBA MAJHERDABRI W/S/SCHEME PH NO.II |  |  | BILL/02801/2023-2024 | BP-2023-24-641 | 29/02/2024 | 29/02/2024 | WBSEDCL | 6.04 | 0 | 0 | 0
5 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | Purbba Majherdabri Tea Garden Area Piped Water Supply Scheme | SM/18157 | New | Cons. of pump house and Tube well Boring by ODEX-165 Method of drilling at HW site and 2nd site, LDS with HDPE pipeline including rising main and delivery connection, Cons. of 100 Cum OHR as per Dept. Design and drawing along with the Soil investigation works, providing FHTC and other allied works for Purba Majherdabri TG PWSS Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000050/2023-2024 | 406/ALD | 22/05/2023 | 01/04/2025 | DAS CONSTRUCTION | 212.4 | 155.27 | 73.1 | 35
6 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | Purbba Majherdabri Tea Garden Area Piped Water Supply Scheme | SM/18157 | New | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for PURBBA MAJHERDABRI T.G. AREA water supply scheme, TW no I AND II under JJM under NMD-II, PHE Dte. APD. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000995/2023-2024 | 2624/NMD-II | 25/08/2023 | 26/04/2025 | BONANZA ENTERPRISE | 21.27 | 5.17 | 24.31 | 100
Total | [13 empty] | 261.1 | 168.47 | 64.52