## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Alipurduar-I | Northern Mechanical Division II | Parpatla Khawa Piped Water Supply Scheme | SM/18158 | New | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for PARPATLA KHAWA water supply scheme, TW no I and II of under JJM under NMD-II, PHE Dte. APD. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000993/2023-2024 | 2625/NMD-II | 25/08/2023 | 24/09/2023 | HARA PROSAD DAS | 21.25 | 0 | 0 | 40
2 | ALIPURDUAR | Alipurduar-I | Northern Mechanical Division II | Parpatla Khawa Piped Water Supply Scheme | SM/18158 | New | NEW SERVICE CONNECTION CHARGES FOR PAR PATLAKHAWA PWSS P/H NO-I |  |  | BILL/03128/2023-2024 | BP-235/24-25 | 29/07/2024 | 29/07/2024 | WBSEDCL | 6.17 | 0 | 0 | 0
3 | ALIPURDUAR | Alipurduar-I | Northern Mechanical Division II | Parpatla Khawa Piped Water Supply Scheme | SM/18158 | New | New Service Connection Charges for Parpatlakhowa PWSS PH NO-II under NMD-II |  |  | BILL/01893/2024-2025 | BP-427/24-25 | 16/12/2024 | 16/12/2024 | WBSEDCL | 13.63 | 0 | 0 | 0
4 | ALIPURDUAR | Alipurduar-I | Alipurduar Division | Parpatla Khawa Piped Water Supply Scheme | SM/18158 | New | Boring of Tube Well by reverse rotary method, Construction of Pump House, Boundary Wall, Laying Of Distribution System and providing FHTC for Parpatlakhawa PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS | JUNIOR ENGINEER,RWS Madarihat - Birpara Block | ORD/000017/2023-2024 | 235/ALD | 04/05/2023 | 23/04/2025 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 113.69 | 70.52 | 62.03 | 16
5 | ALIPURDUAR | Alipurduar-I | Alipurduar Division | Parpatla Khawa Piped Water Supply Scheme | SM/18158 | New | Supply and installation of sign board at different PWSS site of Kumargram Block under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000053/2025-2026 | 679/ALD | 21/05/2025 | 05/07/2025 | TAPASH DAS | 4.69 | 0 | 0 | 100
6 | ALIPURDUAR | Alipurduar-I | Alipurduar Division | Parpatla Khawa Piped Water Supply Scheme | SM/18158 | New | Gap filling of distribution line, land development and other allied works for ParpatlaKhawa Piped Water Supply Scheme within Alipurduar Block-I under Alipurduar Division, PHE Dte. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000066/2025-2026 | 818/ALD | 03/06/2025 | 17/08/2025 | CHITTA RANJAN DEY | 20.25 | 0 | 0 | 0
7 | ALIPURDUAR | Alipurduar-I | Northern Mechanical Division II | Parpatla Khawa Piped Water Supply Scheme | SM/18158 | New | Additional Quotation for PARPATLAKHAWA PWSS PH NO-I Against Ref ID-4003317590 in the dist. of Alipurduar Under NMD-II |  |  | BILL/00354/2025-2026 |  | 07/05/2025 | 07/05/2025 | WBSEDCL | 0.36 | 0 | 0 | 0
Total | [13 empty] | 180.05 | 70.52 | 39.17