## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DALIMPUR PWSS | SM/18254 | Augmentation | Soil investigation work at 3 different places of Dalimpur within Alipurduar District under Alipurduar Division PHE Dte. | Birpara A.E | RWS Falakata Block | ORD/000160/2023-2024 | 965/ALD | 12/07/2023 | 11/08/2023 | CITY ENGINEERING & TESTING LABORATORY | 3.67 | 3.67 | 100 | 100
2 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DALIMPUR PWSS | SM/18254 | Augmentation | Construction of Pump House, Boundary Wall, Tube well Boring by Reverse Rotary Method of drilling including Rising Main at H/W site and 2nd site along with repairing of office godown for Dalimpur Zone-I PWSS Under Alipurduar Division PHE DTE. | Birpara A.E | RWS Falakata Block | ORD/000167/2023-2024 | 973/ALD | 12/07/2023 | 06/07/2024 | NARAYAN CHANDRA SAHA | 48.31 | 48.23 | 99.84 | 65
3 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DALIMPUR PWSS | SM/18254 | Augmentation | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna (Schools, AWC and others) for Dalimpur PWSS under Alipurduar Division, PHE Dte. Part-3 | Birpara A.E | RWS Falakata Block | ORD/000162/2023-2024 | 966/ALD | 12/07/2023 | 08/01/2024 | TAPASH DAS | 34.77 | 4.52 | 13 | 15
4 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DALIMPUR PWSS | SM/18254 | Augmentation | Laying of distribution of UPVC/DI/GI pipeline including FHTC for DALIMPUR PWSS under Alipurduar Division, PHE DTE. PART-2 | Birpara A.E | RWS Falakata Block | ORD/000165/2023-2024 | 970/ALD | 12/07/2023 | 03/11/2024 | MITHUN DAS | 67.93 | 63.74 | 93.84 | 65
5 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DALIMPUR PWSS | SM/18254 | Augmentation | Laying of Rising Main, road and culvert crossing and distribution pipeline in DALIMPUR PWSS (Zone-III) under Alipurduar Division, PHE Dte | Birpara A.E | RWS Falakata Block | ORD/000319/2023-2024 | 2411/ALD | 09/11/2023 | 06/07/2024 | NARENDRA BHADANI. | 17.66 | 16.47 | 93.27 | 10
6 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DALIMPUR PWSS | SM/18254 | Augmentation | Road crossing, hume pipe culvert crossing, and bridge crossing by G.I. pipe at Dalimpur Zone-III PWSS including Laying of UPVC Pipeline for left out household connection of Birpara Sub-Division under Alipurduar Division, P.H.E. Dte. (SM/18254) | Birpara A.E | RWS Falakata Block | ORD/000512/2023-2024 | 830/ALD | 14/03/2024 | 13/05/2024 | MITHUN DAS | 9.04 | 8.79 | 97.22 | 10
7 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DALIMPUR PWSS | SM/18254 | Augmentation | Laying of rising Main,Road and Calvert crossing and Balance distribution pipeline in Dalimpur(Zone-I) under Alipurduar Division,PHE Dte of North Bengal Circle-I, PHE Dte. under JJM Programme. | Birpara A.E | RWS Falakata Block | ORD/000466/2023-2024 | 670/ALD | 06/03/2024 | 31/12/2024 | UJJWAL ROY | 132.1 | 121.02 | 91.62 | 80
8 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DALIMPUR PWSS | SM/18254 | Augmentation | Construction of 150cum. OHR for DALIMPUR ZONE-III Water Supply Scheme under Alipurduar Division, PHE Dte. | Birpara A.E | RWS Falakata Block | ORD/000169/2023-2024 | 972/ALD | 12/07/2023 | 06/07/2024 | UJJWAL ROY | 50.43 | 40.91 | 81.12 | 100
9 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DALIMPUR PWSS | SM/18254 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000012/2024-2025 | 3947/ALD | 26/11/2024 | 26/11/2024 | Resource Division | 25.05 | 0 | 0 | 0
10 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF DALIMPUR PWSS | SM/18254 | Augmentation | New service connection Charges for Dalimpur PWSS Zone-I PH NO-I under NMD-II |  |  | BILL/01887/2024-2025 | BP-426/24-25 | 16/12/2024 | 16/12/2024 | WBSEDCL | 5.05 | 0 | 0 | 0
11 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF DALIMPUR PWSS | SM/18254 | Augmentation | New Service Connection Charges For Aug of Dalimpur Zone-III PH NO-I under NMD-II |  |  | BILL/01892/2024-2025 | BP-425/24-25 | 16/12/2024 | 16/12/2024 | WBSEDCL | 16.01 | 0 | 0 | 0
12 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF DALIMPUR PWSS | SM/18254 | Augmentation | New Service Connection Charges for Aug of Dalimpur Zone-I PH NO-II under NMD-II |  |  | BILL/01890/2024-2025 | BP-424/24-25 | 16/12/2024 | 16/12/2024 | WBSEDCL | 5.85 | 0 | 0 | 0
13 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DALIMPUR PWSS | SM/18254 | Augmentation | Construction of 400cum OHR for DALIMPUR ZONE-I Water Supply Scheme under Alipurduar Division, PHE Dte. | Birpara A.E | RWS Falakata Block | ORD/000161/2023-2024 | 968/ALD | 12/07/2023 | 28/12/2025 | NARAYAN CHANDRA SAHA | 77.28 | 28.26 | 36.57 | 60
14 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF DALIMPUR PWSS | SM/18254 | Augmentation | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for AUGUMENTATION OF DALIMPUR water supply scheme, TW no I and II of Zone - I and TW no I and II of Zone - II and TW no I and II of Zone - III under Jal Jeevan Mission under NMD-II, PHE Dte. Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Northern Mechanical Division-II,PHE | ORD/000875/2023-2024 | 2453/NMD-II | 11/08/2023 | 01/02/2025 | ALPHA ENTERPRISE | 65.55 | 7.99 | 12.19 | 35
15 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DALIMPUR PWSS | SM/18254 | Augmentation | Providing FHTC from existing distribution system as per specification for DALIMPUR PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | RWS Falakata Block | ORD/000287/2023-2024 | 1995/ALD | 15/09/2023 | 03/11/2025 | SREE MAA CONSTRUCTION | 28.8 | 9.96 | 34.59 | 45
16 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DALIMPUR PWSS | SM/18254 | Augmentation | Balance work of rising main, delivery main, bypass arrangement, land development, pipeline for left out household connection and other allied works at Augmentation of Dalimpur(Zone-3)(H/W site) of Birpara Sub-Division under Alipurduar Division, PHE Dte. (SM/18254) | Birpara A.E | RWS Falakata Block | ORD/000502/2023-2024 | 820/ALD | 14/03/2024 | 07/07/2025 | UJJWAL ROY | 41.61 | 0 | 0 | 40
17 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DALIMPUR PWSS | SM/18254 | Augmentation | LAYING OF DISTRIBUTION PIPELINE AT DALIMPUR (ZONE-II, PART-A) PWSS UNDER ALIPURDUAR DIVISION, PHE DTE. | Birpara A.E | RWS Falakata Block | ORD/000401/2024-2025 | 4537/ALD | 26/12/2024 | 25/04/2025 | HITANGSHU CHOUDHURY | 55.82 | 0 | 0 | 80
18 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DALIMPUR PWSS | SM/18254 | Augmentation | LAYING OF DISTRIBUTION PIPELINE AT DALIMPUR (ZONE-II, PART-B) PWSS UNDER ALIPURDUAR DIVISION, PHE DTE. | Birpara A.E | RWS Falakata Block | ORD/000452/2024-2025 | 5169/ALD | 25/02/2025 | 23/10/2025 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 55.35 | 0 | 0 | 10
19 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DALIMPUR PWSS | SM/18254 | Augmentation | Construction of Pump House, Boundary Wall, Tube well Boring by Reverse Rotary Method of drilling including Rising Main at H/W site and 2nd site for Dalimpur Zone-III PWSS Under Alipurduar Division PHE DTE. | Birpara A.E | RWS Falakata Block | ORD/000164/2023-2024 | 967/ALD | 12/07/2023 | 31/07/2025 | NARENDRA BHADANI. | 45.9 | 44.65 | 97.27 | 100
Total | [13 empty] | 786.18 | 398.23 | 50.65