## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | OPERATION CHARGES-PROCUREMENT OF CHEMICALS-GLASSWARE-COMPUTER MAINTENANCE OF PHED MANAGED LABORATORIES RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION | SM/19081 | Support-WQMSP | Continuation work of "Monthly remuneration of PHE managed Alipurduar District water testing laboratory personnel (5 Nos), Samuktalasub-district water testing laboratory personnel (3 Nos), Birpara Sub-district Water testing Laboratory personnel (3 Nos), for 12 months including arrear for 4 months, under Alipurduar Division, PHE Dte." (from 01/09/2024 to 30/09/2024) | Alipurduar RWS | JUNIOR ENGINEER | ORD/000319/2024-2025 | 3110/ALD | 29/08/2024 | 29/09/2024 | TAPAN CHANDA | 2.22 | 2.22 | 100 | 100
2 | ALIPURDUAR |  | Alipurduar Division | OPERATION CHARGES-PROCUREMENT OF CHEMICALS-GLASSWARE-COMPUTER MAINTENANCE OF PHED MANAGED LABORATORIES RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION | SM/19081 | Support-WQMSP | Continuation work of "Monthly remuneration of PHE managed Alipurduar District water testing laboratory personnel (5 Nos), Samuktalasub-district water testing laboratory personnel (3 Nos), Birpara Sub-district Water testing Laboratory personnel (3 Nos), for 12 months including arrear for 4 months, under Alipurduar Division, PHE Dte." (from 01/05/2024 to 31/08/2024) | Alipurduar RWS | Alipurduar Sub Division | ORD/000087/2024-2025 | 1315/ALD | 24/04/2024 | 24/08/2024 | TAPAN CHANDA | 8.9 | 8.9 | 100 | 100
3 | ALIPURDUAR |  | Alipurduar Division | OPERATION CHARGES-PROCUREMENT OF CHEMICALS-GLASSWARE-COMPUTER MAINTENANCE OF PHED MANAGED LABORATORIES RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION | SM/19081 | Support-WQMSP | Monthly Remuneration and day to day operation and maintenance of PHED managed Alipurduar District water testing laboratory personnel (5 Nos), Samuktalasub-district water testing laboratory personnel (3 Nos), Birpara Sub-district Water testing Laboratory personnel (3 Nos) and day to day operation and maintenance of the laboratories for 06 months , under Alipurduar Division, PHE Dte. (from 01.10.2024 to 31.03.2025) | Alipurduar RWS | JUNIOR ENGINEER | ORD/000357/2024-2025 | 3473/ALD | 30/09/2024 | 31/03/2025 | TAPAN CHANDA | 16.68 | 16.68 | 99.99 | 100
Total | [13 empty] | 27.8 | 27.8 | 100