## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | INFORMATION EDUCATION COMMUNICATION (IEC) ACTIVITIES RELATED TO JUDICIOUS & SAFE USE OF DRINKING WATER,WATER CONSERVATION,WATER QUALITY ISSUES AND WASH ISSUES UNDER JALJEEVAN MISSION (JJM) SUPPORT ACTIVITIES AT ALIPURDUAR DISTRICT- July-2023 | SM/19170 | Support-IEC | Execution of Special Community Mobilization and Community ownership drive on JJM/ FHTC ; save water; water conservation, illegal pumping & connection ; safe handling & storage of safe water; Quality issues and other WASH related issues as per guideline of JJM for For Alipurduar I & II Block under Alipurduar District under Alipurduar Division, PHE Dte, , Govt. of West Bengal. (Package 1 ) | HQ-A.E | RWS Kumargram Block | ORD/000033/2025-2026 | 494/ALD | 07/05/2025 | 04/11/2025 | LIMRA SOCIAL WELFARE SOCIETY | 30.97 | 0 | 0 | 30
2 | ALIPURDUAR |  | Alipurduar Division | INFORMATION EDUCATION COMMUNICATION (IEC) ACTIVITIES RELATED TO JUDICIOUS & SAFE USE OF DRINKING WATER,WATER CONSERVATION,WATER QUALITY ISSUES AND WASH ISSUES UNDER JALJEEVAN MISSION (JJM) SUPPORT ACTIVITIES AT ALIPURDUAR DISTRICT- July-2023 | SM/19170 | Support-IEC | "Execution of Special Community Mobilization and Community ownership drive on JJM/ FHTC ; save water; water conservation, illegal pumping & connection ; safe handling & storage of safe water; Quality issues and other WASH related issues as per guideline of JJM For Falakata & Kalchini Block under Alipurduar District under Alipurduar Division, PHE Dte, , Govt. of West Bengal. (Package -2 )" | HQ-A.E | RWS Kumargram Block | ORD/000034/2025-2026 | 495/ALD | 07/05/2025 | 04/11/2025 | BARMAN ENTERPRISE | 30.97 | 0 | 0 | 40
3 | ALIPURDUAR |  | Alipurduar Division | INFORMATION EDUCATION COMMUNICATION (IEC) ACTIVITIES RELATED TO JUDICIOUS & SAFE USE OF DRINKING WATER,WATER CONSERVATION,WATER QUALITY ISSUES AND WASH ISSUES UNDER JALJEEVAN MISSION (JJM) SUPPORT ACTIVITIES AT ALIPURDUAR DISTRICT- July-2023 | SM/19170 | Support-IEC | "Execution of Special Community Mobilization and Community ownership drive on JJM/ FHTC ; save water; water conservation, illegal pumping & connection ; safe handling & storage of safe water; Quality issues and other WASH related issues as per guideline of JJM For Kumargram & Madarihat Block under Alipurduar District under Alipurduar Division, PHE Dte, , Govt. of West Bengal. ( Package -3 )" | HQ-A.E | RWS Kumargram Block | ORD/000035/2025-2026 | 496/ALD | 07/05/2025 | 04/11/2025 | LIMRA SOCIAL WELFARE SOCIETY | 30.47 | 0 | 0 | 26
Total | [13 empty] | 92.41 | 0 | 0