## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Retrofitting for FHTC & Improvement of piped water supply scheme for Pedong Bazar & adjoining areas in connection with (JJM & Jal swapno) | SM/07872 | Retrofitting | Retrofitting for Functional Household Tap Connection (FHTC) of Piped Water Supply Scheme for Pedong Bazar and adjoining areas , Under Neorakhola W/S & Maintenance Division, P.H.Engineering Directorate, District- Kalimpong. | Assistant Engineer I | Junior Engineer III | ORD/000050/2020-2021 | 187/NKWSMD | 12/10/2020 | 11/12/2020 | LEGDEN PRADHAN | 21.21 | 42.12 | 198.59 | 100
2 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Retrofitting for FHTC & Improvement of piped water supply scheme for Pedong Bazar & adjoining areas in connection with (JJM & Jal swapno) | SM/07872 | Retrofitting | Retrofitting in connection with improvement of piped water supply scheme for Pedong Bazar and adjoining areas under Neorakhola W/S & Mtc. Division, P.H.Engineering Directorate, District- Kalimpong. | Assistant Engineer I | Junior Engineer III | ORD/000051/2020-2021 | 297/NKWSMD | 25/01/2021 | 26/03/2021 | LEGDEN PRADHAN | 35.86 | 51.65 | 144.01 | 100
3 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Retrofitting for FHTC & Improvement of piped water supply scheme for Pedong Bazar & adjoining areas in connection with (JJM & Jal swapno) | SM/07872 | Retrofitting | Laying of 65mm G.I. pipe from Upper Thukchu khola towards Pipli Dara under piped water supply scheme for Pedong Bazar and Adjoining Area in Dist-Kalimpong, Block-II, under Neorakhola W/S & Mtc Division under PHE Dte Kalimpong. | Assistant Engineer I | Junior Engineer III | ORD/000102/2021-2022 | 269/NKWSMD | 23/11/2021 | 23/12/2021 | LEGDEN PRADHAN | 4.08 | 3.41 | 83.68 | 100
4 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Retrofitting for FHTC & Improvement of piped water supply scheme for Pedong Bazar & adjoining areas in connection with (JJM & Jal swapno) | SM/07872 | Retrofitting | Laying of 65mm G.I. pipe from Link road towards Pedong Bazar under piped water supply scheme for Pedong Bazar and Adjoining Area in Dist-Kalimpong, Block-II, under Neorakhola W/S & Mtc Division under PHE Dte Kalimpong. | Assistant Engineer I | Junior Engineer III | ORD/000103/2021-2022 | 270/NKWSMD | 23/11/2021 | 23/12/2021 | LEGDEN PRADHAN | 4.71 | 4.09 | 86.87 | 100
5 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Retrofitting for FHTC & Improvement of piped water supply scheme for Pedong Bazar & adjoining areas in connection with (JJM & Jal swapno) | SM/07872 | Retrofitting | Restoration of pipeline of Piped Water Supply Scheme for Pedong Bazar adjoining areas damaged during this monsoon season. | Assistant Engineer I | Junior Engineer III | ORD/000289/2023-2024 | 303/NKWSMD | 27/02/2024 | 27/04/2024 | LEGDEN PRADHAN | 8.56 | 5.13 | 60 | 100
Total | [13 empty] | 74.42 | 106.41 | 142.98