## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Retrofitting of Neorakhola piped water supply scheme to provide Functional Household Tap Connection to the enroute villages of the scheme in Kalimpong Block I & II in Kalimpong District under JJM & JAL SWAPNA Programme | SM/08693 | Retrofitting | Retrofitting of Neorakhola piped water supply scheme to Provide Functional House Hold Tap connection to the en-route villages of the scheme in Kalimpong Block I & II in Kalimpong District under JJM & JAL SWAPNA Programme under Neorakhola Water Supply & Mtc Division under PHE Dte , Kalimpong | Assistant Engineer I | Junior Engineer IV | ORD/000020/2021-2022 | 167/NKWSMD | 06/09/2021 | 06/10/2021 | SONAM TOPGAY BHUTIA | 49.43 | 49.08 | 99.29 | 90
2 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Retrofitting of Neorakhola piped water supply scheme to provide Functional Household Tap Connection to the enroute villages of the scheme in Kalimpong Block I & II in Kalimpong District under JJM & JAL SWAPNA Programme | SM/08693 | Retrofitting | Retrofitting of Neorakhola piped water supply scheme to Provide Functional House Hold Tap connection to the en-route villages of the scheme in Kalimpong Block I in Kalimpong District under JJM & JAL SWAPNA Programme under Neorakhola Water Supply & Mtc Division under PHE Dte , Kalimpong | Assistant Engineer I | Junior Engineer I | ORD/000019/2021-2022 | 166/NKWSMD | 06/09/2021 | 06/10/2021 | SONAM TOPGAY BHUTIA | 48.79 | 48.32 | 99.03 | 90
3 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Retrofitting of Neorakhola piped water supply scheme to provide Functional Household Tap Connection to the enroute villages of the scheme in Kalimpong Block I & II in Kalimpong District under JJM & JAL SWAPNA Programme | SM/08693 | Retrofitting | Engagement of 1(One) no. computer operator (graduate with certificate in computer application) for the works related to JJM/Jal swapna at the Office of the S.E. GTA, P.H.E. Dte from 01.06.2022 to 31.05.2023 | Assistant Engineer II | Junior Engineer I | ORD/000152/2022-2023 | 681/NKWSMD | 31/05/2022 | 31/05/2023 | THE ELECTRIC SPHERE | 2.47 | 0.39 | 15.9 | 45
4 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Retrofitting of Neorakhola piped water supply scheme to provide Functional Household Tap Connection to the enroute villages of the scheme in Kalimpong Block I & II in Kalimpong District under JJM & JAL SWAPNA Programme | SM/08693 | Retrofitting | Engagement of 2(Two) no. computer operator (graduate with certificate in computer application) for the works related to JJM/Jal swapna at the Office of the Executive Engineer, Neorakhola W/S & Mtc. Division, P.H.E. Dte from 01.06.2022 to 31.05.2023 | Assistant Engineer II | Junior Engineer I | ORD/000150/2022-2023 | 680/NKWSMD | 31/05/2022 | 12/06/2022 | THE ELECTRIC SPHERE | 4.98 | 0.79 | 15.8 | 95
Total | [13 empty] | 105.67 | 98.58 | 93.29