## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Augmentation of Neorakhola Water Supply Scheme for extending FHTC Facility to the enroute habitations under Kalimpong Block-I & Block-II under Neorakhola W/S & Mtc Division ,PHE Dte., Kalimpong | SM/10052 | Augmentation | Laying of 406.5 mm OD M.S pipe from ch no 100 to 150 (1500 meters) between thockchu source to Algarah V notch including the carriage of pipe, cleaning & painting of pipe surface (inner & outer surface) , construction of R.C.C thrust block along the stretch under Neorakhola water supply & Mtc Division, PHE Dte Kalimpong. | Assistant Engineer I | Junior Engineer IV | ORD/000130/2021-2022 | 763/NKWSMD | 28/02/2022 | 27/08/2022 | SONAM TOPGAY BHUTIA | 70.73 | 0 | 0 | 0
2 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Augmentation of Neorakhola Water Supply Scheme for extending FHTC Facility to the enroute habitations under Kalimpong Block-I & Block-II under Neorakhola W/S & Mtc Division ,PHE Dte., Kalimpong | SM/10052 | Augmentation | Laying of 406.5 mm OD M.S pipe from ch no 150 to 200 (1500 meters) between Thockchu source to Algarah V notch including the carriage of pipe, cleaning & painting of pipe surface (inner & outer surface), construction of R.C.C thrust block along the stretch under Neorakhola water supply & Mtc Division, PHE Dte Kalimpong. | Assistant Engineer I | Junior Engineer IV | ORD/000131/2021-2022 | 764/NKWSMD | 28/02/2022 | 27/08/2022 | HEMANT MOKTAN | 70.72 | 0 | 0 | 0
3 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Augmentation of Neorakhola Water Supply Scheme for extending FHTC Facility to the enroute habitations under Kalimpong Block-I & Block-II under Neorakhola W/S & Mtc Division ,PHE Dte., Kalimpong | SM/10052 | Augmentation | Laying of 406.5 mm OD M.S pipe from ch no 200 to 262 (1860 meters) between thockchu source to Algarah V notch including the carriage of pipe, cleaning & painting of pipe surface (inner & outer surface) , construction of R.C.C thrust block along the stretch under Neorakhola water supply & Mtc Division ,PHE Dte Kalimpong. | Assistant Engineer I | Junior Engineer IV | ORD/000132/2021-2022 | 765/NKWSMD | 28/02/2022 | 27/08/2022 | JUSTINE BHUTIA | 91.64 | 0 | 0 | 0
4 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Augmentation of Neorakhola Water Supply Scheme for extending FHTC Facility to the enroute habitations under Kalimpong Block-I & Block-II under Neorakhola W/S & Mtc Division ,PHE Dte., Kalimpong | SM/10052 | Augmentation | Laying of 406.5 mm OD M.S pipe from thukchu source to ch no 50 (1500 meters) between thockchu source to Alagarah V notch including the carriage of pipe, cleaning & painting of pipe surface (inner & outer surface) , construction of R.C.C thrust block along the stretch under Neorakhola water supply & Mtc Division ,PHE Dte Kalimpong. | Assistant Engineer I | Junior Engineer IV | ORD/000128/2021-2022 | 761/NKWSMD | 28/02/2022 | 27/08/2022 | SONAM TOPGAY BHUTIA | 72.76 | 0 | 0 | 0
5 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Augmentation of Neorakhola Water Supply Scheme for extending FHTC Facility to the enroute habitations under Kalimpong Block-I & Block-II under Neorakhola W/S & Mtc Division ,PHE Dte., Kalimpong | SM/10052 | Augmentation | Laying of 406.5 mm OD M.S pipe from ch no 50 to ch no 100 (1500 meters) between lava to thockchu including the carriage of pipe, cleaning & painting of pipe surface (inner & outer surface) , construction of R.C.C thrust block along the stretch under Neorakhola water supply & Mtc Division, PHE Dte Kalimpong. | Assistant Engineer II | Junior Engineer III | ORD/000123/2021-2022 | 756/NKWSMD | 28/02/2022 | 27/08/2022 | DAWA LAMA | 71.25 | 0 | 0 | 0
6 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Augmentation of Neorakhola Water Supply Scheme for extending FHTC Facility to the enroute habitations under Kalimpong Block-I & Block-II under Neorakhola W/S & Mtc Division ,PHE Dte., Kalimpong | SM/10052 | Augmentation | Laying of 406.5 mm OD M.S pipe from ch no 150 to ch no 200 (1500 meters) between lava to thockchu including the carriage of pipe, cleaning & painting of pipe surface (inner & outer surface), construction of R.C.C thrust block along the stretch under Neorakhola water supply & Mtc Division ,PHE Dte Kalimpong. | Assistant Engineer II | Junior Engineer III | ORD/000125/2021-2022 | 758/NKWSMD | 28/02/2022 | 27/08/2022 | THUPDEN BHUTIA | 73.05 | 0 | 0 | 0
7 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Augmentation of Neorakhola Water Supply Scheme for extending FHTC Facility to the enroute habitations under Kalimpong Block-I & Block-II under Neorakhola W/S & Mtc Division ,PHE Dte., Kalimpong | SM/10052 | Augmentation | Laying of 406.5 mm OD M.S pipe from ch no 262 to Algarah v notch (1890 meters) between thukchu source to Algarah V notch including the carriage of pipe, cleaning & painting of pipe surface (inner & outer surface) , construction of R.C.C thrust block along the stretch of Neorakhola water supply & Mtc Division, PHE Dte Kalimpong | Assistant Engineer I | Junior Engineer IV | ORD/000133/2021-2022 | 766/NKWSMD | 28/02/2022 | 27/08/2022 | JUSTINE BHUTIA | 92.4 | 0 | 0 | 0
8 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Augmentation of Neorakhola Water Supply Scheme for extending FHTC Facility to the enroute habitations under Kalimpong Block-I & Block-II under Neorakhola W/S & Mtc Division ,PHE Dte., Kalimpong | SM/10052 | Augmentation | Providing Protection & Restoration work of abutments including repair & maintenance of structural members of steel bridge no 33 to 40 from dolay transit camp towards lava (ch no 303 to 395) ,under Neorakhola Water Supply & Mtc Division ,PHE Dte Kalimpong. | Assistant Engineer I | Junior Engineer III | ORD/000138/2021-2022 | 771/NKWSMD | 28/02/2022 | 27/08/2022 | JUSTINE BHUTIA | 74.38 | 74.04 | 99.55 | 75
9 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Augmentation of Neorakhola Water Supply Scheme for extending FHTC Facility to the enroute habitations under Kalimpong Block-I & Block-II under Neorakhola W/S & Mtc Division ,PHE Dte., Kalimpong | SM/10052 | Augmentation | Providing Protection & Restoration work of abutments including repair & maintenance of structural members of steel bridge no 10 to 17 from Dhaula source towards lava (ch no 14 to 104) ,under Neorakhola Water Supply & Mtc Division ,PHE Dte Kalimpong. |  | Junior Engineer III | ORD/000135/2021-2022 | 768/NKWSMD | 28/02/2022 | 27/08/2022 | BHUTIA AND SONS | 86.41 | 80.57 | 93.24 | 85
10 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Augmentation of Neorakhola Water Supply Scheme for extending FHTC Facility to the enroute habitations under Kalimpong Block-I & Block-II under Neorakhola W/S & Mtc Division ,PHE Dte., Kalimpong | SM/10052 | Augmentation | Providing Protection & Restoration work of abutments including repair & maintenance of structural members of steel bridge no 18 to 24 from Dhaula source towards lava (ch no 104 to 194) ,under Neorakhola Water Supply & Mtc Division, PHE Dte Kalimpong. |  | Junior Engineer III | ORD/000136/2021-2022 | 769/NKWSMD | 28/02/2022 | 27/08/2022 | THUPDEN BHUTIA | 86.63 | 72.16 | 83.3 | 80
11 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Augmentation of Neorakhola Water Supply Scheme for extending FHTC Facility to the enroute habitations under Kalimpong Block-I & Block-II under Neorakhola W/S & Mtc Division ,PHE Dte., Kalimpong | SM/10052 | Augmentation | Providing Protection & Restoration work of abutments including repair & maintenance of structural members of steel bridge no 25 to 32 from Dhaula source towards lava (ch no 194 to 284) ,under Neorakhola Water Supply & Mtc Division ,PHE Dte Kalimpong. |  | Junior Engineer III | ORD/000137/2021-2022 | 770/NKWSMD | 28/02/2022 | 27/08/2022 | DAWA LAMA | 86.29 | 64.93 | 75.24 | 80
12 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Augmentation of Neorakhola Water Supply Scheme for extending FHTC Facility to the enroute habitations under Kalimpong Block-I & Block-II under Neorakhola W/S & Mtc Division ,PHE Dte., Kalimpong | SM/10052 | Augmentation | Providing Protection & Restoration work of abutments including repair & maintenance of structural members of steel bridge no 1 to 9 from Neora source towards Dhalua source (ch no -29 to 219), under Neorakhola Water Supply & Mtc Division ,PHE Dte Kalimpong. | Assistant Engineer II | Junior Engineer III | ORD/000134/2021-2022 | 767/NKWSMD | 28/02/2022 | 27/08/2022 | DHURBA KUMAR PRADHAN | 98.22 | 98.1 | 99.88 | 100
13 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Augmentation of Neorakhola Water Supply Scheme for extending FHTC Facility to the enroute habitations under Kalimpong Block-I & Block-II under Neorakhola W/S & Mtc Division ,PHE Dte., Kalimpong | SM/10052 | Augmentation | Laying of 406.5 mm OD M.S pipe from ch no 200 to ch no 250 (1500 meters) between lava to thockchu including the carriage of pipe, cleaning & painting of pipe surface (inner & outer surface) , construction of R.C.C thrust block along the stretch under Neorakhola water supply & Mtc Division, PHE Dte Kalimpong. |  | Junior Engineer III | ORD/000126/2021-2022 | 759/NKWSMD | 28/02/2022 | 27/08/2022 | KUMAR THAPA | 73.24 | 0 | 0 | 0
14 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Augmentation of Neorakhola Water Supply Scheme for extending FHTC Facility to the enroute habitations under Kalimpong Block-I & Block-II under Neorakhola W/S & Mtc Division ,PHE Dte., Kalimpong | SM/10052 | Augmentation | Laying of 406.5 mm OD M.S pipe from ch no 250 to thukchu source (1500 meters) between lava to thockchu including the carriage of pipe, cleaning & painting of pipe surface (inner & outer surface) , construction of R.C.C thrust block along the stretch under Neorakhola water supply & Mtc Division ,PHE Dte Kalimpong. |  | Junior Engineer III | ORD/000127/2021-2022 | 760/NKWSMD | 28/02/2022 | 27/08/2022 | BINOD TAMANG | 73.24 | 0 | 0 | 0
15 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Augmentation of Neorakhola Water Supply Scheme for extending FHTC Facility to the enroute habitations under Kalimpong Block-I & Block-II under Neorakhola W/S & Mtc Division ,PHE Dte., Kalimpong | SM/10052 | Augmentation | Laying of 406.5 mm OD M.S pipe from ch no 50 to 100 (1500 meters) between thockchu source to Algarah V notch including the carriage of pipe, cleaning & painting of pipe surface (inner & outer surface), construction of R.C.C thrust block along the stretch under Neorakhola water supply & Mtc Division ,PHE Dte Kalimpong. | Assistant Engineer I | Junior Engineer IV | ORD/000129/2021-2022 | 762/NKWSMD | 28/02/2022 | 27/08/2022 | SANJAY GURUNG | 72.79 | 0 | 0 | 0
16 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Augmentation of Neorakhola Water Supply Scheme for extending FHTC Facility to the enroute habitations under Kalimpong Block-I & Block-II under Neorakhola W/S & Mtc Division ,PHE Dte., Kalimpong | SM/10052 | Augmentation | Laying of 406.5 mm OD M.S pipe from Off take structure to ch no 50 (1500 meters) between lava to thockchu including the carriage of pipe, cleaning & painting of pipe surface (inner & outer surface), construction of R.C.C thrust block along the stretch under Neorakhola water supply & Mtc Division, PHE Dte Kalimpong. |  | Junior Engineer III | ORD/000122/2021-2022 | 755/NKWSMD | 28/02/2022 | 27/08/2022 | DHURBA KUMAR PRADHAN | 71.47 | 0 | 0 | 0
17 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Augmentation of Neorakhola Water Supply Scheme for extending FHTC Facility to the enroute habitations under Kalimpong Block-I & Block-II under Neorakhola W/S & Mtc Division ,PHE Dte., Kalimpong | SM/10052 | Augmentation | Providing Protection & Restoration work of abutments including repair & maintenance of structural members of steel bridge no 59 & 66 from saddle back towards thokchu (ch no-183 -300) under Neorakhola Water Supply & Mtc Division, PHE Dte Kalimpong. | Assistant Engineer II | Junior Engineer IV | ORD/000141/2021-2022 | 774/NKWSMD | 28/02/2022 | 27/08/2022 | BINOD TAMANG | 50.59 | 20.31 | 40.14 | 47
18 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Augmentation of Neorakhola Water Supply Scheme for extending FHTC Facility to the enroute habitations under Kalimpong Block-I & Block-II under Neorakhola W/S & Mtc Division ,PHE Dte., Kalimpong | SM/10052 | Augmentation | Providing Protection & Restoration work of abutments including repair & maintenance of structural members of steel bridge no 41 to 47 from dolay transit camp towards lava (ch no 395 to 487) ,under Neorakhola Water Supply & Mtc Division ,PHE Dte Kalimpong. |  | Junior Engineer III | ORD/000139/2021-2022 | 772/NKWSMD | 28/02/2022 | 27/08/2022 | MOHAN KR. RAI | 74.69 | 56.73 | 75.95 | 80
19 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Augmentation of Neorakhola Water Supply Scheme for extending FHTC Facility to the enroute habitations under Kalimpong Block-I & Block-II under Neorakhola W/S & Mtc Division ,PHE Dte., Kalimpong | SM/10052 | Augmentation | Laying of 406.5 mm OD M.S pipe from ch no 100 to ch no 150 (1500 meters) between lava to thockchu including the carriage of pipe, cleaning & painting of pipe surface (inner & outer surface), construction of R.C.C thrust block along the stretch under Neorakhola water supply & Mtc Division ,PHE Dte Kalimpong. |  | Junior Engineer III | ORD/000124/2021-2022 | 757/NKWSMD | 28/02/2022 | 27/08/2022 | MOHAN KUMAR RAI | 71.21 | 0 | 0 | 0
20 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Augmentation of Neorakhola Water Supply Scheme for extending FHTC Facility to the enroute habitations under Kalimpong Block-I & Block-II under Neorakhola W/S & Mtc Division ,PHE Dte., Kalimpong | SM/10052 | Augmentation | Providing Protection & Restoration work of abutments including repair & maintenance of structural members of steel bridge no 48 to 54 from dolay transit camp towards lava (ch no 520 to 612) ,under Neorakhola Water Supply & Mtc Division ,PHE Dte Kalimpong. |  | Junior Engineer III | ORD/000140/2021-2022 | 773/NKWSMD | 28/02/2022 | 27/08/2022 | KUMAR THAPA | 82.45 | 59.32 | 71.95 | 71
21 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Augmentation of Neorakhola Water Supply Scheme for extending FHTC Facility to the enroute habitations under Kalimpong Block-I & Block-II under Neorakhola W/S & Mtc Division ,PHE Dte., Kalimpong | SM/10052 | Augmentation | Replacement of 3 nos Damaged Steel Bridge with 3 nos New Steel bridge of 20m Span in between Ch no 252-253, 35 m span steel bridge in between chain no.04 to 05 and new tubular steel bridge of 20m span at chain no 63, namly (bridge no-64, bridge no-55 and bridge no-57) resting over concrete abutment on both the sides including construction of slope protection works for abutments under Neorakhola Water Supply Scheme under PHE Dte. | Assistant Engineer II | Junior Engineer IV | ORD/000004/2022-2023 | 103/NKWSMD | 13/04/2022 | 10/10/2022 | DHURBA KUMAR PRADHAN | 169.64 | 46.27 | 27.27 | 47
22 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Augmentation of Neorakhola Water Supply Scheme for extending FHTC Facility to the enroute habitations under Kalimpong Block-I & Block-II under Neorakhola W/S & Mtc Division ,PHE Dte., Kalimpong | SM/10052 | Augmentation | Replacement of existing RCC bridge locally known as OLD English Bridge Bridge No 70 with New Steel bridge of 20m Span in between chain no-129 to 130 Span resting over concrete abutment on both the sides including construction of slope protection works for abutments under Neorakhola Water Supply Scheme under PHE Dte, Kalimpong | Assistant Engineer I | Junior Engineer IV | ORD/000005/2022-2023 | 104/NKWSMD | 13/04/2022 | 10/10/2022 | JUSTINE BHUTIA | 50.25 | 0 | 0 | 99
23 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Augmentation of Neorakhola Water Supply Scheme for extending FHTC Facility to the enroute habitations under Kalimpong Block-I & Block-II under Neorakhola W/S & Mtc Division ,PHE Dte., Kalimpong | SM/10052 | Augmentation | Replacement of 4 nos Damaged Steel Bridge with 3 nos New Steel bridge of 15m span in between ch no-119-120 (Bridge no-58), steel bridge 10m span chain no ¿ 144 (Bridge no-69) new tubular Steel bridge of 10m span in between ch no-95 (Bridge no-61) and construction of RCC bridge at ch no-92 in place of bridge no 15(Dhalua to Dolay), including resting over concrete abutment on both the sides including construction of slope protection works for abutments under Neorakhola Water Supply Scheme under PHE Dte. | Assistant Engineer I | Junior Engineer III | ORD/000006/2022-2023 | 105/NKWSMD | 13/04/2022 | 10/10/2022 | THUPDEN BHUTIA | 173.91 | 25 | 14.38 | 90
24 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Augmentation of Neorakhola Water Supply Scheme for extending FHTC Facility to the enroute habitations under Kalimpong Block-I & Block-II under Neorakhola W/S & Mtc Division ,PHE Dte., Kalimpong | SM/10052 | Augmentation | (Continuation) Hiring of Vehicle for the Office of the Superintending Engineer, G.T.A-Circle, Public Health Engineering Directorate for the period of 6 (Six) Months, other than G.T.A Area from 01/02/2024 to 31/07/2024. Note: With effect from the date of issuing work order. | Assistant Engineer II | Junior Engineer I | ORD/000292/2023-2024 | 170/NKWSMD | 31/01/2024 | 29/07/2024 | SUJIT DEB | 0.99 | 0 | 0 | 0
25 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Augmentation of Neorakhola Water Supply Scheme for extending FHTC Facility to the enroute habitations under Kalimpong Block-I & Block-II under Neorakhola W/S & Mtc Division ,PHE Dte., Kalimpong | SM/10052 | Augmentation | (Continuation) Hiring of Vehicle for the Office of the Superintending Engineer, G.T.A-Circle, Public Health Engineering Directorate for the period of 6 (Six) Months for G.T.A Area from 01/02/2024 to 31/07/2024. Note: With effect from the date of issuing work order. |  |  | ORD/000330/2023-2024 | 169/NKWSMD | 31/01/2024 | 29/07/2024 | YAMA CONSTRUCTIONS LLP | 0.99 | 0 | 0 | 0
Total | [13 empty] | 1939.94 | 597.42 | 30.8