## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W | SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD - GIS drawing incl. preparation of project Report for Village : Upper Tanek piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | Assistant Engineer I | Junior Engineer I | ORD/000093/2021-2022 | 371/NKWSMD | 31/12/2021 | 30/01/2022 | LEMNISCATE | 4.29 | 0 | 0 | 0
2 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W | SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD - GIS drawing incl. preparation of project Report for Village : Seokbir Khasmahal piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | Assistant Engineer I | Junior Engineer I | ORD/000092/2021-2022 | 370/NKWSMD | 31/12/2021 | 30/01/2022 | LEMNISCATE | 4.64 | 0 | 0 | 0
3 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W | SM/10140 | Support-M&E | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS)/ layout of plan of the zone-wise Command area of water distribution and transmission network (WD&TN) showing all requisite design (physical) features,Preparation of piped network & design of pipe network &Preparation & Submission of DPR booklet of PWSS all complete in consultation with PHED in Upper & Lower Pochak, Majong Dara in GItdabling GP under Block-Kalimpong-I Kalimpong District under Neorakhola water Supply & Maintenance Division PHE Dte. | Assistant Engineer I | Junior Engineer IV | ORD/000207/2021-2022 | 284/NKWSMD | 23/11/2021 | 23/12/2021 | CIVIL ENGINEERING CONSULTANCY | 2.3 | 2.29 | 99.81 | 0
4 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W | SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD - GIS drawing incl. preparation of project Report for Village : Riayang Railway Station piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | Assistant Engineer I | Junior Engineer I | ORD/000079/2021-2022 | 357/NKWSMD | 31/12/2021 | 15/01/2022 | GOUTAM KUMAR BHADURI | 3.5 | 3.08 | 88.09 | 0
5 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W | SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD - GIS drawing incl. preparation of project Report for Village : Nobgaon Khasmahal piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | Assistant Engineer I | Junior Engineer I | ORD/000085/2021-2022 | 363/NKWSMD | 31/12/2021 | 30/01/2022 | LEMNISCATE | 4.43 | 4.43 | 100 | 0
6 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W | SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD - GIS drawing incl. preparation of project Report for Village : Nimbong Khasmahal piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | Assistant Engineer I | Junior Engineer I | ORD/000087/2021-2022 | 365/NKWSMD | 31/12/2021 | 30/01/2022 | M/S R. DUTTA & CO. | 4.9 | 4.9 | 100 | 0
7 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W | SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD - GIS drawing incl. preparation of project Report for Village : Kankaebong Khasmahal piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | Assistant Engineer I | Junior Engineer I | ORD/000088/2021-2022 | 366/NKWSMD | 31/12/2021 | 30/01/2022 | LEMNISCATE | 4.14 | 4.14 | 100 | 0
8 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W | SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD - GIS drawing incl. preparation of project Report for Village : Bong Khasmahal piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | Assistant Engineer I | Junior Engineer I | ORD/000089/2021-2022 | 367/NKWSMD | 31/12/2021 | 30/01/2022 | LEMNISCATE | 4.57 | 4.57 | 100 | 100
9 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W | SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD - GIS drawing incl. preparation of project Report for Village :Yang Makum Khasmahal piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | Assistant Engineer I | Junior Engineer I | ORD/000094/2021-2022 | 372/NKWSMD | 31/12/2021 | 30/01/2022 | LEMNISCATE | 4.68 | 0 | 0 | 100
10 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W | SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD - GIS drawing incl. preparation of project Report for Village : Dalapchand Khasmahal piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | Assistant Engineer I | Junior Engineer I | ORD/000095/2021-2022 | 373/NKWSMD | 31/12/2021 | 30/01/2022 | LEMNISCATE | 4.5 | 0 | 0 | 100
11 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W | SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD - GIS drawing incl. preparation of project Report for Village : Lingsay Khasmahal piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | Assistant Engineer I | Junior Engineer I | ORD/000097/2021-2022 | 375/NKWSMD | 31/12/2021 | 30/01/2022 | ROY CHOWDHURY ASSOCIATES | 4.75 | 0 | 0 | 100
12 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W | SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD - GIS drawing incl. preparation of project Report for Village : sakiyong Khasmahal piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | Assistant Engineer I | Junior Engineer I | ORD/000100/2021-2022 | 378/NKWSMD | 31/12/2021 | 30/01/2022 | ROY CHOWDHURY ASSOCIATES | 4.82 | 0 | 0 | 100
13 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W | SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD - GIS drawing incl. preparation of project Report for Village : Chunabhatti Bazar D.I.F & Lish Forest piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | Assistant Engineer I | Junior Engineer IV | ORD/000077/2021-2022 | 355/NKWSMD | 31/12/2021 | 30/01/2022 | CIVIL ENGINEERING CONSULTANCY | 4.64 | 3.05 | 65.89 | 0
14 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W | SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD - GIS drawing incl. preparation of project Report for Village : Riyong Forest piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | Assistant Engineer I | Junior Engineer I | ORD/000080/2021-2022 | 358/NKWSMD | 31/12/2021 | 15/01/2022 | GOUTAM KUMAR BHADURI | 3.42 | 2.77 | 80.75 | 0
15 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W | SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD - GIS drawing incl. preparation of project Report for Village :Suntalay Khasmahal piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | Assistant Engineer I | Junior Engineer IV | ORD/000081/2021-2022 | 359/NKWSMD | 31/12/2021 | 15/01/2022 | A3D A CIVIL ENGINEERING CONSULTANCY | 3.93 | 2.8 | 71.36 | 0
16 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W | SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD - GIS drawing incl. preparation of project Report for Village : Bhalukhop Khasmahal piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | Assistant Engineer I | Junior Engineer I | ORD/000090/2021-2022 | 368/NKWSMD | 31/12/2021 | 30/01/2022 | LEMNISCATE | 4.93 | 0 | 0 | 100
17 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W | SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD - GIS drawing incl. preparation of project Report for Village : Samalbong Khasmahal piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | Assistant Engineer I | Junior Engineer I | ORD/000091/2021-2022 | 369/NKWSMD | 31/12/2021 | 30/01/2022 | LEMNISCATE | 4.5 | 4.5 | 100 | 0
18 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W | SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD - GIS drawing incl. preparation of project Report for Village : Lolay Khasmahal piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | Assistant Engineer I | Junior Engineer I | ORD/000098/2021-2022 | 376/NKWSMD | 31/12/2021 | 30/01/2022 | ROY CHOWDHURY ASSOCIATES | 4.21 | 0 | 0 | 100
19 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W | SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD - GIS drawing incl. preparation of project Report for Village : paiyong Khasmahal piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | Assistant Engineer I | Junior Engineer I | ORD/000099/2021-2022 | 377/NKWSMD | 31/12/2021 | 30/01/2022 | ROY CHOWDHURY ASSOCIATES | 4.97 | 0 | 0 | 100
20 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W | SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD - GIS drawing incl. preparation of project Report for Village :Santuk Khasmahal piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | Assistant Engineer I | Junior Engineer I | ORD/000101/2021-2022 | 379/NKWSMD | 31/12/2021 | 30/01/2022 | ROY CHOWDHURY ASSOCIATES | 4.79 | 0 | 0 | 100
21 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W | SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD - GIS drawing incl. preparation of project Report for Village : Mayrong piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | Assistant Engineer I | Junior Engineer IV | ORD/000082/2021-2022 | 360/NKWSMD | 31/12/2021 | 15/01/2022 | CIVIL ENGINEERING CONSULTANCY | 3.35 | 3.35 | 100 | 0
22 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W | SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD - GIS drawing incl. preparation of project Report for Village : Pudung Khasmahal piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | Assistant Engineer I | Junior Engineer I | ORD/000083/2021-2022 | 361/NKWSMD | 31/12/2021 | 30/01/2022 | M/S R. DUTTA & CO. | 4.64 | 4.64 | 100 | 100
23 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W | SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD - GIS drawing incl. preparation of project Report for Village : Pemling Khasmahal piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | Assistant Engineer I | Junior Engineer I | ORD/000086/2021-2022 | 364/NKWSMD | 31/12/2021 | 30/01/2022 | M/S R. DUTTA & CO. | 4.4 | 4.4 | 100 | 100
24 | KALIMPONG |  | Resource | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W | SM/10140 | Support-M&E | Formal order for Preparation of DPR for Schemes under Jal Jeevan Mission in West Bengal. |  |  | ORD/000082/2021-2022 | 1997/RS | 03/11/2021 | 02/05/2022 | NABCONS PRIVATE LIMITED | 5500 | 17.28 | 0.31 | 80
25 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W | SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD - GIS drawing incl. preparation of project Report for Village : Paringar Khasmahal piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | Assistant Engineer I | Junior Engineer I | ORD/000084/2021-2022 | 362/NKWSMD | 31/12/2021 | 30/01/2022 | M/S R. DUTTA & CO. | 4.61 | 4.61 | 100 | 0
26 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W | SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD - GIS drawing incl. preparation of project Report for Village : Lingsaykha Khasmahal piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | Assistant Engineer I | Junior Engineer I | ORD/000096/2021-2022 | 374/NKWSMD | 31/12/2021 | 30/01/2022 | LEMNISCATE | 4.57 | 0 | 0 | 100
27 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W | SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD - GIS drawing incl. preparation of project Report for Village : samethar Khasmahal piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | Assistant Engineer I | Junior Engineer IV | ORD/000078/2021-2022 | 356/NKWSMD | 31/12/2021 | 30/01/2022 | CIVIL ENGINEERING CONSULTANCY | 4.78 | 3.85 | 80.51 | 0
28 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W | SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD GIS drawing incl. preparation of project Report for Village : Upper Echhay piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | Assistant Engineer I | Junior Engineer IV | ORD/000206/2021-2022 | 948/NKWSMD | 31/03/2022 | 30/04/2022 | A3D A CIVIL ENGINEERING CONSULTANCY | 4.47 | 0 | 0 | 0
29 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W | SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD GIS drawing incl. preparation of project Report for Village : Kaffir Khasmahal piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | Assistant Engineer I | Junior Engineer IV | ORD/000195/2021-2022 | 913/NKWSMD | 31/03/2022 | 30/04/2022 | CIVIL ENGINEERING CONSULTANCY | 4.11 | 0 | 0 | 0
30 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W | SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD GIS drawing incl. preparation of project Report for Village : Mansong Chinchona Plantation piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | Assistant Engineer I | Junior Engineer IV | ORD/000201/2021-2022 | 922/NKWSMD | 31/03/2022 | 30/04/2022 | CIVIL ENGINEERING CONSULTANCY | 4.47 | 0 | 0 | 0
31 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W | SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD ¿ GIS drawing incl. preparation of project Report for Village : Lava- Gitbeong Khasmahal piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | Assistant Engineer I | Junior Engineer IV | ORD/000198/2021-2022 | 918/NKWSMD | 31/03/2022 | 30/04/2022 | CIVIL ENGINEERING CONSULTANCY | 4.11 | 4.11 | 100 | 0
32 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W | SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD ¿ GIS drawing incl. preparation of project Report for Village : Palla Khasmahal piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | Assistant Engineer I | Junior Engineer IV | ORD/000199/2021-2022 | 919/NKWSMD | 31/03/2022 | 30/04/2022 | A3D A CIVIL ENGINEERING CONSULTANCY | 3.75 | 3.27 | 87.04 | 0
33 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W | SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD ¿ GIS drawing incl. preparation of project Report for Village : Pedong Khasmahal piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | Assistant Engineer I | Junior Engineer IV | ORD/000200/2021-2022 | 920/NKWSMD | 31/03/2022 | 30/04/2022 | CIVIL ENGINEERING CONSULTANCY | 4.47 | 4.47 | 100 | 0
34 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W | SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD ¿ GIS drawing incl. preparation of project Report for Village : Git Dubling Khasmahal piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. |  | Junior Engineer I | ORD/000202/2021-2022 | 928/NKWSMD | 31/03/2022 | 30/04/2022 | GOUTAM KUMAR BHADURI | 4.47 | 4.47 | 100 | 0
35 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W | SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD ¿ GIS drawing incl. preparation of project Report for Village : Suruk Khasmahal piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | Assistant Engineer I | Junior Engineer IV | ORD/000203/2021-2022 | 940/NKWSMD | 31/03/2022 | 30/04/2022 | CIVIL ENGINEERING CONSULTANCY | 3.75 | 3.75 | 100 | 0
36 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W | SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD ¿ GIS drawing incl. preparation of project Report for Village : Mazeok Forest piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | Assistant Engineer I | Junior Engineer IV | ORD/000205/2021-2022 | 938/NKWSMD | 31/03/2022 | 30/04/2022 | CIVIL ENGINEERING CONSULTANCY | 4.54 | 2.91 | 64.04 | 0
37 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W | SM/10140 | Support-M&E | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS)/ layout of plan of the zone-wise Command area of water distribution and transmission network (WD&TN) showing all requisite design (physical) features,Preparation of piped network & design of pipe network &Preparation & Submission of DPR booklet of PWSS all complete in consultation with PHED in Purba Kabigaon & Deurali(GP- Shamthar) , Tamyang(Part)(GP-Parbintar) in Block-Kalimpong-I Kalimpong District under Neorakhola water Supply & Maintenance Division PHE Dte. |  | Junior Engineer I | ORD/000208/2021-2022 | 283/NKWSMD | 31/03/2022 | 30/04/2022 | GOUTAM KUMAR BHADURI | 2.3 | 2.29 | 99.81 | 0
38 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W | SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD ¿ GIS drawing incl. preparation of project Report for Village : Rongpo Forest piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | Assistant Engineer I | Junior Engineer I | ORD/000188/2021-2022 | 923/NKWSMD | 31/03/2022 | 30/04/2022 | INDRANIL DUTTA & ASSOCIATES | 3.75 | 3.75 | 100 | 100
39 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W | SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD ¿ GIS drawing incl. preparation of project Report for Village : Ladam piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | Assistant Engineer I | Junior Engineer IV | ORD/000196/2021-2022 | 916/NKWSMD | 31/03/2022 | 30/04/2022 | CIVIL ENGINEERING CONSULTANCY | 3.75 | 3.75 | 100 | 0
40 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W | SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD ¿ GIS drawing incl. preparation of project Report for Village : Homes St. and Graihms piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | Assistant Engineer I | Junior Engineer IV | ORD/000204/2021-2022 | 933/NKWSMD | 31/03/2022 | 30/04/2022 | CIVIL ENGINEERING CONSULTANCY | 4.54 | 4.3 | 94.65 | 0
41 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W | SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD GIS drawing incl. preparation of project Report for Village : Kalimpong Khasmahal piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | Assistant Engineer I | Junior Engineer I | ORD/000190/2021-2022 | 912/NKWSMD | 31/03/2022 | 30/04/2022 | LEMNISCATE | 4.79 | 4.79 | 100 | 100
42 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W | SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD ¿ GIS drawing incl. preparation of project Report for Village : Mangwa Forest piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | Assistant Engineer I | Junior Engineer I | ORD/000192/2021-2022 | 945/ NKWSMD | 31/03/2022 | 30/04/2022 | INDRANIL DUTTA & ASSOCIATES | 3.21 | 0 | 0 | 100
43 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W | SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD GIS drawing incl. preparation of project Report for Village : Mong Pong Forest piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | Assistant Engineer I | Junior Engineer I | ORD/000191/2021-2022 | 914/NKWSMD | 31/03/2022 | 30/04/2022 | LEMNISCATE | 3.39 | 0 | 0 | 100
44 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W | SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD GIS drawing incl. preparation of project Report for Village : Singibong Khasmahal piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | Assistant Engineer I | Junior Engineer I | ORD/000193/2021-2022 | 942/NKWSMD | 31/03/2022 | 30/04/2022 | INDRANIL DUTTA & ASSOCIATES | 4.28 | 0 | 0 | 100
45 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W | SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD GIS drawing incl. preparation of project Report for Village : Yokprintam Khasmahal piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. |  | Junior Engineer I | ORD/000194/2021-2022 | 941/ NKWSMD | 31/03/2022 | 30/04/2022 | INDRANIL DUTTA & ASSOCIATES | 3.39 | 3.39 | 100 | 100
46 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W | SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD ¿ GIS drawing including preparation of project Report for Village: Kalimpong Dansong Forest Piped Water Supply Scheme as per latest Jal Jeevan Mission and WBPHED Norms under Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate, District-Kalimpong. | Assistant Engineer I | Junior Engineer IV | ORD/000281/2022-2023 | 01/NKWSMD | 01/04/2022 | 01/05/2022 | CIVIL ENGINEERING CONSULTANCY | 3.39 | 3.39 | 100 | 0
47 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W | SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD ¿ GIS drawing including preparation of project Report for Village: Kalimpong Rambi Bazar DIF Piped Water Supply Scheme as per latest Jal Jeevan Mission and WBPHED Norms under Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate, District-Kalimpong. | Assistant Engineer I | Junior Engineer IV | ORD/000282/2022-2023 | 11/NKWSMD | 04/04/2022 | 04/05/2022 | CIVIL ENGINEERING CONSULTANCY | 4.54 | 3.51 | 77.23 | 0
48 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W | SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD ¿ GIS drawing including preparation of project Report for Village: Kalimpong Teesta Bazar DIF Piped Water Supply Scheme as per latest Jal Jeevan Mission and WBPHED Norms under Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate, District-Kalimpong. | Assistant Engineer I | Junior Engineer IV | ORD/000283/2022-2023 | 64/NKWSMD | 11/04/2022 | 11/05/2022 | CIVIL ENGINEERING CONSULTANCY | 4.54 | 4.54 | 100 | 0
49 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W | SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD ¿ GIS drawing incl. preparation of project Report for Village : Sangser Khasmahal piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. |  | Junior Engineer III | ORD/000185/2021-2022 | 949/NKWSMD | 31/03/2022 | 30/04/2022 | SAMARTH INFRA TECH SERVICES PVT. LTD. | 4.58 | 4.58 | 100 | 0
50 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W | SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD ¿ GIS drawing incl. preparation of project Report for Village : Icha Khasmahal piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. |  | Junior Engineer III | ORD/000186/2021-2022 | 935/NKWSMD | 31/03/2022 | 30/04/2022 | SAMARTH INFRA TECH SERVICES PVT. LTD. | 4.48 | 4.48 | 100 | 0
51 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W | SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD ¿ GIS drawing incl. preparation of project Report for Village : Slokbhir Khasmahal piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. |  | Junior Engineer III | ORD/000187/2021-2022 | 939/NKWSMD | 31/03/2022 | 30/04/2022 | SAMARTH INFRA TECH SERVICES PVT. LTD. | 3.4 | 3.4 | 100 | 0
52 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W | SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD ¿ GIS drawing incl. preparation of project Report for Village : Singi Khasmahal piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. |  | Junior Engineer III | ORD/000184/2021-2022 | 937/NKWSMD | 31/03/2022 | 30/04/2022 | SAMARTH INFRA TECH SERVICES PVT. LTD. | 3.4 | 3.4 | 100 | 0
53 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W | SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD¿GIS drawing incl. preparation of project Report for Village::PANKHASARI KHASMAHAL(PART) Village piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | Assistant Engineer I | Junior Engineer IV | ORD/000249/2022-2023 | 25/AE-II/NKWSMD | 02/09/2022 | 02/10/2022 | CIVIL ENGINEERING CONSULTANCY | 3.43 | 3.43 | 100 | 0
54 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W | SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD¿GIS drawing incl. preparation of project Report for Village :Upper Rubek piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | Assistant Engineer I | Junior Engineer IV | ORD/000247/2022-2023 | 21/AE-II/NKWSMD | 02/09/2022 | 02/10/2022 | CIVIL ENGINEERING CONSULTANCY | 4.58 | 3.47 | 75.87 | 0
55 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W | SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD ¿ GIS drawing incl. preparation of project Report for Village :LAVA FOREST Village piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | Assistant Engineer I | Junior Engineer IV | ORD/000245/2022-2023 | 22/AE-II/NKWSMD | 02/09/2022 | 02/10/2022 | CIVIL ENGINEERING CONSULTANCY | 4.76 | 3.85 | 80.89 | 0
56 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W | SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD¿GIS drawing incl. preparation of project Report for Village :DUNGRA KHASMAHAL Village piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | Assistant Engineer I | Junior Engineer IV | ORD/000246/2022-2023 | 23/AE-II/NKWSMD | 02/09/2022 | 02/10/2022 | CIVIL ENGINEERING CONSULTANCY | 4.65 | 4.65 | 99.96 | 0
57 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W | SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD¿GIS drawing incl. preparation of project Report for Village:TARZUM FOREST Village piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | Assistant Engineer I | Junior Engineer IV | ORD/000248/2022-2023 | 24/AE-II/NKWSMD | 02/09/2022 | 02/10/2022 | CIVIL ENGINEERING CONSULTANCY | 4.07 | 3.68 | 90.21 | 0
58 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W | SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD ¿ GIS drawing incl. preparation of project Report for Village : Kagay Khasmahal piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | Assistant Engineer I | Junior Engineer I | ORD/000189/2021-2022 | 915/NKWSMD | 31/03/2022 | 30/04/2022 | INDRANIL DUTTA & ASSOCIATES | 3.75 | 0 | 0 | 100
59 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W | SM/10140 | Support-M&E | Route survey & all related field works, Preparation and supply of geo-referenced CAD ¿ GIS drawing incl. preparation of project Report for Village : Kashone Khasmahal piped water supply Scheme as per latest JJM and WBPHED Noms under Neorakhola W/S & Mtc. Division, P.H.E Dte, District-Kalimpong. | Assistant Engineer I | Junior Engineer IV | ORD/000197/2021-2022 | 917/NKWSMD | 31/03/2022 | 30/04/2022 | CIVIL ENGINEERING CONSULTANCY | 4.65 | 4.65 | 100 | 0
Total | [13 empty] | 5742.99 | 170.9 | 2.98