## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision Of Drinking water from spring water source to sourceless schoolsunder Kalimpong Block I , Kalimpong Block II &Gorubathan Block in the District of Kalimpong Under Neorakhola water Suppply & Mtc. Division ,Kalimpong PHE Dte | SM/10214 | School | Creating gravity based Provision Of Drinking water from spring water source for gairigoan primary school dalim G.P under Gorubathan Block in the District of kalimpong under Neorakhola water Suppply Division ,Kalimpong PHE Dte. | Assistant Engineer I | Junior Engineer I | ORD/000156/2021-2022 | 593/NKWSMD | 10/02/2022 | 12/03/2022 | THE ELECTRIC SPHERE | 3.9 | 3.64 | 93.16 | 0
2 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision Of Drinking water from spring water source to sourceless schoolsunder Kalimpong Block I , Kalimpong Block II &Gorubathan Block in the District of Kalimpong Under Neorakhola water Suppply & Mtc. Division ,Kalimpong PHE Dte | SM/10214 | School | Creating gravity based Provision Of Drinking water from spring water source for Kumai Khas primary school in Samsing G.P under Gorubathan Block in the District of kalimpong under Neorakhola water Suppply Division ,Kalimpong PHE Dte. | Assistant Engineer I | Junior Engineer I | ORD/000157/2021-2022 | 594/NKWSMD | 10/02/2022 | 12/03/2022 | THE ELECTRIC SPHERE | 4.02 | 3.8 | 94.67 | 0
3 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision Of Drinking water from spring water source to sourceless schoolsunder Kalimpong Block I , Kalimpong Block II &Gorubathan Block in the District of Kalimpong Under Neorakhola water Suppply & Mtc. Division ,Kalimpong PHE Dte | SM/10214 | School | Creating gravity based Provision Of Drinking water from spring water source for 26 Numbers of school under Kalimpong Block 1 (Part -3) in the district of Kalimpong under Neorakhola water Suppply Division, Kalimpong PHE Dte | Assistant Engineer I | Junior Engineer IV | ORD/000116/2021-2022 | 748/NKWSMD | 28/02/2022 | 29/05/2022 | SONAM TOPGAY BHUTIA | 79.08 | 77.99 | 98.62 | 0
4 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision Of Drinking water from spring water source to sourceless schoolsunder Kalimpong Block I , Kalimpong Block II &Gorubathan Block in the District of Kalimpong Under Neorakhola water Suppply & Mtc. Division ,Kalimpong PHE Dte | SM/10214 | School | Creating gravity based Provision Of Drinking water from spring water source for 17 Numbers of school under Kalimpong Block 1 (Part -2) in the district of Kalimpong under Neorakhola water Suppply Division, Kalimpong PHE Dte | Assistant Engineer I | Junior Engineer IV | ORD/000115/2021-2022 | 747/NKWSMD | 28/02/2022 | 29/05/2022 | HEMANT MOKTAN | 79.35 | 74.73 | 94.18 | 0
5 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision Of Drinking water from spring water source to sourceless schoolsunder Kalimpong Block I , Kalimpong Block II &Gorubathan Block in the District of Kalimpong Under Neorakhola water Suppply & Mtc. Division ,Kalimpong PHE Dte | SM/10214 | School | Creating gravity based Provision Of Drinking water from spring water source for 28 Numbers of school under Kalimpong Block 1 (Part -1) in the district of Kalimpong under Neorakhola water Suppply Division, Kalimpong PHE Dte | Assistant Engineer I | Junior Engineer IV | ORD/000114/2021-2022 | 746/NKWSMD | 28/02/2022 | 29/05/2022 | JUSTINE BHUTIA | 82.43 | 80.06 | 97.13 | 90
6 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision Of Drinking water from spring water source to sourceless schoolsunder Kalimpong Block I , Kalimpong Block II &Gorubathan Block in the District of Kalimpong Under Neorakhola water Suppply & Mtc. Division ,Kalimpong PHE Dte | SM/10214 | School | Additional works in connection with Creating gravity based Provision Of Drinking water from spring water source for 15 number of Schools under Gorubathan Block (Part -1) in the District of Kalimpong under Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate, Kalimpong. |  | Junior Engineer I | ORD/000396/2022-2023 | 1157/NKWSMD | 16/08/2022 | 15/09/2022 | ASHIT RAI | 4.85 | 0 | 0 | 0
7 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision Of Drinking water from spring water source to sourceless schoolsunder Kalimpong Block I , Kalimpong Block II &Gorubathan Block in the District of Kalimpong Under Neorakhola water Suppply & Mtc. Division ,Kalimpong PHE Dte | SM/10214 | School | Additional works in connection with Creating gravity based Provision Of Drinking water from spring water source for 12 number of Schools under Gorubathan Block (Part -1) in the District of Kalimpong under Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate, Kalimpong. |  | Junior Engineer I | ORD/000397/2022-2023 | 1158/NKWSMD | 16/08/2022 | 15/09/2022 | ASHIT RAI | 4.85 | 0 | 0 | 0
8 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision Of Drinking water from spring water source to sourceless schoolsunder Kalimpong Block I , Kalimpong Block II &Gorubathan Block in the District of Kalimpong Under Neorakhola water Suppply & Mtc. Division ,Kalimpong PHE Dte | SM/10214 | School | Creating gravity based Provision Of Drinking water from spring water source for 15 Numbers of school under Kalimpong Block II (Part -1) in the district of Kalimpong under Neorakhola water Suppply Division, Kalimpong PHE Dte | Assistant Engineer II | Junior Engineer III | ORD/000158/2021-2022 | 887/NKWSMD | 28/03/2022 | 26/06/2022 | MS. SURYA I PVT. LTD COMPANY | 93.6 | 73.32 | 78.34 | 85
9 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision Of Drinking water from spring water source to sourceless schoolsunder Kalimpong Block I , Kalimpong Block II &Gorubathan Block in the District of Kalimpong Under Neorakhola water Suppply & Mtc. Division ,Kalimpong PHE Dte | SM/10214 | School | Creating gravity based Provision Of Drinking water from spring water source for 34 Numbers of school under Mirik Sub-Division in the district of Darjeeling under Neorakhola water Suppply Division, Kalimpong PHE Dte | Assistant Engineer II | Junior Engineer III | ORD/000159/2021-2022 | 888/NKWSMD | 28/03/2022 | 26/06/2022 | MS. SURYA I PVT. LTD COMPANY | 107.23 | 77.12 | 71.92 | 80
10 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision Of Drinking water from spring water source to sourceless schoolsunder Kalimpong Block I , Kalimpong Block II &Gorubathan Block in the District of Kalimpong Under Neorakhola water Suppply & Mtc. Division ,Kalimpong PHE Dte | SM/10214 | School | Creating gravity based Provision Of Drinking water from spring water source for 36 Numbers of school under Kalimpong Block II (Part -3) in the district of Kalimpong under Neorakhola water Suppply Division, Kalimpong PHE Dte | Assistant Engineer I | Junior Engineer III | ORD/000118/2021-2022 | 751/NKWSMD | 28/02/2022 | 29/05/2022 | BINOD TAMANG | 130.7 | 101.45 | 77.62 | 70
11 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision Of Drinking water from spring water source to sourceless schoolsunder Kalimpong Block I , Kalimpong Block II &Gorubathan Block in the District of Kalimpong Under Neorakhola water Suppply & Mtc. Division ,Kalimpong PHE Dte | SM/10214 | School | Creating gravity based Provision Of Drinking water from spring water source for 34 Numbers of school under Gorubathan Block 1 (Part -1) in the district of Kalimpong under Neorakhola water Suppply Division, Kalimpong PHE Dte | Assistant Engineer I | Junior Engineer I | ORD/000119/2021-2022 | 752/NKWSMD | 28/02/2022 | 29/05/2022 | THUPDEN BHUTIA | 130.14 | 120.3 | 92.44 | 100
12 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision Of Drinking water from spring water source to sourceless schoolsunder Kalimpong Block I , Kalimpong Block II &Gorubathan Block in the District of Kalimpong Under Neorakhola water Suppply & Mtc. Division ,Kalimpong PHE Dte | SM/10214 | School | Creating gravity based Provision Of Drinking water from spring water source for 26 Numbers of school under Kalimpong Block II (Part -2) in the district of Kalimpong under Neorakhola water Suppply Division, Kalimpong PHE Dte | Assistant Engineer I | Junior Engineer III | ORD/000121/2021-2022 | 750/NKWSMD | 28/02/2022 | 29/05/2022 | JUSTINE BHUTIA | 87.87 | 53.17 | 60.51 | 70
Total | [13 empty] | 808.02 | 665.59 | 82.37