## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong - II | Neorakhola W/S & Mtc.Div. | Gravity based piped water supply scheme for Bokhim khasmahal & paygang khasmahal (PC) under Gitdabling G.P. Kalimpong Blick-II in the District of Kalimpong in connection under Neorakhola Water Supply & Maintenance Division, P.H.E Directorate. | SM/10562 | New | Creating Gravity based piped water supply scheme for Bokhim Khasmaha & Paygang Khasmal (PC) under Gitdabling G.P kalimpong Block -II in the district of Kalimpong in connection with JJM & Jal Swapna, under Neorakhola w/s & MtC Division , PHE Dte, Kalimpong | Assistant Engineer I | Junior Engineer IV | ORD/000036/2022-2023 | 501/NKWSMD | 24/05/2022 | 20/11/2022 | TIKARAM SHARMA | 126.49 | 66.02 | 52.2 | 85
Total | [13 empty] | 126.49 | 66.02 | 52.2