## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong -I | Neorakhola W/S & Mtc.Div. | Gravity based piped water supply scheme for pemling forest under Kaffer - Kankebong G.P. Kalimpong Block-I, Dist-Kalimpong in connection under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. | SM/10563 | New | The Supply, Installation, commissioning & Monitoring of "Non-Electrical Continuous Chlorinator" approved by Government of India & recommended by National Jal Jeevan Mission (NJJM) supplied through Piped Water Supply Schemes (PWSS) maintained by the Public Health Engineering Department (PHED) Government of West Bengal for a minimum period of 03 (Three) months in the District of Kalimpong under different Schemes (As per Schedule) Tentative number of units:6 Unit (Each Unit containing 2 no of Device) | Assistant Engineer II | Junior Engineer II | ORD/000046/2023-2024 | 259/NKWSMD | 15/05/2023 | 13/08/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 31.66 | 0 | 0 | 0
2 | KALIMPONG | Kalimpong -I | Neorakhola W/S & Mtc.Div. | Gravity based piped water supply scheme for pemling forest under Kaffer - Kankebong G.P. Kalimpong Block-I, Dist-Kalimpong in connection under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. | SM/10563 | New | Material Requisition To Resource Division |  |  | RTOR000094/2022-2023 | 1379/NKWSMD | 22/09/2022 |  | Resource Division | 0.21 | 0 | 0 | 0
3 | KALIMPONG | Kalimpong -I | Neorakhola W/S & Mtc.Div. | Gravity based piped water supply scheme for pemling forest under Kaffer - Kankebong G.P. Kalimpong Block-I, Dist-Kalimpong in connection under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. | SM/10563 | New | Creating Gravity based piped water supply scheme for Pemling Forest under Kaffer - Kankebong G.P kalimpong Block -I, Dist- Kalimpong inconnection with JJM & Jal Swapna, under Neorakhola w/s & MtC Division , PHE Dte, Kalimpong | Assistant Engineer I | Junior Engineer III | ORD/000068/2022-2023 | 575/NKWSMD | 26/05/2022 | 24/08/2022 | SANTOSH TAMANG | 57.25 | 17.19 | 30.02 | 50
Total | [13 empty] | 89.12 | 17.19 | 19.28