## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | Gravity based piped water supply scheme for Paren forest Village under Paten Godak GP in Gorubathan Block in connection with implementation in the district of Kalimpong under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. | SM/10576 | New | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED |  |  | BILL/00502/2023-2024 | BP-2023-24-302 | 09/11/2023 | 09/11/2023 | WEST BENGAL PARIVESH CAMPA | 5.25 | 0 | 0 | 0
2 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | Gravity based piped water supply scheme for Paren forest Village under Paten Godak GP in Gorubathan Block in connection with implementation in the district of Kalimpong under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. | SM/10576 | New | Creating gravity based Provision Of Drinking water from spring water source Paren forest village under Paten Godak Gram Panchayat under Gorubathan Block in the District of Kalimpong Under Neorakhola water Supply Division ,Kalimpong PHE Dte | Assistant Engineer I | Junior Engineer III | ORD/000064/2022-2023 | 571/NKWSMD | 26/05/2022 | 15/02/2024 | SACHIN RAI | 47.13 | 29.69 | 62.99 | 100
3 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | Gravity based piped water supply scheme for Paren forest Village under Paten Godak GP in Gorubathan Block in connection with implementation in the district of Kalimpong under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. | SM/10576 | New | PROPOSED 0.0607 HA LAND TO DIVERTED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR PAREN FOREST UNDER PATEN GODAK G.P. Block: GORUBATHAN, DISTRICT KALIMPONG |  |  | BILL/00280/2025-2026 |  | 24/09/2025 | 24/09/2025 | WEST BENGAL STATE FOREST DEVLOPMENT AGENCY | 1.27 | 0 | 0 | 0
Total | [13 empty] | 53.65 | 29.69 | 55.33