## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | Gravity based piped water supply scheme for Dalapchand slip reserve forest Village under Dalapchand GP in Kalimpong Block II in connecion with implementation in the district of Kalimpong under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. | SM/10601 | New | Creating gravity based Provision Of Drinking water from spring water source Dalapchand Slip reserve forest village under Dalapchand Gram Panchayat under Kalimpong Block - 1 in the District of Kalimpong Under Neorakhola water Supply Division ,Kalimpong PHE Dte PART (A) | Assistant Engineer I | Junior Engineer IV | ORD/000070/2022-2023 | 577/NKWSMD | 26/05/2022 | 25/06/2022 | SONAM TOPGAY BHUTIA | 4.7 | 3.91 | 83.18 | 95
2 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | Gravity based piped water supply scheme for Dalapchand slip reserve forest Village under Dalapchand GP in Kalimpong Block II in connecion with implementation in the district of Kalimpong under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. | SM/10601 | New | Creating gravity based Provision Of Drinking water from spring water source Dalapchand Slip reserve forest village under Dalapchand Gram Panchayat under Kalimpong Block - 1 in the District of Kalimpong Under Neorakhola water Supply Division ,Kalimpong PHE Dte (B) | Assistant Engineer II | Junior Engineer IV | ORD/000071/2022-2023 | 579/NKWSMD | 26/05/2022 | 25/06/2022 | SONAM TOPGAY BHUTIA | 4.79 | 4.79 | 100 | 100
Total | [13 empty] | 9.48 | 8.69 | 91.67