## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | Gravity based piped water supply scheme for Rissium forest Village under Santook GP in Kalimpong Block-II, in the District of Kalimpong in connecion with implementation under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. | SM/10602 | New | Creating gravity based Provision Of Drinking water from spring water source Rissium forest village under Santook Gram Panchayat under Kalimpong Block-II in the District of Kalimpong Under Neorakhola water Supply Division ,Kalimpong PHE Dte | Assistant Engineer I | Junior Engineer IV | ORD/000063/2022-2023 | 570/NKWSMD | 26/05/2022 | 24/08/2022 | DAWA TANGEE SHERPA | 21.57 | 0 | 0 | 80
Total | [13 empty] | 21.57 | 0 | 0