## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | Gravity based piped water supply scheme for Noam forest Village under Pokhriabong GP in Gorubathan Block in connecion with implementation in the district of Kalimpong under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. | SM/10603 | New | Creating gravity based Provision Of Drinking water from spring water source Noam forest village under Pokhriabong Gram Panchayat under Gorubathan Block in the District of Kalimpong Under Neorakhola water Supply Division ,Kalimpong PHE Dte | Assistant Engineer II | Junior Engineer III | ORD/000061/2022-2023 | 568/NKWSMD | 26/05/2022 | 24/08/2022 | PRAKASH TAMANG | 44.19 | 37.19 | 84.15 | 100
2 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | Gravity based piped water supply scheme for Noam forest Village under Pokhriabong GP in Gorubathan Block in connecion with implementation in the district of Kalimpong under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. | SM/10603 | New | Material Requisition To Resource Division |  |  | RTOR000101/2022-2023 | 1553/NKWSMD | 19/10/2022 | 19/10/2022 | Resource Division | 0.34 | 0 | 0 | 0
3 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | Gravity based piped water supply scheme for Noam forest Village under Pokhriabong GP in Gorubathan Block in connecion with implementation in the district of Kalimpong under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. | SM/10603 | New | The Supply, Installation, commissioning & Monitoring of "Non-Electrical Continuous Chlorinator" approved by Government of India & recommended by National Jal Jeevan Mission (NJJM) supplied through Piped Water Supply Schemes (PWSS) maintained by the Public Health Engineering Department (PHED) Government of West Bengal for a minimum period of 03 (Three) months in the District of Kalimpong under different Schemes (As per Schedule) Tentative number of units:6 Unit (Each Unit containing 2 no of Device) | Assistant Engineer II | Junior Engineer II | ORD/000046/2023-2024 | 259/NKWSMD | 15/05/2023 | 15/08/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 31.66 | 0 | 0 | 0
4 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | Gravity based piped water supply scheme for Noam forest Village under Pokhriabong GP in Gorubathan Block in connecion with implementation in the district of Kalimpong under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. | SM/10603 | New | PROPOSED 0.2609 HA LAND TO DIVERTED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR NAOM FOREST UNDER NIM G.P, Block : GORUBATHAN, DISTRICT:KALIMPONG |  |  | BILL/00722/2024-2025 |  | 31/01/2025 | 31/01/2025 | DIVISIONAL FOREST OFFICER | 4.16 | 0 | 0 | 0
Total | [13 empty] | 80.36 | 37.19 | 46.28