## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong - II | Neorakhola W/S & Mtc.Div. | Gravity based piped water supply scheme for Icha forest Village under Sangsey GP Kalimpong Block-II, in the District of Kalimpong in connecion with implementation under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. | SM/10624 | New | Creating gravity based Provision Of Drinking water from spring water source Icha forest village under Sangseer Gram Panchayat under Kalimpong Block - II in the District of Kalimpong Under Neorakhola water Supply Division ,Kalimpong PHE Dte | Assistant Engineer II | Junior Engineer III | ORD/000051/2022-2023 | 533/NKWSMD | 25/05/2022 | 23/08/2022 | SAINATH CONSTRUCTION COMPANY | 38.89 | 20.06 | 51.6 | 100
Total | [13 empty] | 38.89 | 20.06 | 51.6