## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | PROPOSED SURFACE WATER BASED YAKPRINTAM KHASMAHAL (part) PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. | SM/10635 | New | PROPOSED SURFACE WATER BASED YAKPRINTAM KHASMAHAL (part) PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. | Assistant Engineer I | Junior Engineer III | ORD/000139/2022-2023 | 830/NKWSMD | 30/06/2022 | 17/09/2024 | SANTOSH TAMANG | 127.14 | 119.03 | 93.62 | 95
2 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | PROPOSED SURFACE WATER BASED YAKPRINTAM KHASMAHAL (part) PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. | SM/10635 | New | Additional Work for Proposed Surface Water Based Yakprintam Khasmahal (Part) Piped Water Supply Scheme to accommodate Functional Household Tap Connection (FHTC) in Kalimpong-I, Block within Kalimpong District under Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate. | Assistant Engineer II | Junior Engineer III | ORD/000061/2024-2025 | 1325/NKWSMD | 29/07/2024 | 25/01/2025 | RELLI PALA CONSTRUCTION | 20.76 | 0 | 0 | 100
3 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | PROPOSED SURFACE WATER BASED YAKPRINTAM KHASMAHAL (part) PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. | SM/10635 | New | PROPOSED 0.0163 HA LAND TO BE DIVERTED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR YOKPRINTAM KHASMAHAL(PART) PIPED WATER SUPPLY SCHEME UNDER SAMTHAR G.P, BLOCK: KALIMPONG- II |  |  | BILL/00286/2025-2026 |  | 24/09/2025 | 24/09/2025 | WEST BENGAL STATE FOREST DEVLOPMENT AGENCY | 0.16 | 0 | 0 | 0
Total | [13 empty] | 148.07 | 119.03 | 80.39