## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FROM NEROLA JHORA TO LOWER ECHHEY UNDER KALIMPONG BLOCK - I UNDER JJM AND JAL SWAPNO PROGRAMME | SM/10694 | New | PIPED WATER SUPPLY SCHEME FROM NEROLA JHORA TO LOWER ECHHEY UNDER BLOCK-1 KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. |  |  | ORD/000040/2022-2023 | 522/NKWSMD | 25/05/2022 | 24/07/2022 | SRINIWAS AGARWAL | 84.96 | 55.95 | 65.85 | 70
2 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FROM NEROLA JHORA TO LOWER ECHHEY UNDER KALIMPONG BLOCK - I UNDER JJM AND JAL SWAPNO PROGRAMME | SM/10694 | New | Left out scheme from Nerola Jhora to Lower Ecchey Block- Kalimpong I, District Kalimpong in connection with Jal Jeevan Mission, under PHED Darjeeling Division-II GTA. |  |  | ORD/000003/2025-2026 | 453/NKWSMD | 02/04/2025 | 01/06/2025 | DIPENDRA CHETTRI | 8.12 | 0 | 0 | 0
Total | [13 empty] | 93.09 | 55.95 | 60.1