## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FROM AGINGAREY KHOLCHA TO 8 12 AND KHOTILINE UNDER GORUBATHAN BLOCK UNDER JJM AND JAL SWAPNO PROGRAMME | SM/10696 | New | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and writing the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour sample as will be supplied by Public Health Engineering Directorate by engaging skilled artist and helper artist in different location within 332 Villages in Different Block under Darjeeling and Kalimpong District under Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate all complete as per direction of EIC. In Each Village in 4 Locations tentatively, In Each Location (8 X 5= 40 Sq.Ft) Writing Area Required or as per the Dimension given by Public Health Engineering Directorate, Writing area should be Geo Tagged in appropriate portal as guided by Public Health Engineering Department. | Assistant Engineer II | Junior Engineer I,Junior Engineer IV | ORD/000294/2023-2024 | 179/AE-II/NKWSMD | 05/03/2024 | 05/04/2024 | RADIANT | 10 | 0 | 0 | 40
2 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FROM AGINGAREY KHOLCHA TO 8 12 AND KHOTILINE UNDER GORUBATHAN BLOCK UNDER JJM AND JAL SWAPNO PROGRAMME | SM/10696 | New | PIPED WATER SUPPLY SCHEME FROM AGINGAREY KHOLCHA TO 12,8 NO. & KOTHIDARA UNDER GORUBATHAN BLOCK KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. |  |  | ORD/000044/2022-2023 | 526/NKWSMD | 25/05/2022 | 21/11/2022 | MAHADEO PRASAD AGARWAL & CO | 97.89 | 80.87 | 82.62 | 100
Total | [13 empty] | 107.89 | 80.87 | 74.96