## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FROM DADALEY JHORA TO BURMAIK UNDER SANGSEY G.P BLOCK-II, KALIMPONG UNDER JJM AND JAL SWAPNO PROGRAMME | SM/10699 | New | PIPED WATER SUPPLY SCHEME FROM DADALEY JHORA TOBURMAIK UNDER SANGSEY G.P. BLOCK-II KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. |  |  | ORD/000046/2022-2023 | 528/NKWSMD | 25/05/2022 | 21/11/2022 | M/S. ASHOK KUMAR PERIWAL | 147.75 | 64.76 | 43.83 | 50
Total | [13 empty] | 147.75 | 64.76 | 43.83